## Slide 1: SA2 Work Planning
Puneet Jain
SA2 Chair
SA WG2 Meeting #147E (e-meeting) S2-2107759
Oct 18 – 22, 2021

## Slide 2: Rel-18 timelines
SA#92-e
Jun/2021
SA#93e
Sep/2021
SA#94-e
Dec/2021
SA#95
Mar/2022
SA#96
Jun/2022
SA#97
Sep/2022
SA#98
Dec/2022
SA#99
Mar/2023
R17
stage 2
freeze
R17
stage 3
freeze
R17 code
freeze
stage 1
100%;
SA2 SIDs prioritization
R18 stage 2
Functional freeze
R18 stage 3
freeze
stage 1
>= 80%; SA2 SIDs Discussion
SA#100
Jun/2023
SA
Rel-18
Workshop
RAN
Rel-18
Workshop
Rel-18
timeline
Rel-18
content agreed
Rel-17
Schedule
Rel-18
Planning
exceptions
S1 normative ongoing;
SA2 SID Discussion
SA#101
Sep/2023
SA#102
Dec/2023
Exceptions
(if any)
R18 stage 2
SID Completion
/WIDs Approval
SA#103
Mar/2024
R18 code
freeze
R18 Stage 2 Study Phase
R18 Stage 2 Normative Phase
TEI18 propsoal submission/approval
TEI18 handling
R18 Stage 2 Study Agreed/ Endorsed

## Slide 3: SA2 Meeting Planning
TSG
WG
WG
I
N
A
C
T
I
V
E
P
E
R
I
O
D
I
N
A
C
T
I
V
E
P
E
R
I
O
D
TSG
T
S
G
#
9
3 E
Planned as E-meetings
6-10
13-17
20-24
27-1
4-8
11-15
18-22
25-29
1-5
8-12
15-19
22-26
29-3
6-10
13-17
20-24
September
2021
October
2021
November
2021
December
2021
TBC in December (f2f or E-meeting)
WG
WG
TSG
January
2022
February
2022
17-21
24-28
31-04
07-11
14-18
21-25
March
2022
28-04
07-11
14-18
T
S
G
#
9
5
RAN1-E
(5+4)
RAN2/3
(5+4)
10-14
03-07
WG
WG
TSG
G
O
L
D
E
N
W
E
E
K
T
H
A
N
K
S
G
I
V
I
N
G
RAN1-E
(5+2)
RAN2/3
T
S
G
#
9
4
E
S
P
R
I
N
G
F
E
S
T
I
V
A
L
21-25
I
N
A
C
T
I
V
E
P
E
R
I
O
D
RAN1-E
(2+5)
RAN2/3
(5+2/3)
RAN1-E
(5+2)
INACTIVE
April
2022
May
2022
11-15
18-22
25-29
02-06
09-13
16-20
June
2022
23-27
30-3
6-10
20-24
28-01
13-17
04-08
T
S
G
#
9
6
RAN1-E
RAN2/3-E
I
N
A
C
T
I
V
E
P
E
R
I
O
D
#147E
(5)
#148E
(5)
#148ah
(5)
#149E
(5)
MED
(R18)
#149E
(5+5)
#150
(5)
#151
(5)
Option#1: 2x5 days e-meeting; Submission deadline #148ah (10-Jan); #149E (14-Feb); #148ah will have reduced agenda.
Option#2: 1x(5+5) days e-meeting; Submission deadline #149E (28-Jan);

## Slide 4
Stage 2 Rel-17 status
UID | Name | Acronym | WG | TCD | %
930019 | Architecture support for NB-IoT/eMTC Non-Terrestrial Networks in EPS | IoT_SAT_ARCH_EPS | S2 | 12/21 | 0%
930018 | Architecture Enhancement for NR Reduced Capability Devices | ARCH_NR_REDCAP | S2 | 12/21 | 20%
920062 | Stage 2 of MINT | MINT | S2 | 12/21 | 50%
900009 | Stage 2 for 5MBS | 5MBS | S2 | 09/21 | 85%
900015 | Stage 2 for eNPN | eNPN | S2 | 09/21 | 95%
870001 | Stage 2 of 5G_eLCS_ph2 | 5G_eLCS_ph2 | S2 | 09/21 | 95%
910021 | Stage 2 of eV2XARC_Ph2 | eV2XARC_Ph2 | S2 | 09/21 | 95%
900016 | Stage 2 of eEDGE_5GC | eEDGE_5GC | S2 | 09/21 | 95%
900011 | Stage 2 for Enhancement of Network Slicing Phase 2 | eNS_Ph2 | S2 | 09/21 | 97%
900014 | (Stage 2 of) Support of Uncrewed Aerial Systems Connectivity, Identification, and Tracking | ID_UAS | S2 | 09/21 | 98%
900013 | (Stgae 2 of) System enablers for Multi-USIM devices | MUSIM | S2 | 09/21 | 98%
900007 | Stage 2 for Proximity based Services in 5GS | 5G_ProSe | S2 | 09/21 | 98%
860005 | (Stage 2 of) Integration of satellite components in the 5G architecture | 5GSAT_ARCH | S2 | 09/21 | 99%
900010 | Stage 2 of eNA_Ph2 | eNA_Ph2 | S2 | 09/21 | 99%
870002 | Stage 2 of MPS2 | MPS2 | S2 | 06/21 | 99%
IIOT, 5G-AIS, ATSSS_Ph2 are 100% complete

## Slide 5: Input documents control
Rel-17 agenda items will be subjected to input document control
  Maximum 4 TDocs (CR) per company (as first author) per Rel-17 agenda item (as shown in the meeting agenda) will be handled. Since 5MBS is only 85% complete and requires major co-ordination with other WGs, maximum 7 TDocs (CR) per company (as first author) will be handled for 5MBS.
    This is inline with RAN2 Tdoc control, 1 TU -> 4 Tdocs; 2 TU -> 7 TDocs
  Any additional TDocs (CR) will be not be handled and removed from the initial Chair’s note.
  Following will not be counted towards the quota
    Contributions on RAN co-ordination SIDs - IoT_SAT_ARCH_EPS, ARCH_NR_REDCAP, MINT
    Multi-company contribution with 10 or more co-signers
    Any LS OUT and Discussion papers
    Any TDocs generated during the meeting
    Planning documents/status reports from the Rapporteur
For Rel-17 FASMO criterion will not be enforced in Q4.
  Rapporteur are encouraged to work on single Mega CR having editorial fixes. This will not be counted towards quota.
This may extend to other agenda items for other release in the future.

## Slide 6: Rel-18 SID/WID handling
SID/WID Template (provided over SA2 reflector) needs to be strictly followed to make it consistent across all SID/WID. Must contain following as per the template -
  Self contained Work Tasks with interdependencies.
  TU estimates at Work Task granularity. Please use TU at a granularity in multiple of 0.5 (or if really necessary, at multiple of 0.25 TU). Please avoid complex TU granularity (e.g., 0.13, 0.18 etc.).
  Potential RAN dependency.
  Potential inter Work Task dependency.
Rel-18 SID/WID can be agreed at either SA2#147-E or SA2#148-E.
Both “agreed” and “technically endorsed” Rel-18 SID/WIDs will be reported to SA#94-E.
Moderated email discussion (1-5 Nov) on Rel-18 SID/WIDs requiring more discussion – [To be confirmed after Oct meeting].
  Inputs provided by each companies on email (DISCUSSION/main SA2/EMEET – TBD) list.
  Moderator to consolidate the inputs and provide revised version to SA2#148-E

## Slide 7: TEI18 Handling
Deferred until Q3, 2022.
Invited for discussion at Q2 and Q3, 22.
Approval at Q3, 22 (Aug meeting).
  7 - 9 TU available from the buffer - TBD
  Prioritization within SA2, if necessary
Scheduling in Q4, 22 and Q1, 23

## Slide 8: Rel-18 TU Considerations
Total TU budget available for Rel-18 work (study + normative) = 183 TUs.
Max TU that can be allocated per SID/WID = 2 TUs per meeting * Total # of meetings = 16 TUs.

## Slide 9: SA2#147E Dates/Agenda
Preliminary Agenda (subjected to changes):
  AI 4.1: Incoming LSs on all agenda items
  AI 4.2: inclusive language for 2G/3G specs
  No AI 5.X, 6.X, 7.X
  AI 8.X: Rel-17 (Input Doc control applies)
  AI 9.X: Rel-18 SID/WID
  No TEI18 mini WIDs
Docs request | 11 Oct 2021 (Monday), CC#1 | 2359 UTC
Docs submission | 11 Oct 2021 (Monday) | 2359 UTC
Start of e-meeting | 18 Oct 2021 (Monday) | 0000 UTC
Revisions | 20 Oct 2021 (Wednesday) | 1600 UTC
Final Comments | 21 Oct 2021 (Thursday) | 1600 UTC
Close of e-meeting | 22 Oct 2021 (Friday), CC#2 | 1700 UTC
Upload Approved docs | 25 Oct 2021 (Monday) | 1700 UTC

## Slide 10: SA2#148E Dates/Agenda
Preliminary Agenda (subjected to changes):
  AI 4.1: Incoming LSs on all agenda items
  AI 4.2: inclusive language for 2G/3G specs
  AI 5.X, 6.X, 7.X
  AI 8.X: Rel-17 (Input Doc control applies)
  AI 9.X: Rel-18 SID/WID
  No TEI18 mini WID
Proposal: Extend the SA2#148E meeting by one day. Focus of additional day will be mainly on Rel-18 SID/WID finalization.
Docs request | 08 Nov 2021 (Monday), CC#1 | 2359 UTC
Docs submission | 08 Nov 2021 (Monday) | 2359 UTC
Start of e-meeting | 15 Nov 2021 (Monday) | 0000 UTC
Revisions | 17 Nov 2021 (Wednesday) | 1700 UTC
Final Comments | 18 Nov 2021 (Thursday) | 1700 UTC
Close of e-meeting | 19 Nov 2021 (Friday), CC#2 | 1800 UTC
Close of e-meeting | 22 Nov 2021 (Monday), CC#3 | 1800 UTC
Upload Approved docs | 23 Nov 2021 (Tuesday) | 1800 UTC

## Slide 11: Items for Endorsement
#1: SA2#149E e-meeting dates: 14 – 25 Feb, 2022, TDoc submission deadline: 28 Jan, 2022.
#2: TEI18 topics (mini WIDs) will be invited starting at Q2, 2022. Approval at Q3, 2022 (Aug meeting). TEI18 topics be scheduled in Q4, 2022 and Q1, 2023.
#2: Total TU budget available for Rel-18 work (study + normative) = 183 TUs.
#3: SA2#148E meeting will be extended by one day (see slide#10). Focus of additional day will be mainly on Rel-18 SID/WID finalization.