## Slide 1: ♥ eV2XARC_Ph2 Status Report ♥
LaeYoung Kim
LG Electronics

## Slide 2: eV2XARC_Ph2 status after SA2#147E
WI Code | Work Item Title | WP | Target Date | WID#
eV2XARC_Ph2 | Architecture enhancements for 3GPP support of advanced V2X services – Phase 2 | 95% > 99% | Sep, 21 | SP-210090
General
  1 CR agreed to TS 23.287 regarding Tx Profile for NR PC5 DRX operations.
  Reply LS on Tx Profile sent to RAN2.
Key Issue 1 (Support of QoS aware NR PC5 power efficiency for pedestrian UEs):
  1 CR agreed to TS 23.287. Reply LS on Tx Profile sent to RAN2.
  Next Steps: Maintenance and alignment with RAN2 work.
  RAN impacts and dependencies:
  Sidelink DRX related operation has RAN dependency.
Contentious Issue:
  None
Focus for the Next Meeting
  SA2#148E: Maintenance and alignment with RAN2 work.

## Slide 3: BACKUP SA2#146E eV2XARC_Ph2 Status Report (S2-2106531) for information

## Slide 4: eV2XARC_Ph2 Status at SA#93-e
Progress since SA#92-e:
  3 CRs agreed to TS 23.287 based on the RAN2 progress/agreements regarding NR PC5 DRX operations.
RAN impacts or dependencies:
  Sidelink DRX related operation
Next steps:
  Maintenance and alignment with RAN2 work.
WI Code | Work Item Title | WP | Target Date | WID#
eV2XARC_Ph2 | Architecture enhancements for 3GPP support of advanced V2X services – Phase 2 | 70% -> 95% | June, 21 -> Sep, 21 | SP-210090

## Slide 5: eV2XARC_Ph2 status after SA2#146E
WI Code | Work Item Title | WP | Target Date | WID#
eV2XARC_Ph2 | Architecture enhancements for 3GPP support of advanced V2X services – Phase 2 | 70% > 95% | June, 21 -> Sep, 21 | SP-210090
General
  3 CRs agreed to TS 23.287 based on the RAN2 progress/agreements regarding NR PC5 DRX operations.
  The following issue in the exception sheet was discussed with DP proposing ‘no work’, but no conclusion.  can be discussed in SA2#147E with companies input if submitted.
    Whether the V2X layer exposes transmission schedule information to the V2X application layer and what is the content for the transmission schedule information based on the applied PC5 DRX information/parameters provided by the AS layer to the V2X layer to be defined in RAN2.
Key Issue 1 (Support of QoS aware NR PC5 power efficiency for pedestrian UEs):
  3 CRs agreed to TS 23.287.
  Next Steps: Maintenance and alignment with RAN2 work.
  RAN impacts and dependencies:
  Sidelink DRX related operation has RAN dependency.
Contentious Issue:
  None
Focus for the Next Meetings
  SA2#147E and SA2#148E: Maintenance and alignment with RAN2 work.

## Slide 6: BACKUP SA2#145E eV2XARC_Ph2 Status Report (S2-2105190) for information

## Slide 7: eV2XARC_Ph2 Status at SA#92-e
Progress since SA#91-e:
  3 CRs agreed to TS 23.287 based on the study conclusions regarding NR PC5 DRX operations.
  Exception requested for finalizing normative work.
RAN impacts or dependencies:
  Sidelink DRX related operation
Next steps:
  Finalize normative work via coordination with RAN2, when the requested exception is granted.
WI Code | Work Item Title | WP | Target Date | WID#
eV2XARC_Ph2 | Architecture enhancements for 3GPP support of advanced V2X services – Phase 2 | 0% -> 70% | June, 21 -> Sep, 21 | SP-210090

## Slide 8: eV2XARC_Ph2 status after SA2#145E
WI Code | Work Item Title | WP | Target Date | WID#
eV2XARC_Ph2 | Architecture enhancements for 3GPP support of advanced V2X services – Phase 2 | 0% > 70% | June, 21 -> Sep, 21 | SP-210090
General
  3 CRs agreed to TS 23.287 based on the study conclusions regarding NR PC5 DRX operations.
  Exception sheet sent to SA#92-e.
Key Issue 1 (Support of QoS aware NR PC5 power efficiency for pedestrian UEs):
  3 CRs agreed to TS 23.287.
  Next Steps:
    Finalize normative work via coordination with RAN2.
  RAN impacts and dependencies:
  Sidelink DRX related operation has RAN dependency.
Contentious Issue:
  None
Focus for the Next Meeting
  SA2#146E: Finalize normative work via coordination with RAN2.