## Slide 1: eNPN Status Report
Peter Hedman
Ericsson (Rapporteur)

## Slide 2: eNPN status after SA2#148E (1/4)
General
  1 update to editorial cleanup CR agreed (23.501)
  Reply LS on network slice admission control for SNPN onboarding to CT1
  Reply LS on limited service availability of an SNPN to RAN2 to CT1, RAN2
  LS on support of DCS variants in UE Onboarding Architecture to SA3 providing some SA2 assumptions related to the DCS options and asking for SA3 feedback (related to KI#4)
  No agreement how to reply to LS from CT1 on PCF in case of SNPN with CH using AUSF/UDM for primary auth, and related CR postponed
  No agreement how to reply to LS from CT1 on the scope of applying Network Slicing feature in Rel-17 and Rel-16
  1 CR to 23.501 agreed related to network slice admission control for SNPN onboarding (eNPN and eNS_Ph2)
  1 CR to 23.501 agreed related to network Slicing scope in relation to SNPNs (eNPN and eNS_Ph2), but no agreement on how network slicing enhancements NSSAA, NSAC and NSSRG can be supported by SNPNs
  1 CR to 23.502 agreed related to NF discovery by NRF in Onboarding or external authentication scenario
Related to Key Issue 1 (Enhancements to Support SNPN along with credentials owned by an entity separate from the SNPN):
  1 CR to 23.501 agreed related to corrections for CH using AUSF/UDM
  1 CR to 23.501 agreed related to correction for switching 3GPP access between SNPN and PLMN
  Next Steps: maintenance
WI Code | Work Item Title | WP | Target Date | WID#
eNPN | Enhanced support of Non-Public Networks | 97% > 98% | Sept, 21 | SP-200980

## Slide 3: eNPN status after SA2#148E (2/4)
Related to Key Issue 2 (NPN support for Video, Imaging and Audio for Professional Applications (VIAPA))
  1 CR to 23.501 agreed related to clarification for QoS differentiation for User Plane IPsec Child SA in underlay network
  Next Steps: maintenance
Related to Key Issue 3 (Support of IMS voice and emergency services for SNPN)
  1 CR to 23.501 agreed related to support for emergency calls in limited service state
  Next Steps: maintenance
WI Code | Work Item Title | WP | Target Date | WID#
eNPN | Enhanced support of Non-Public Networks | 97% > 98% | Sept, 21 | SP-200980

## Slide 4: eNPN status after SA2#148E (3/4)
Related to Key Issue 4 (UE Onboarding and remote provisioning)
  1 CR to 23.501 agreed related to correction to AMF Onboarding Configuration Data
  CRs related UE onboarding architecture postponed, and CR approved from SA2#147E unapproved
  3 CRs (23.501, 23.502 and 23.503) agreed related to use of S-NSSAI/DNN for onboarding, Onboarding indication and PVS handling
  1 CR to 23.502 agreed related to Registration procedure with Onboarding SNPN
  Next Steps: maintenance
WI Code | Work Item Title | WP | Target Date | WID#
eNPN | Enhanced support of Non-Public Networks | 97% > 98% | Sept, 21 | SP-200980

## Slide 5: eNPN status after SA2#148E (4/4)
  RAN impacts and dependencies:
  No new RAN impacts or dependencies
SA3 dependencies
  SA3 dependencies related to UE onboarding architecture and assumptions on DCS options
Contentious Issue:
  -
Focus for the Next Meeting (SA2#149E):
  Maintenance including changes required to support input from other WGs e.g.
    Reply to LS from CT1 on PCF in case of SNPN with CH using AUSF/UDM for primary auth
    reply to LS from CT1 on the scope of applying Network Slicing feature in Rel-17 and Rel-16
    Complete UE onboarding based on SA3 progress
Overall Plan:
  Maintenance
Risks:
  Completion of the work dependent on progress in SA3 (KI#4)

## Slide 6: eNPN Status at SA#94e
Progress since SA#93-e:
  4 Liaisons sent to other WGs in 3GPP replying on questions and asking for feedback
  1 Liaison sent to GSMA asking whether a device is required to have/signal separate IMEI for each simultaneous registration towards separate network (PLMN and SNPN)
  25 CRs (23.501, 23.502 and 23.503) agreed and sent to SA for approval
    Some CRs related to both eNPN and eNS_Ph2 Work Items
  No conclusions/agreements on following topics (i.e. conclusions expected at the next SA2 meeting):
    UE onboarding architecture (require SA3 progress)
    PCF and UE policies in case of SNPN with CH using AUSF/UDM
    SNPN support of Network Slicing features in Rel-17 and Rel-16
  RAN impacts and dependencies:
    No new RAN impacts or dependencies
Next steps:
  Corrections, answering LSes and alignments with other WGs, and especially complete the UE onboarding work based on SA3 progress
WI Code | Work Item Title | WP | Target Date | WID#
eNPN | Enhanced support of Non-Public Networks | 95% > 98% | Sept, 21 | SP-200980