## Slide 1: SA WG2 Status report for ID_UAS
Stefano Faccin
Qualcomm

## Slide 2: ID_UAS status after SA2#148E (1/2)
General
  ID_UAS is captured in TS 23.256
  TS 23.256 sent to SA for approval.
    This is the third time that the TS is presented to SA. All exceptions have been resolved
  14 CRs were approved
    Editorial CRs on various parts of the TS
    A correction addressing the previously contential issue of network and UE behavior for UUAA when the UE aerial subscription is missing
    CRs addressing UAS NF/USS discovery
    CRs addressing the UUAA revocation
  Reply LS to CT1 on support of ePCO and UUAA in pre-rel. 17 EPS network.
  Progress was achieved on the tasks on the previous exception sheet.
  No major contentious issues remain. No technical modifications expected. Work on some Editor’s Notes is required.
WI Code | Work Item Title | WP | Target Date | WID#
ID_UAS | Support of Uncrewed Aerial Systems Connectivity, Identification, and Tracking | 99% > 100% | December 2021 | SP-200979

## Slide 3: ID_UAS status after SA2#148E (2/2)
  RAN impacts and dependencies:
  None
SA3 dependencies
  None.
Contentious Issue:
  None. The contention on the support of notification for change if UE aerial subscription was solved without the introduction of any specific solution.
Focus for the Next Meeting (SA2#149E):
  Corrections as required.
Overall Plan:
  Proceed with necessary corrections after approval by SA plenary.
Risks:
  None

## Slide 4: ID_UAS status after SA2#147E (1/2)
General
  ID_UAS is captured in TS 23.256 v1.1.0
  22 CRs were approved
  Progress was achieved on all areas.
  No major contentious issues remain. No technical modifications expected. Work on some Editor’s Notes is required.
WI Code | Work Item Title | WP | Target Date | WID#
ID_UAS | Support of Uncrewed Aerial Systems Connectivity, Identification, and Tracking | 98% > 99% | December 2021 | SP-200979

## Slide 5: ID_UAS status after SA2#147E (2/2)
  RAN impacts and dependencies:
  None
SA3 dependencies
  None.
Contentious Issue:
  Support of notification for change if UE aerial subscription, no agreement was possible.
Focus for the Next Meeting (SA2#147E):
  Progress and complete normative work to perform alignments and to remove editor’s notes.
Overall Plan:
  Proceed with necessary corrections after approval by SA plenary.
Risks:
  None

## Slide 6: ID_UAS status after SA2#146E (1/2)
General
  ID_UAS is captured in TS 23.256 v1.1.0
  TS 23.256 sent to SA for approval.
    This is the second time that the TS is presented to SA. All exceptions have been resolved
  28 CRs were approved
  Progress was achieved on the tasks on the previous exception sheet:
    C2 (Command and control) authorization and UAV – UAV Controller pairing.
    UAV Controller replacement procedure
  No major contentious issues remain. No technical modifications expected. Work on some Editor’s Notes is required.
WI Code | Work Item Title | WP | Target Date | WID#
ID_UAS | Support of Uncrewed Aerial Systems Connectivity, Identification, and Tracking | 80% > 98% | September 2021 | SP-200979

## Slide 7: ID_UAS status after SA2#146E (2/2)
  RAN impacts and dependencies:
  None
SA3 dependencies
  An EN remains indicating authentication procedure will be revisited after security aspects are fully determined by SA3.
Contentious Issue:
  None.
Focus for the Next Meeting (SA2#147E):
  Progress and complete normative work to perform alignments and to remove editor’s notes.
Overall Plan:
  Proceed with necessary corrections after approval by SA plenary.
Risks:
  None

## Slide 8: ID_UAS status after SA2#145E (1/2)
General
  ID_UAS is captured in TS 23.256 v0.3.0
  21 CRs were approved
  The following tasks were not completed and an exception sheet is submitted in S2-2105186
    C2 (Command and control) authorization and UAV – UAV Controller pairing.
    UAV Controller replacement procedure
  Contentious issues:
    Use of NEF services for delivering PDU session policing information for C2 traffic and for UAV controller replacement (including USS triggered procedures).
WI Code | Work Item Title | WP | Target Date | WID#
ID_UAS | Support of Uncrewed Aerial Systems Connectivity, Identification, and Tracking | 45% > 80% | June 2021 | SP-200979

## Slide 9: ID_UAS status after SA2#145E (2/2)
  RAN impacts and dependencies:
  None
SA3 dependencies
  An EN remains (from S2-2103482) that the UUAA procedure will be revisited after security aspects are determined by SA3.
Contentious Issue:
  Use of NEF services for delivering PDU session policing information for C2 traffic and for UAV controller replacement (including USS triggered procedures).
Focus for the Next Meeting (SA2#146E):
  Address exceptions
  Progress and complete normative work
Overall Plan:
  Complete the normative work at SA2#146e and submit T2 23.256 to SA#93-e plenary for approval.
Risks:
  If contentious issues are not solved, progress of stage 3 work will be impacted.

## Slide 10: ID_UAS status after SA2#144E (1/2)
General
  ID_UAS is captured in TS 23.256.
  18 CRs were approved
  It was concluded to proceed with an API-based solution for UUAA procedures specific for UAV UE (not generic to all UEs). The solution will be captured solely in TS 23.256 with no impacts on TS 23.501 and TS 23.502.
WI Code | Work Item Title | WP | Target Date | WID#
ID_UAS | Support of Uncrewed Aerial Systems Connectivity, Identification, and Tracking | 15% > 45% | June 2021 | SP-200979

## Slide 11: ID_UAS status after SA2#144E (2/2)
  RAN impacts and dependencies:
  None
SA3 dependencies
  An EN has been added in S2-2103482 that the UUAA procedure will be revisited after security aspects are determined by SA3.
Contentious Issue:
  The exact UAS NF interfaces to other NFs is still being discussed.
  Some aspects concluded in the TR are still being challenged and require further discussion.
Focus for the Next Meeting (SA2#144E):
  Progress and complete normative work
Overall Plan:
  Complete the normative work at SA2#145e and submit T2 23.256 to SA#92-e plenary for approval.
Risks:
  If basic TR conclusions are being challenged, there is a risk of inability to complete the WID.

## Slide 12: ID_UAS status after SA2#143E (1/2)
General
  ID_UAS is captured in TS 23.256.
WI Code | Work Item Title | WP | Target Date | WID#
ID_UAS | Support of Uncrewed Aerial Systems Connectivity, Identification, and Tracking | 0% > 15% | June 2021 | SP-200979

## Slide 13: ID_UAS status after SA2#143E (2/2)
  RAN impacts and dependencies:
  None
SA3 dependencies
  Discussion on expanding the applicability of EAP-based UAV authentication to be applicable beyond UAV, i.e. a generic API-based solution for authentication, may require SA3 feedback.
Contentious Issue:
  The conclusion from the TR whether to use a UUAA procedure based on API, instead of an EAP-based procedure, was challenged in SA2#143E and related papers could not be approved. Note that the conclusion was driven by an LS from the aviation community indicating no interest in EAP-based solutions.
Focus for the Next Meeting (SA2#144E):
  Progress normative work
Overall Plan:
  Submit T2 23.256 to SA#92-e plenary for approval.
Risks:
  If basic TR conclusions are being challenged, there is a risk of inability to complete the WID.