## Slide 1: FS_Ranging_SL Work Plan
TR Skeleton, Scope
Reference & Definition
Architecture requirement & assumptions
Key Issue
Solution
Evaluation & Conclusion
WID Approval
TS Development
 |  |  |  |  |  |  | 
 |  |  |  |  |  |  | 
 |  |  |  |  |  |  | 
 |  |  |  |  |  |  | 
 |  |  |  |  |  |  | 
 |  |  |  |  |  |  | 
 |  |  |  |  |  |  | 
 |  |  |  |  |  |  | 
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155
FS_Ranging_SL | 3.5 | 2 | 5.5 | 0.5 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 1 | 1
TR for information @ SA#97
TR for approval & WID for approval @ SA#98
WID completion @ SA#99
 Contributions are conditionally handled & approved
 Contributions are handled and approved
 Last chance for new proposal to be handled and approved
S2-2201106

## Slide 2: Notes
TR Skeleton, Scope
  completed at SA2#149e
Reference & Definition
  the work starts from SA2#149e, and can be further updated along with the KI and solution input
Architecture requirement & assumptions
  the work starts from SA2#149e, and can be further updated at SA2#150e
  To avoid any fundamental change than may impact solution development, evaluation and conclusion, only minor change or editorial change is accepted after SA2#150e
Key Issue
  SA2#151e is the last change to propose new KI, only KI update can be accepted after that
Solution
  Solution can be handled at SA2#149e with lower priority than the papers for TR Skeleton, Scope, Reference & Definition, Architecture requirement & assumptions, and Key Issue
  Solution can be approved at SA2#149e under the condition that the corresponding KI(s) is approved
  SA2#153e is the last change to propose new solution, only solution update can be accepted after that
Evaluation & Conclusion
  the work starts from SA2#151, and can be further updated until SA2#154e
WID Approval
  The earlier it can be submitted is SA2#153e, when the issue with RAN dependency is clarified, as RAN plan to close the work at RAN#97e
TS Development
  TS work can start earlier before TR is approved under the condition that the WID is approved and conclusions of some specific KI is stable