## Slide 1
FS_SUECR Status Report
Lalith Kumar
Samsung (Rapporteur)
3GPP TSG SA WG2 Meeting #149E
E-Meeting, 14-25 February 2022
Agenda 10.2
S2-2201194

## Slide 2: FS_SUECR status after SA2#149E (1/2)
General
  Total TUs requested for Study Phase are 1.5 TU.
  TR skeleton(TR 23.700-61), scope, architecture assumptions and requirements, key issues are specified.
Key Issue 1 (xxxx):
  x solutions added
WI Code | Work Item Title | WP | Target Date | WID#
FS_SUECR | Study on Seamless UE context recovery | 0% > x % | May, 22 | SP-211654

## Slide 3: FS_SUECR status after SA2#149E (2/2)
  RAN impacts and dependencies:
  None
Contentious Issue:
  None
Focus for the Next Meeting (SA2#150):
  To discuss and document solutions on the agreed KI(s).
Overall Plan:
  SA2#149E Feb(0.5 TU): TR Skeleton, Scope, architecture requirements, New KIs approval, Last meeting for New KIs approval.
  SA2#150E Apr(0.5 TU): Start of new solutions approval, continuing the architecture requirements, assumptions, terminology & possible reference architecture.
  SA2#151E May(0.5 TU): TR solution clean-up, solution evaluation and conclusions.

## Slide 4: FS_SUECR Status at SA#95
WI Code | Work Item Title | WP | Target Date | WID#
FS_SUECR | Study on Seamless UE context recovery | 0% > x % | May, 22 | SP-211654
Progress since SA#94:
  TR skeleton, scope, architecture assumptions and requirements, key issues are specified.
  X key issues are documented.
  RAN impacts and dependencies:
  None.
Next steps:
  Start of solutions approval, continuing the work on architecture requirements, assumptions, terminology

## Slide 5: Backup Slide for Overall Work Planning
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153
FS_SUECR | 1.5 | 0.25 | 1.75 | 0.5 | 0.5 | 0.5 | NOT on Agenda | 0.25
TR Skeleton,Scope,Arch requirmenet and assupmions, and etc |  |  |  | yes | yes(updates) |  |  | 
Key Issues |  |  |  | yes,last chance for new KI | yes(updates) |  |  | 
New Solutions |  |  |  | yes, if time/TU permit | yes. | yes,last chance for new Sol. |  | 
Solutions Updates |  |  |  |  | yes | yes |  | 
Evaluations/conclusions |  |  |  |  | yes, if time/TU permit | yes |  | 
Normative |  |  |  |  |  |  |  | Yes