## SA2 Work Plan
SA WG2 Meeting #149E (e-meeting) |  |  | S2-2201217
Feb 14 – 25, 2022
|  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23
|  |  |  | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155
|  |  |  | Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan
Rel-15/Rel-16 maintenance
| Combined (Multiple WIDs) |  |  | 3 | 3 | 0 | 2 | 2 | 2 | 2 | 2
| Sum |  |  | 3 | 3 | 0 | 2 | 2 | 2 | 2 | 2
Rel-17 maintenance
| Combined (17 WIDs) |  |  | 12 | 12 | 10 | 8 | 8 | 6 | 4 | 4
| Sum |  |  | 12 | 12 | 10 | 8 | 8 | 6 | 4 | 4
Rel-17 Alignment (with RAN/CT)
| Combined (3 WIDs) |  |  | 3 | 3 | 3 | 2 | 2 | 1 | 0 | 0
Total (Maintenance) |  |  |  | 18 | 18 | 13 | 12 | 12 | 9 | 6 | 6
Buffer (TEI18, overflow, other)
| Buffer |  |  | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3
Total (Maintenance + Buffer) |  |  |  | 18 | 18 | 13 | 12 | 15 | 12 | 9 | 9
Available for Rel-18 SIDs/WIDs |  |  |  | 20 | 20 | 25 | 26 | 23 | 26 | 29 | 29
|  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_AMP | 1.5 | 0.5 | 2 | 0.5 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 2
FS_5WWC_Ph2 | 1.5 | 1 | 2.5 | 0.5 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0.5 | 0 | 2.5
FS_VMR | 2.75 | 2.25 | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 1 | 5
FS_TRS_URLLC | 5 | 4 | 9 | 1 | 1 | 1 | 1.5 | 1.5 | 1 | 1 | 1 | 9
FS_Ranging_SL | 3.5 | 2 | 5.5 | 0.5 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 1 | 1 | 5.5
FS_5G_ProSe_Ph2 | 6 | 3.25 | 9.25 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1.25 | 9.25
FS_SATB | 3.5 | 1.5 | 5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 0.5 | 0 | 5
FS_AIMLsys | 7 | 5 | 12 | 1 | 1 | 1.5 | 2 | 1.5 | 1 | 2 | 2 | 12
FS_XRM | 9 | 5 | 14 | 1 | 2 | 2 | 2 | 2 | 1 | 2 | 2 | 14
FS_5GSAT_Ph2 | 4 | 1 | 5 | 0.5 | 0.5 | 1 | 1 | 1 | 0.5 | 0 | 0.5 | 5
FS_UPEAS | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0.5 | 0 | 5.5
FS_eNA_Ph3 | 8 | 6 | 14 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 14
FS_5MBS_Ph2 | 7.5 | 4.5 | 12 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 2 | 12
FS_PIN | 3.5 | 2 | 5.5 | 0.5 | 0.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | 1 | 5.5
FS_DetNet | 1 | 1 | 2 | 0.25 | 0 | 0.5 | 0.25 | 0 | 0 | 0.5 | 0.5 | 2
FS_eNPN_Ph2 | 5.5 | 4.25 | 9.75 | 1 | 1 | 1.5 | 1 | 1.5 | 1 | 1 | 1.75 | 9.75
FS_SUECR | 1.5 | 0.25 | 1.75 | 0.5 | 0.5 | 0.5 | 0 | 0.25 | 0 | 0 | 0 | 1.75
MPS_WLAN | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2
FS_REDCAP_Ph2 | 2 | 1 | 3 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5 | 0 | 0.5 | 3
FS_eLCS_Ph3 | 6.25 | 4 | 10.25 | 1 | 1 | 1 | 1.5 | 1.75 | 1 | 1.5 | 1.5 | 10.25
FS_UAS_Ph2 | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 0.5 | 1 | 0.75 | 0.5 | 1 | 0.75 | 5.5
FS_ATSSS_ph3 | 6 | 2.5 | 8.5 | 0.5 | 1.5 | 1 | 2 | 1 | 0.5 | 1 | 1 | 8.5
FS_EDGE_Ph2 | 7.25 | 4.25 | 11.5 | 1 | 1 | 2 | 2 | 1 | 1 | 1.5 | 2 | 11.5
FS_eNS_Ph3 | 6 | 3.25 | 9.25 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1.25 | 9.25
FS_eUEPO | 4.25 | 1.5 | 5.75 | 0.5 | 1 | 1 | 1 | 0.75 | 0.5 | 0.5 | 0.5 | 5.75
FS_SFC | 2.5 | 1.5 | 4 | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 0 | 4
FS_GMEC | 4 | 1.75 | 5.75 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.25 | 0.5 | 5.75
FS_NG_RTC | 4 | 2 | 6 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 6
Total | 119.5 | 71.75 | 191.25 | 19.25 | 21.5 | 27.5 | 29.75 | 25 | 21 | 22.75 | 24.5 | 191.25
NOTE1: Planning is based on max 38 TUs (including 3TU as buffer) per meeting
NOTE2: TU budget estimates assumes 8 meetings untill stage-2 freeze deadline
Note on J32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .25 + .75
Note on I33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 0.5 + 1
Note on I40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .25 + .75
Note on J42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 0.5 + 0.5
Note on J52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .25 + .75