## Slide 1: SA2 Work Planning
Puneet Jain
SA2 Chair
SA WG2 Meeting #149E (e-meeting) S2-2201218
Feb 14 – 25, 2022

## Slide 2: Rel-18 timelines
SA#92-e
Jun/2021
SA#93e
Sep/2021
SA#94-e
Dec/2021
SA#95
Mar/2022
SA#96
Jun/2022
SA#97
Sep/2022
SA#98
Dec/2022
SA#99
Mar/2023
R17
stage 2
freeze
R17
stage 3
freeze
R17 code
freeze
stage 1
100%;
SA2 SIDs prioritization
R18 stage 2
Functional freeze
R18 stage 3
freeze
stage 1
>= 80%; SA2 SIDs Discussion
SA#100
Jun/2023
SA
Rel-18
Workshop
RAN
Rel-18
Workshop
Rel-18
timeline
Rel-18
content agreed
Rel-17
Schedule
Rel-18
Planning
exceptions
S1 normative ongoing;
SA2 SID Discussion
SA#101
Sep/2023
SA#102
Dec/2023
Exceptions
(if any)
R18 stage 2
SID Completion
/WIDs Approval
SA#103
Mar/2024
R18 code
freeze
R18 Stage 2 Study Phase
R18 Stage 2 Normative Phase
TEI18 propsoal submission/approval
TEI18 handling
R18 Stage 2 Study Agreed/ Endorsed

## Slide 3: SA2 Meeting Planning
TSG
WG
WG
I
N
A
C
T
I
V
E
P
E
R
I
O
D
I
N
A
C
T
I
V
E
P
E
R
I
O
D
Planned as E-meetings
January
2022
February
2022
17-21
24-28
31-04
07-11
14-18
21-25
March
2022
28-04
07-11
14-18
T
S
G
#
9
5
RAN1-E
(5+4)
RAN2/3
(5+4)
WG
WG
TSG
S
P
R
I
N
G
F
E
S
T
I
V
A
L
21-25
RAN2/3
(5+2/3)
RAN1-E
(5+2)
April
2022
May
2022
11-15
18-22
25-29
02-06
09-13
16-20
June
2022
23-27
30-3
6-10
20-24
28-01
13-17
04-08
T
S
G
#
9
6
RAN1-E
RAN2/3-E
I
N
A
C
T
I
V
E
P
E
R
I
O
D
SA2
149-E
(5+5)
SA2
150-E
(3+2)
SA2
151-E
(5)
July
2022
27-1
4-8
18-29
11-15
Aug
2022
1-5
8-12
22-26
15-19
TSG
Sep
2022
29-2
5-9
19-23
12-16
T
S
G
#
9
7
Oct
2022
26-30
3-7
17-21
10-14
Nov
2022
24-28
31-4
7-11
SA2
152-E
(3+5)
SA2
153-E
(5)
14-18
SA2
154-E
(5)
Planned as both F2F and E-meetings
152
(5)
153
(5)
154
(5)
E-meetings
F2F -meetings

## Slide 4: SA2 meeting dates for 1H, 2022
SA2 meeting in 1H will be held as e-meetings.
SA2 E-meeting calendar for 2H, 2022
  SA2 #149-E (14 – 25 Feb, 2022)
  SA2 #150-E (06 – 12 April, 2022)
    TBD – How to celebrate SA2 150th Anniversary?
  SA2 #151-E (16 – 20 May, 2022)

## Slide 5: SA2 meeting dates for 2H, 2022
2H 2022 will be maintained as dual calendar (with both F2F and e-meeting dates).
  Whether meeting will be conducted as F2F or e-meeting will be confirmed based on TSG SA guidance.
SA2 F2F meeting calendar for 2H, 2022
  SA2 #153 (22 – 26 Aug, 2022) – Gothenburg, SE
    Meeting host cannot accommodate additional days.
    TBD – whether post meeting email approval, or pre e-meeting needs to be scheduled to accommodate Rel-18 workload.
  SA2 #154 (10 – 14 Oct, 2022) – China, CN
  SA2 #155 (14 – 18 Nov, 2022) – TBD, US
SA2 E-meeting calendar for 2H, 2022
  SA2 #153-E (17 – 26 Aug, 2022)
  SA2 #154-E (10 – 14 Oct, 2022)
    TBD – whether to extend by 1 day (5 + 1) to be scheduled to accommodate Rel-18 workload.
  SA2 #155-E (14 – 18 Nov, 2022)
    TBD – whether to extend by 1 day (5 + 1) to be scheduled to accommodate Rel-18 workload.
  SA2 July Ad-hoc (26 June – 1 July, 2022) is cancelled.

## Slide 6: Rel-18 TU Considerations
For 1H 22 e-meetings, allocate the full buffer to Rel-18 SIDs.
For May meeting (SA2#151-e) mainly focus on Rel-17 correction + Rel-18 SID + agenda 4.1 (urgent LSs). No 5.X, 6.X and 7.X on the agenda.
Aug meeting e-meeting will be extended by 3 days.
For pre-rel-18 FASMO criterion will be strictly enforced from the April meeting onwards.
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155
FS_AMP | 1.5 | 0.5 | 2 | 0.5 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 0
FS_5WWC_Ph2 | 1.5 | 1 | 2.5 | 0.5 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0.5 | 0
FS_VMR | 2.75 | 2.25 | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 1
FS_TRS_URLLC | 5 | 4 | 9 | 1 | 1 | 1 | 1.5 | 1.5 | 1 | 1 | 1
FS_Ranging_SL | 3.5 | 2 | 5.5 | 0.5 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 1 | 1
FS_5G_ProSe_Ph2 | 6 | 3.25 | 9.25 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1.25
FS_SATB | 3.5 | 1.5 | 5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 0.5 | 0
FS_AIMLsys | 7 | 5 | 12 | 1 | 1 | 1.5 | 2 | 1.5 | 1 | 2 | 2
FS_XRM | 9 | 5 | 14 | 1 | 2 | 2 | 2 | 2 | 1 | 2 | 2
FS_5GSAT_Ph2 | 4 | 1 | 5 | 0.5 | 0.5 | 1 | 1 | 1 | 0.5 | 0 | 0.5
FS_UPEAS | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0.5 | 0
FS_eNA_Ph3 | 8 | 6 | 14 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2
FS_5MBS_Ph2 | 7.5 | 4.5 | 12 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 2
FS_PIN | 3.5 | 2 | 5.5 | 0.5 | 0.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | 1
FS_DetNet | 1 | 1 | 2 | 0.25 | 0 | 0.5 | 0.25 | 0 | 0 | 0.5 | 0.5
FS_eNPN_Ph2 | 5.5 | 4.25 | 9.75 | 1 | 1 | 1.5 | 1 | 1.5 | 1 | 1 | 1.75
FS_SUECR | 1.5 | 0.25 | 1.75 | 0.5 | 0.5 | 0.5 | 0 | 0.25 | 0 | 0 | 0
MPS_WLAN | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
FS_REDCAP_Ph2 | 2 | 1 | 3 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5 | 0 | 0.5
FS_eLCS_Ph3 | 6.25 | 4 | 10.25 | 1 | 1 | 1 | 1.5 | 1.75 | 1 | 1.5 | 1.5
FS_UAS_Ph2 | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 0.5 | 1 | 0.75 | 0.5 | 1 | 0.75
FS_ATSSS_ph3 | 6 | 2.5 | 8.5 | 0.5 | 1.5 | 1 | 2 | 1 | 0.5 | 1 | 1
FS_EDGE_Ph2 | 7.25 | 4.25 | 11.5 | 1 | 1 | 2 | 2 | 1 | 1 | 1.5 | 2
FS_eNS_Ph3 | 6 | 3.25 | 9.25 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1.25
FS_eUEPO | 4.25 | 1.5 | 5.75 | 0.5 | 1 | 1 | 1 | 0.75 | 0.5 | 0.5 | 0.5
FS_SFC | 2.5 | 1.5 | 4 | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 0
FS_GMEC | 4 | 1.75 | 5.75 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.25 | 0.5
FS_NG_RTC | 4 | 2 | 6 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5
Total | 119.5 | 71.75 | 191.25 | 19.25 | 21.5 | 27.5 | 29.75 | 25 | 21 | 22.75 | 24.5
Please see S2-2201217 for latest SA2 work planning sheet

## Slide 7: Tracking of TU for Rel-18 SIDs
During F2F, one TU (Time Unit) corresponds to 1.5 hours slot in which roughly 10-15 contributions can be handled.
For SA2#149E e-meeting onwards, TU will be tracked as per the following mechanism.
  Maximum of 30 TDocs (P-CRs) per 1 TU will be handled. If a Rel-18 SID is assigned 0.5 TU then maximum of 15 TDocs (P-CR) will be handled. If a Rel-18 SID is assigned .25 TU then maximum of 7 TDocs (P-CRs) will be handled.
  If the SID is assigned 1 TU in SA2#149-E and it receives more than 30 papers then only 30 will be picked based on sorting (after submission deadline but before start of the e-meeting) by the SA2 leadership. Fairness criterion will be applied, and Rapporteur input will be required on such sorting.
  Rapporteur are required to provide the sorting order to SA2 leadership as soon as possible (after the TD submission deadline).
  Rapporteur’s input papers on TR skeleton, TR scope etc. will be exempted.
  Discussion Paper (for Information) will be exempted.
  LS IN/OUT will be exempted
If this mechanism hinders progress, then it will be revisited in the future e-meeting.
This may be extended to other Agenda Items in future e-meeting, if necessary.

## Slide 8: Guidance to Rel-18 Rapporteurs
Rel-18 Rapporteurs should put together a work plan for their SID and how they plan to utilize the assigned TU for each meeting. Update the Work Plan after each meeting. Can be part of the status report.
For e.g. -
  SA2#149-E, 1 TU assigned, finish TR Skeleton, TR Scope, Architectural Assumption, KI, etc.
  SA2#150-E, 1 TU assigned, last e-meeting for any new KI, solutions for Key Issue X Y Z.
  SA2#151-E, 2 TU assigned, last e-meeting for any new solution, start the initial evaluation.
  SA2#152-E, 1 TU assigned, solution evaluation and conclusion, normative WID creation, etc.
  Rel-18 Rapporteurs shall provide the status report after each (e-)meeting on the progress, any controversial issue, RAN dependency, etc. Please use template defined for Rel-17 SIDs/WIDs.

## Slide 9: TEI18 Handling
TEI18 proposals will be on agenda in May and Aug e-meeting.
TEI18 proposal may be technically endorsed (but not approved) in May e-meeting.
No TEI18 proposals will be considered after Aug, 22 e-meeting.
TEI18 proposals can be Approval at Q3, 22 (Aug meeting).
  7 - 9 TU available from the buffer - TBD
  Prioritization within SA2, if necessary
Scheduling in Q4, 22 and Q1, 23

## Slide 10: Proposals
It is proposed to endorse SA2 work Plan for 2022 (all previous slides).
It is proposed to endorse that SA2 Ad-Hoc in Jan 2023 will be scheduled (TBD - F2F or e-meeting).