## Slide 1: FS_EDGE_Ph2 status report
Patrice Hédé
Huawei Technologies

## Slide 2: EDGE Ph2 status at SA#95-e
  Progress since SA#94-e:
  Total TUs requested for Study phase in 2022 is 7,25, 1 TU used in SA2#149E and 6,25 TUs remaining.
  TR skeleton, scope and architectural assumptions of TR 23.700-48 v0.0.0 are agreed.
  7 KIs corresponding to all SID objectives have been agreed.
  RAN impacts and dependencies:
  RAN impacts depending on the study outcome.
Next steps:
  Capture new solutions for all KIs.
WI Code | Work Item Title | WP | Target Date | WID#
FS_EDGE_Ph2 | Study on Edge Computing Phase 2 | 0% → 13% | Sept 2022 → Dec 2022 | SP-211638

## Slide 3: EDGE Ph2 status after SA2#149E
  Progress since SA#94-e:
  Total TUs requested for Study phase in 2022 is 7,25, 1 TU used in SA2#149E and 6,25 TUs remaining.
  TR skeleton, scope and architectural assumptions of TR 23.700-48 v0.0.0 are agreed.
  7 KIs corresponding to all SID objectives have been agreed.
  RAN impacts and dependencies:
  TBD
Next steps:
  Capture new solutions for all KIs.
WI Code | Work Item Title | WP | Target Date | WID#
FS_EDGE_Ph2 | Study on Edge Computing Phase 2 | 0% → 13% | Sept 2022 → Dec 2022 | SP-211638

## Slide 4: EDGE Ph2 status after SA2#149E — work plan
Study phase
  SA2#149e, Feb (1TU): Agreement on scenarios/use cases and assumptions for all KIs
  SA2#150e, Apr (1TU): Completion of KI definition. Solutions
  SA2#151e, May (2TU): Solutions
  SA2#152e, Aug (2TU): Solutions, evaluations, conclusions
    Approval of Edge ph2 WID based on first conclusions, TR sent for information
  SA2#153e, Oct (1TU): evaluations, conclusions
    Update of Edge ph2 WID based on remaining conclusions
  SA2#154e, Nov (0,25 TU): final conclusions
    TR sent for approval
 |  |  |  | Feb. 22 | Apr. 22 | May 22 | Aug. 22 | Oct. 22 | Nov. 22 | Jan. 23 | Feb. 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_EDGE_Ph2 | 7,25 | 4,25 | 11,5 | 1 | 1 | 2 | 2 | 1 | 0,25/0,75 | 1,5 | 2 | 11,5