## Slide 1: FS_VMR Status Report
Qualcomm Incorporated
S2-2201889

## Slide 2: FS_VMR status after SA2#149E (1/2)
General
  TR 23.700-05 v.0.1.0 was created based on approved contributions.
  8 contributions agreed (including TR skeleton, scope, architecture assumptions and requirements, and key issues).
  1 LS Out to RAN (and RAN3) regarding the IAB support of NR satellite access.
  1 contribution postponed pending response of the LS.
  0.5 TU used and 2.25 TU left for the Study Phase.
6 Key Issues agreed for the study:
  KI#1: Mobile base station relay configuration support in 5GC
  KI#2: Efficient mobility for UEs connecting to/disconnecting from VMR
  KI#3: Efficient mobility and service continuity when served by VMR
  KI#4: Support of roaming of mobile base station relays
  KI#5: Support of location services for UEs accessing via a mobile base station relay
  KI#6: Provide cell ID/TAC of mobile base station relay for services
  RAN impacts and dependencies:
  RAN impacts or dependencies identified for Key Issue #1, #2, #3, #4, #6
Other WG dependencies
  Charging support is expected to be handled by SA5, and alignment work in SA2 may be required
WI Code | Work Item Title | WP | Target Date | WID#
FS_VMR | Study on Vehicle Mounted Relays | 0% > 20% | Sept, 22 | SP-211636

## Slide 3: FS_VMR status after SA2#149E (2/2)
Contentious Issue:
  None.
Focus of the Next Meeting (SA2#150E):
  Handle any new Key Issue
  Handle solutions for all Key Issues
Overall Plan: (study phase)
  SA2#149 Feb’22: 0.5 (TR skeleton, arch assumptions, KIs)
  SA2#150 Apr’22: 0.5 (last chance for new KIs; solutions)
  SA2#151 May’22: 0.5 (last chance for new solutions; solution updates)
  SA2#152 Aug’22: 0.5 (Evaluations; Interim conclusions, send TR to RAN for comments)
  SA2#153 Oct’22: 0.5 (Finalize conclusions; WID approval)
  SA2#154 Nov’22: 0.25 (Resolve RAN dependent open issues for selected solutions); start normative work.
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_VMR | 2.75 | 2.25 | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 (0.25+0.75) | 0.5 | 1 | 5

## Slide 4: FS_VMR status at SA#95e
Progress since SA#94-e:
  TR Skeleton agreed
  TR Scope, Architectural assumptions and requirements agreed
  6 Key Issues agreed
  TR 23.700-05 v0.1.0 generated based on the agreed contributions
RAN impacts and dependencies:
  RAN dependency identified for 5 key issues
  1 LS to RAN/RAN3 regarding IAB support of NR satellite access
Next steps:
  Continue the study
WI Code | Work Item Title | WP | Target Date | WID#
FS_VMR | Study on Vehicle Mounted Relays | 0% > 20% | Sept, 22 | SP-211636