## Slide 1: FS_AIMLsys Status Report
Tricci So
OPPO (Rapporteur)
David Gutierrez Estevez
Samsung (Rapporteur)

## Slide 2: FS_AIMLsys status after SA2#149E (1/2)
General
  FS_AIMLsys TR 23.700-80 v0.1.0 will be available after SA2#149E meeting.
  Total TUs requested for Study and Normative Phases was 12 TUs of which 1 has been used for SA2#149E and 11 TUs are remaining.
  TR skeleton and scope are agreed. 3 Architecture Assumptions and 2 Architecture Requirements are identified.
List of 7 agreed KIs:
    Monitoring of network resource utilization for support of Application AI/ML operations (S2-2201816)
    5GC information exposure to UE (S2-2201817)
    5GC Information Exposure to authorized 3rd party (S2-2201854)
    Enhancing External Parameter Provisioning (S2-2201818)
    5GC Enhancements to enable Application AI/ML Traffic Transport (S2-2201819)
    QoS and Policy Enhancement (S2-2201820)
    5GS Assistance to Federated Learning Operation (S2-2201821)
WI Code | Work Item Title | WP | Target Date | WID#
FS_AIMLsys | Study on System Support for AI/ML-based Services | 0% > 10 % | October, 22 | SP-211648

## Slide 3: FS_AIMLsys status after SA2#149E (2/2)
  RAN impacts and dependencies:
  TBD
Contentious Issue:
  None
Focus for the Next Meeting (SA2#150):
  “Last” meeting to finalize KIs, start of collecting new possible solutions. Continuation to study the architecture requirements and assumptions discussions as well as terminology.
Overall Plan:
  SA2#149E Feb(1.0 TU): TR Skeleton, Scope & New KIs approval & architecture requirements, assumptions, terminology.
  SA2#150E Apr(1.0 TU): Last meeting to finalize KIs, start of collecting new possible solutions, continuation to study the architecture requirements, assumptions, terminology.
  SA2#151E May(1.5 TU): Last meeting for accepting new possible solutions, TR solution clean up, start of solution evaluation, and interim conclusion, if possible
  SA2#152E Aug(2.0 TU): TR solution clean-up, solution evaluation, interim conclusions and/or final conclusion, if possible
  SA2#153E Oct(1.5 TU): Study phase final conclusion

## Slide 4: FS_AIMLsys Status at SA#95
WI Code | Work Item Title | WP | Target Date | WID#
FS_AIMLsys | Study on System Support for AI/ML-based Services | 0% > 10 % | October, 22 | SP-211648
Progress since SA#94:
  TR skeleton and scope were agreed. 3 Architecture Assumptions and 2 Architecture Requirements were identified.
  8 key issues are documented.
  RAN impacts and dependencies:
  RAN impact depends on the study outcomes of the solutions.
Next steps:
  SA2#150E Apr (1.0 TU): Last meeting to finalize KIs, start of collecting new possible solutions, continuation to study the architecture requirements, assumptions, terminology.

## Slide 5: Backup Slide for Overall Work Planning
(1) TR Skeleton, Scope & New KIs approval & architecture requirements, assumptions, terminology
(2) Last meeting for finalizing KIs, start of collecting possible solutions, continuation to study collecting architecture requirements, assumptions, terminology
(4) TR solution clean-up, solution evaluation, interim conclusions and/or possible finalize conclusion per KI, if possible
(5) Study phase final conclusion
TR 23.700-80 Submission to Dec. 2022 TSG SA#98 for Approval
(3) Last meeting for collecting possible solutions, TR solution clean up, start of solution evaluation and agreeing on interim conclusion, if possible
TR 23.700-80 Submission to Sep. 2022 TSG SA#97 for Information
TR 23.700-80
Study phase
Normative phase