## Slide 1: FS_5GSAT_Ph2 Status Report
Jean Yves Fine
Thales (Rapporteur)
S2-2201892

## Slide 2: FS_5GSAT_Ph2 status after SA2#149E (1/2)
General
  Total TUs requested for Study Phase is 4 TUs.
  0.5 TU is used, and 3.5 TUs are remaining for study Phase
  TR skeleton , scope, Architecture Assumptions are agreed
List of 2 agreed Key Issues:
  KI#1: Mobility Management enhancement with discontinuous satellite coverage
  KI#2: Power saving enhancement for UE in discontinuous coverage
List of 1 agreed solution:
  Solution#1: Power Saving based on AMF awareness of coverage information
WI Code | Work Item Title | WP | Target Date | WID#
FS_5GSAT_Ph2 | Study on satellite access, Phase2 | 0% > 12.5% | Oct, 22 | SP-211651

## Slide 3: FS_5GSAT_Ph2 status after SA2#149E (2/2)
  RAN impacts and dependencies:
  RAN impacts or dependencies identified for Key Issue #1 and #2
Contentious Issue:
  None
Overall Plan:
  SA2#150 meeting: start solutions discussions. Finalize the KIs (last chance for new KIs).
  SA2#151 meeting: continue the solution discussions and start to evaluate solutions.
  SA2#152 meeting: solution updates and finalize the evaluation and conclusion; send TR for infomation; first draft of WID
  SA2#153 meeting: continue the evaluation and conclusion for remaining TR KIs; WID Approval; start normative work for concluded KIs
  SA2#154, #154AH and #155 meeting: normative work
Available for Rel-18 SIDs/WIDs |  |  |  | 20 | 20 | 25 | 26 | 23 | 26 | 29 | 29 | 
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_5GSAT_Ph2 | 4 | 1 | 5 | 0,5 | 0,5 | 1 | 1 | 1 | 0,5 | 0 | 0,5 | 5

## Slide 4: FS_5GSAT_Ph2 status at SA#95e
Progress since SA#94-e:
  TR skeleton , scope, Architecture Assumptions are agreed
  2 KIs agreed
  1 Solution agreed
RAN impacts and dependencies:
  RAN impacts identified on KI#1 & KI#2
Next steps:
  SA2#150e (0.5 TU): start solutions discussions. Finalize the KIs (last chance for new KIs).
  SA2#151e (1 TU): continue the solution discussions and start to evaluate solutions.
WI Code | Work Item Title | WP | Target Date | WID#
FS_5GSAT_Ph2 | Study on satellite access, Phase2 | 0% > 12.5% | Oct, 22 | SP-211651