## Slide 1: FS_PIN Status Report
vivo Mobile Communication Co., Ltd.
S2-2201894

## Slide 2: FS_PIN status after SA2#149E (1/2)
General
  TR 23.700-88 v.0.1.0 was created based on approved contributions.
  10 contributions agreed (including TR skeleton, scope, terms and abbreviations, architecture requirements and assumptions, and key issues).
  1 contribution noted (key issue related to identification of PIN and PIN Elements), and 1 contribution postponed (solution).
  2 contributions not handled (vivo, interdigital).
6 Key Issues agreed for the study:
  KI#1: 5GC architecture enhancements to support PIN
  KI#2: Authorization for PIN
  KI#3: Management of PIN and PIN Elements
  KI#4: PIN and PIN element discovery and selection
  KI#5: Communication of PIN
  KI#6: Policy and parameters provisioning for PIN
  RAN impacts and dependencies:
  none
Other WG dependencies
  SA3 for the Security aspects, SA5 for the Charging aspects, SA6 for application-level aspects
WI Code | Work Item Title | WP | Target Date | WID#
FS_PIN | Study on Personal IoT Networks | 0% > 20% | Sept, 22 | SP-211643

## Slide 3
Contentious Issue:
  Whether subscription linkage and PIN definition need to be studied:
    It is for further consideration whether to study requirements for association of the PIN elements with a 3GPP subscription for accessing services offered by the 5GS.
    It is FFS whether to study requirements on how and who defines a PIN as part of this KI or in another KI e.g. PIN management related KI
Focus of the Next Meeting (SA2#150E):
  Handle contentious issue to approve key issue related to identification
  Handle solutions for all agreed key issues and identification key issue based on S2-2200837r07
Overall Plan: (study phase)
  SA2#149 (0.5TU): TR skeleton, scope, arch assumptions; new KIs, new solutions
  SA2#150 (0.5TU): New solutions, (new/updated) KIs, KI with solution
  SA2#151 (1TU): Solutions, initial evaluations
  SA2#152 (1TU): Solutions, evaluations, Interim conclusions
  SA2#153 (0.5TU): Finalize conclusions, evaluation updates; WID approval
  SA2#154: start normative work.
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155
FS_PIN | 3.5 | 2 | 5.5 | 0.5 | 0.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | 1
FS_PIN status after SA2#149E (2/2)

## Slide 4: FS_PIN status at SA#95e
Progress since SA#94-e:
  TR Skeleton agreed
  TR Scope, Architectural requirements and assumptions, as well as terms and abbreviation agreed
  6 Key Issues agreed
  TR 23.700-88 v0.1.0 generated based on the agreed contributions
RAN impacts and dependencies:
  none
Next steps:
  Continue the study
WI Code | Work Item Title | WP | Target Date | WID#
FS_PIN | Study on Personal IoT Networks | 0% > 20% | Sept, 22 | SP-211643