## Slide 1: FS_UPEAS Status Report
Yan Han
China Mobile
S2-2201899

## Slide 2: FS_UPEAS status after SA2#149E (1/2)
  General
  TR 23.700-62 v.0.1.0 was created based on approved contributions.
  Total TUs requested for Study phase in 2022 is 3.25, 0.5 TU used in SA2#149E and 2.75 TUs remaining.
  7 contributions agreed (including TR skeleton, scope, architecture assumptions and requirements, key issues, Annex, and solutions).
2 Key Issues agreed for the study
  KI#1: Support UPF expose information to other NFs
  KI#2: Study UPF event exposure service registration and discovery
1 Solution agreed for the study
  Solution#1: UPF event exposure service framework enhancements to support registration, deregistration and discovery via NRF
1 Annex agreed for the study
  Annex for NWDAF requirements of UPF event exposure service(s)
  RAN impacts and dependencies:
  None.
WI Code | Work Item Title | WP | Target Date | WID#
FS_UPEAS | Study on UPF enhancement for Exposure And SBA | 0% > 20% | Sept, 22 | SP-211652

## Slide 3: FS_UPEAS status after SA2#149E (2/2)
Other WG dependencies
  None.
Contentious Issue:
  None.
Focus for the Next Meeting (SA2#150E):
  Handle any new Key Issue, and solutions discussion for all Key Issues.
Overall Plan:
  SA2#149e, Feb (0.5TU): TR skeleton, scope, Arch assumptions and requirements, and KIs
  SA2#150e, Apr (0.5TU): last chance for new KIs; solutions discussion
  SA2#151e, May (1TU): solutions (last chance for new solutions), evaluations
  SA2#152e, Aug (1TU): solution updates, and try to finalize the evaluation and conclusion; send TR for approval; WID Approval
  SA2#153e, Oct (1TU): finalize the conclusion for remaining TR KIs; start normative work
  SA2#154e, Nov (1TU): normative work
  SA2#154AH, Jan (0.5TU): normative work
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_UPEAS | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 1 | 1 | 1 (0.25+0.75) | 1 | 0.5 | 0 | 5.5

## Slide 4: FS_UPEAS status at SA#95e
  Progress since SA#94-e:
  TR skeleton, scope, Architectural assumptions and requirements agreed.
  2 Key Issues agreed.
  1 Solution, 1 Annex agreed.
  TR 23.700-62 v0.1.0 generated based on the agreed contributions
RAN impacts and dependencies:
  None.
Next steps:
  Continue the study.
WI Code | Work Item Title | WP | Target Date | WID#
FS_UPEAS | Study on UPF enhancement for Exposure And SBA | 0% > 20% | Sept, 22 | SP-211652