## Slide 1: FS_5MBS_Ph2 Status Report
Li, Meng
Huawei

## Slide 2: FS_5MBS_Ph2 Status after SA2#149E (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS_Ph2 | Study on architectural enhancements for 5G multicast-broadcast services Phase 2 | 0%  15% | Sept., 2022 | SP-211645
  Progress since SA#94-e:
  Total TUs requested for Study phase in 2022 is 7.5, 1 TU used in SA2#149E and 6.5 TUs remaining.
  Skeleton, scope and architectural assumption of TR 23.700-47 are approved.
  The revised SID was approved for polishing, e.g. TR# addition, target dates modification.
  5 KIs and 2 solutions are agreed.
  RAN impacts and dependencies:
  2 agreed KIs have RAN impacts as per agreed pCRs.
Other WG dependencies
  3 agreed KIs have potential SA4 impacts as per agreed pCRs.
Contentious Issue:
  None.
Next steps in SA2#150E:
  Complete the key issues with modifying current existing one (s) or adding new one (s).
  Finalize description for already captured solutions, and capture new solutions.
  List identified RAN dependencies and send liaisons to relevant RAN WGs if needed.
Need to be updated

## Slide 3: FS_5MBS_Ph2 Status after SA2#149E (2/2)
Overall Plan: (study phase)
  SA2#149e, Feb (1TU): Focus on KIs, solutions are allowed. Agree the skeleton/scope/architectural assumption.
  SA2#150e, Apr (1TU): Focus on Solutions and complete all KIs. Potential updates/new KIs. Last meeting for KI proposal/modification.
  SA2#151e, May (2TUs): Solutions
  SA2#152, Aug (2TUs): Solutions, evaluations, conclusions
  SA2#153, Oct (1TU): evaluations, conclusions
    Approval of MBS_Ph2 WID
  SA2#154, Nov (0.5 TU): final conclusions
    Adjustment/issues depends on RAN progress
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_5MBS_Ph2 | 7.5 | 4.5 | 12 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 2 | 12
Need to be updated

## Slide 4: FS_5MBS_Ph2 Status at SA#95-e
  Progress since SA#94-e:
  Total TUs requested for Study phase in 2022 is 7.5, 1 TU used in SA2#149E and 6.5 TUs remaining.
  Skeleton, scope and architectural assumption of TR 23.700-47 are approved.
  The revised SID was approved for polishing, e.g. TR# addition, target dates modification.
  5 KIs and 2 solutions are agreed.
  RAN impacts and dependencies:
  2 agreed KIs have RAN impacts as per agreed pCRs.
Next steps:
  Complete the key issues with modifying current existing one (s) or adding new one (s).
  Finalize description for already captured solutions, and capture new solutions.
  List identified RAN dependencies and send liaisons to relevant RAN WGs if needed.
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS_Ph2 | Study on architectural enhancements for 5G multicast-broadcast services Phase 2 | 0%  15% | Sept., 2022 | SP-211645
Need to be updated