## Slide 1: FS_5MBS_Ph2 Status Report
Li, Meng
Huawei

## Slide 2: FS_5MBS status after SA2#150E (1/2)
General
  TR 23.700-47 v0.2.0 is available.
  Total TUs requested for Study Phase is 7.5, 2 TUs used after 150E and 5.5 TUs remaining.
  Added new Key Issue #6 (Improvement for potential performance issues related to high numbers of public safety UEs)
Architectural requirement
  The architectural requirement was updated and included public safety requirement.
Key Issue 1 (RRC Inactive for Multicast)
  Four new solutions were included in the TR and one solution was updated.
  Next step: in SA2#151E finalize description for solutions with strong support. Potential proceeding with solution evaluation and interim conclusion.
Key Issue 2 (MOCN for broadcast)
  Three solutions were captured and two updates were agreed.
  Next step: in SA2#151E finalize description for solutions with strong support. Potential proceeding with solution evaluation and interim conclusion.
Key Issues 3 (AF triggered MBS session management)
  Two solutions were captured.
  Next step: in SA2#151E discuss and capture solutions.
Key Issue 4 (Group message delivery)
  Two solutions captured.
  Next step: in SA2#151E discuss and capture solutions.
Key Issues 5 (Power Saving mechanisms)
  Two solutions captured.
  Next step: in SA2#151E discuss and capture solutions
Key Issues 6 (Public safety)
  Two solutions captured.
  Next step: in SA2#151E discuss and capture solutions
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS_Ph2 | Study on architectural enhancements for 5G multicast-broadcast services Phase 2 | 15%  35% | Sept., 2022 | SP-211645

## Slide 3: FS_5MBS status after SA2#150E (2/2)
  RAN impacts and dependencies:
  Most of the key issues may lead to RAN impact.
Contentious Issue:
  None.
Focus for the Next Meeting (SA2#150):
  Finalize description for already captured solutions with strong support.
  Capture new solutions with strong support.
  List identified RAN dependencies and send liaisons to relevant RAN WGs if needed.

## Slide 4: FS_5MBS_Ph2 Status after SA#95-e
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS_Ph2 | Study on architectural enhancements for 5G multicast-broadcast services Phase 2 | 15%  35% | Sept., 2022 | SP-211645
  Progress since SA#95-e:
  1 KI is agreed, and architectural requirement is updated.
  1 LS is sent to RAN WGs.
  15 new solutions and 3 solution updates are agreed.
  RAN impacts and dependencies:
  3 KIs have RAN WGs coordination requirement as per agreed pCR.
Other WG dependencies
  KIs have potential SA6/SA4/SA3 coordination requirements accordingly as per agreed pCR.
Contentious Issue:
  None.
Next steps in SA2#151E:
  Finalize description for already captured solutions with strong support.
  Capture new solutions with strong support.
  List identified RAN dependencies and send liaisons to relevant RAN WGs if needed.

## Slide 5: Annex

## Slide 6: Work Plan
Overall Plan: (study phase)
  SA2#149e, Feb (1TU): Focus on KIs, solutions are allowed. Agree the skeleton/scope/architectural assumption.
  SA2#150e, Apr (1TU): Focus on Solutions and complete all KIs. Potential updates/new KIs. Last meeting for KI proposal/modification.
  SA2#151e, May (2TUs): Solutions
  SA2#152, Aug (2TUs): Solutions, evaluations, conclusions
  SA2#153, Oct (1TU): evaluations, conclusions
    Approval of MBS_Ph2 WID
  SA2#154, Nov (0.5 TU): final conclusions
    Adjustment/issues depends on RAN progress
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_5MBS_Ph2 | 7.5 | 4.5 | 12 | 1 | 1 | 2 | 2 | 1 | 1 | 2 | 2 | 12