## Slide 1: FS_AIMLsys Status Report
Tricci So
OPPO (Rapporteur)
David Gutierrez Estevez
Samsung (Rapporteur)

## Slide 2: FS_AIMLsys_Ph2 status after SA2#150E (1/2)
General
  FS_AIMLsys TR 23.700-80 v0.2.0 is available TBD
  Total TUs requested for Study Phase is 7 TUs of which 2 TUs have been consumed and 5 TUs are remaining.
  100% coverage of all Key Issues during SA2#150-e.
  Total of 27 solutions were agreed, Key Issue#3 and Key Issue#6 were updated
List of Agreed Solutions for KIs: (Note: Some solutions may apply to more than one KI, please refer to TR for details)
    KI#1: Monitoring of network resource utilization for support of Application AI/ML operations (3 solutions)
    KI#2: 5GC information exposure to UE (5 solutions)
    KI#3: 5GC Information Exposure to authorized 3rd party for Application Layer AI/ML (3 solutions)
    KI#4: Enhancing External Parameter Provisioning (2 solutions)
    KI#5: 5GC Enhancements to enable Application AI/ML Traffic Transport (5 solutions)
    KI#6: QoS and Policy Enhancements (6 solutions)
    KI#7: 5GS Assistance to Federated Learning Operation (14 solutions)
WI Code | Work Item Title | WP | Target Date | WID#
FS_AIMLsys | Study on System Support for AI/ML-based Services | 10 > 30 % | October, 22 | SP-211648

## Slide 3: FS_AIMLsys status after SA2#150E (2/2)
  RAN impacts and dependencies:
  RAN impact depends on the study outcomes of the solutions.
  SA WG3 (KI#3, 4, 5), SA WG4 (KI#2) and SA WG5 (KI#5)
Contentious Issue:
  None
Focus for the Next Meeting (SA2#151E):
  Update adopted solutions, address architecture requirements, assumptions as well as terminology. SA2#151E is the “last” meeting for proposing new solutions.
Overall Plan:
  SA2#149E Feb(1.0 TU): TR Skeleton, Scope & New KIs approval & architecture requirements, assumptions, terminology.
  SA2#150E Apr(1.0 TU): Last meeting to finalize KIs, start of collecting new possible solutions, continuation to study the architecture requirements, assumptions, terminology.
  SA2#151E May(1.5 TU): Last meeting for accepting new possible solutions, TR solution clean up, start of solution evaluation, and interim conclusion, if possible
  SA2#152E Aug(2.0 TU): TR solution clean-up, solution evaluation, interim conclusions or final conclusion, if possible
  SA2#153E Oct(1.5 TU): Study phase conclusion

## Slide 4: FS_AIMLsys Status at SA#96
WI Code | Work Item Title | WP | Target Date | WID#
FS_AIMLsys | Study on System Support for AI/ML-based Services | 0% > 10 % | October, 22 | SP-211648
Progress since SA#94:
  TR skeleton and scope were agreed. 3 Architecture Assumptions and 2 Architecture Requirements were identified.
  7 key issues approved covering WT#1.1a/b/c/d, WT#1.2 and WT#1.3 from the SID.
  RAN impacts and Other WGs dependencies:
  RAN impact depends on the study outcomes of the solutions.
  SA WG3 (KI#3, 4, 5) and SA WG5 (KI#5)
Next steps:
  Finalized KIs, start of new solution discussions in SA2#150, continuation to study architecture requirements, assumptions, terminology
  SA2#150E Apr (1.0 TU): Last meeting to finalize KIs, start of collecting new possible solutions, continuation to study the architecture requirements, assumptions, terminology.
TO Be Updated

## Slide 5: Backup Slide for Overall Work Planning
(1) TR Skeleton, Scope & New KIs approval & architecture requirements, assumptions, terminology
(2) Last meeting for finalizing KIs, start of collecting possible solutions, continuation to study collecting architecture requirements, assumptions, terminology
(4) TR solution clean-up, solution evaluation, interim conclusions and possible finalize conclusion per KI, if possible
(5) Study phase conclusion
TR 23.700-80 Submission to Dec. 2022 TSG SA#98 for Approval
(3) Last meeting for collecting possible solutions, TR solution clean up, start of solution evaluation and agreeing on interim conclusion, if possible
TR 23.700-80 Submission to Sep. 2022 TSG SA#97 for Information
TR 23.700-80
Study phase
Normative phase