## Slide 1: FS_SFC Status Report
Intel (Rapporteur)

## Slide 2: FS_SFC status after SA2#150E
General
  The latest TR 23.700-18 is available here.
  Total TUs requested for Study Phase is 2.5 TUs, 1.5 TU remaining.
  Total 1 key issues update, 8 solutions agreed
New Key Issues (SA2#150e last e-meeting for any new Key Issue)
  No new Key issue proposal for SA#151e meeting.
Solutions (SA2#151 is the last e-meeting for any new solutions)
  KI#1: Solution for Key Issue #1 for Traffic Steering Policy and SFC Enhancements (S2-2203434)
  KI#1: UPF enhancement with SFC capability (S2-2203438)
  KI#1 & 2: AF influencing Service Function Chaining support by 5GC (S2-2203436)
  KI#1 & 2: New Solution for traffic steering control and SFC enhancements (S2-2203437)
  KI#1 & 2: AF request predefined SFC for traffic flow(s) related with target UE(s) (S2-2203441)
  KI#2: Solution for Key Issue #2 for Exposure to enable AF to request predefined SFC for traffic flow(s) related with target UE(s) (S2-2203435)
  KI#2: Service Function Chaining exposure (S2-2203439)
  KI#2: Enhancing Application Function influence on traffic routing to an N6-LAN based on pre-defined SFC policies (S2-2203440)
WI Code | Work Item Title | WP | Target Date | WID#
FS_SFC | Study on System Enabler for Service Function Chaining | 50% | Aug, 22 | SP-211594

## Slide 3: FS_SFC Work Plan
SA5 dependencies
  SA5 dependencies related to Service Function Management
Contentious Issue:
  N/A
Focus for the Next Meeting (SA2#151E):
  Solutions for all Key Issues, initial evaluation, TR for information at SA#96
Overall Plan:
  SA2#149-E: TR Skeleton, TR Scope, Architectural Assumption, Key Issues, solutions for KIs related to WT#2 and WT#3 (low priority if exceeding 30 papers limits)
  SA2#150-E: any new Key Issue (last meeting), new/revised solutions for all Key Issues/WTs
  [next meeting] SA2#151-E: any new/revised solution (last e-meeting), initial evaluation and potential conclusion, TR for information at SA#96.
  SA2#152-E: solution evaluation and conclusion completion, normative WID, TR for approval at SA#97.
  SA2#153-154AH: update of normative WID if needed, and normative works.
Risks:
  -
TR submission to June 2022 TSG SA#96
for Information
TR and WID submission to Sept. 2022 TSG SA#97 for Approval