## Slide 1: FS_EDGE_Ph2 status report
Patrice Hédé
Huawei Technologies

## Slide 2: EDGE Ph2 status after SA2#150E
  Progress since SA2#149-e:
  Total TUs requested for Study phase in 2022 is 7,25, 2 TUs used until SA2#150E and 5,25 TUs remaining.
  LS reply to SA6 on EDGEAPP Solution for support of roaming UEs in S2-2203479.
  26 contributions approved:
    3 Key issue updates
    23 solutions approved (KI#1: 10; KI#2: 3; KI#4: 6; KI#5: 4)
  Due to quota restrictions, solutions to KI#3, KI#6, KI#7 could not be discussed (19 documents)
  RAN impacts and dependencies:
  TBD
Next steps:
  Conclude KI updates as needed
  Capture new solutions for all KIs.
    Priority will be given to contributions for solutions towards KI#3, KI#6, KI#7 if necessary.
  Update solutions, resolve editor's notes
WI Code | Work Item Title | WP | Target Date | WID#
FS_EDGE_Ph2 | Study on Edge Computing Phase 2 | 13% → 28% | Dec 2022 | SP-211638 → SP-220352

## Slide 3: EDGE Ph2 status after SA2#150E — work plan
Study phase
  SA2#149e, Feb (1TU): Agreement on scenarios/use cases and assumptions for all KIs
  SA2#150e, Apr (1TU): Updates to KI definition. Solutions
  SA2#151e, May (2TU): Solutions
  SA2#152e, Aug (2TU): Solutions, evaluations, conclusions
    Approval of Edge ph2 WID based on first conclusions, TR sent for information
  SA2#153e, Oct (1TU): evaluations, conclusions
    Update of Edge ph2 WID based on remaining conclusions
  SA2#154e, Nov (0,25 TU): final conclusions
    TR sent for approval
 |  |  |  | Feb. 22 | Apr. 22 | May 22 | Aug. 22 | Oct. 22 | Nov. 22 | Jan. 23 | Feb. 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_EDGE_Ph2 | 7,25 | 4,25 | 11,5 | 1 | 1 | 2 | 2 | 1 | 0,25/0,75 | 1,5 | 2 | 11,5

## Slide 4: EDGE Ph2 status at SA#96
  Progress since SA#95-e:
  Total TUs requested for Study phase in 2022 is 7,25,4 TU used until SA2#151E and 3,25 TUs remaining.
  TBD
  RAN impacts and dependencies:
  TBD
Next steps:
  TBD.
WI Code | Work Item Title | WP | Target Date | WID#
FS_EDGE_Ph2 | Study on Edge Computing Phase 2 | 13% →55%? | Dec 2022 | SP-211638 → SP-220352
TO BE UPDATED AFTER SA2#151E