## Slide 1: FS_REDCAP_Ph2 Status Report
Qian Chen
Ericsson

## Slide 2: FS_REDCAP_Ph2 status after SA2#151E (1/2)
  General:
  Total 6 pCRs are agreed, including:
    4 solution update papers (S2-2203711, S2-2204529, S2-2204986, S2-2204987)
    2 evaluation papers (S2-2203712, S2-2204988)
  1 LS out to RAN2/RAN3 is agreed (S2-2204989)
  TR 23.700-68 v0.3.0 is generated based on above agreed contributions
  Total TUs requested for Study Phase in 2022 is 3. 1.5 TU is used and 1.5 TUs are remaining (including 1 TU for normative work)
  RAN impacts and dependencies:
  Conclusions need responses form RAN WGs
  Contentious Issue:
  None
WI Code | Work Item Title | WP | Target Date | WID#
FS_REDCAP_Ph2 | Study on RedCap phase 2 | 50% -> 70 % | September, 22 | SP-220074

## Slide 3: FS_REDCAP_Ph2 status after SA2#151E (2/2)
Focus for the Next Meeting (SA2#152E):
  Evaluation update, if any
  Conclusion
  WID proposal
Overall Plan:
  70% progress on the study. Continue the study based on following overall time plan
    SA2#149E Feb(0.5 TU): TR skeleton; Agreement on scope, architecture assumptions and requirements, key issues; solution proposals
    SA2#150E Apr(0.5 TU): Solution proposals/updates; initial evaluation
    SA2#151E May(0.5 TU): Evaluations; solution update; initial conclusion; TR for information
    SA2#152E Aug(0.5 TU): Evaluations; conclusions; WID approval; TR for approval

## Slide 4: FS_REDCAP_Ph2 Status at SA#96
WI Code | Work Item Title | WP | Target Date | WID#
FS_REDCAP_Ph2 | Study on RedCap phase 2 | 30% -> 70 % | September, 22 | SP-211635
Progress since SA#95-e
  Total 12 pCRs agreed, including:
    9 solutions related papers (S2-2203278, S2-2203279, S2-2203280, S2-2203281, S2-2203599 S2-2203711, S2-2204529, S2-2204986, S2-2204987)
    3 evaluation related papers (S2-2203282, S2-2203712, S2-2204988)
  1 LS out to RAN2/RAN3 is agreed (S2-2204989)
  FS_REDCAP_Ph2 TR 23.700-68 v0.3.0
  RAN impacts and dependencies:
  Conclusions need responses from RAN WGs.
  Next steps:
  Finalize the conclusions

## Slide 5: Annex (FS_REDCAP_Ph2 Status Report from SA#150)

## Slide 6: FS_REDCAP_Ph2 status after SA2#150E (1/2)
  General:
  Total 6 pCRs are agreed, including:
    3 solution update papers (S2-2203278, S2-2203279, S2-2203280)
    2 new solution papers (S2-2203281, S2-2203599)
    1 evaluation paper (S2-2203282)
  TR 23.700-68 v0.2.0 is generated based on above agreed contributions
  Total TUs requested for Study Phase in 2022 is 3. 1 TU is used and 2 TUs are remaining
  RAN impacts and dependencies:
  Key issue 1 requires coordination with RAN WGs
  Contentious Issue:
  None
WI Code | Work Item Title | WP | Target Date | WID#
FS_REDCAP_Ph2 | Study on RedCap phase 2 | 30% -> 50 % | September, 22 | SP-220074

## Slide 7: FS_REDCAP_Ph2 status after SA2#150E (2/2)
Focus for the Next Meeting (SA2#151E):
  Solving ENs/Improvement of existing solutions
  Evaluation, initial conclusion
  Potential further discussion on NF selection function (depends on Rel-17 CR outcome)
Overall Plan:
  50% progress on the study. Continue the study based on following overall time plan
    SA2#149E Feb(0.5 TU): TR skeleton; Agreement on scope, architecture assumptions and requirements, key issues; solution proposals
    SA2#150E Apr(0.5 TU): Solution proposals/updates; initial evaluation
    SA2#151E May(0.5 TU): Evaluations; solution update; initial conclusion; TR for information
    SA2#152E Aug(0.5 TU): Evaluations; conclusions; WID approval; TR for approval