## Slide 1: WI Status Report: Study on Vehicle Mounted Relays (FS_VMR)
Qualcomm Incorporated
S2-2205326

## Slide 2: FS_VMR status after SA2#151E (1/2)
General
  TR 23.700-05 v.0.3.0 was created based on approved contributions.
  7 key issues, 15 solutions documented in the TR.
  0.5 TU used for SA2#151E (1.5 TU used in total) and 1.25 TU left for the Study Phase.
7 Key Issues agreed for the study:
  KI#1: Mobile base station relay configuration support in 5GC
  KI#2: Efficient mobility for UEs connecting to/disconnecting from VMR
  KI#3: Efficient mobility and service continuity when served by VMR
  KI#4: Support of roaming of mobile base station relays
  KI#5: Support of location services for UEs accessing via a mobile base station relay
  KI#6: Provide cell ID/TAC of mobile base station relay for services
  KI#7: Control of UE's access to 5GS via a mobile base station relay
15 candidate solutions documented in TR 23.700-05:
  Solutions addressed KI#1 to 6.
  RAN impacts and dependencies:
  RAN impacts or dependencies identified for Key Issue #1, #2, #3, #4, #6, #7
Other WG dependencies
  Charging support is expected to be handled by SA5, and alignment work in SA2 may be required
WI Code | Work Item Title | WP | Target Date | WID#
FS_VMR | Study on Vehicle Mounted Relays | 40% > 55% | Sept, 22 | SP-211636

## Slide 3: FS_VMR status after SA2#151E (2/2)
Contentious Issue:
  None.
Focus of the Next Meeting (SA2#152E):
  Last chance for new solutions.
  Solution updates and evaluations.
  Interim conclusions.
Overall work Plan:
  SA2#149 Feb’22: 0.5 (TR skeleton, arch assumptions, KIs)
  SA2#150 Apr’22: 0.5 (New KIs; solutions)
  SA2#151 May’22: 0.5 (Last chance for KIs; last chance for new solutions; solution updates)
  SA2#152 Aug’22: 0.5 (Solution updates; evaluations; Interim conclusions, send TR to RAN for comments)
  SA2#153 Oct’22: 0.5 (Finalize conclusions; WID approval)
  SA2#154 Nov’22: 0.25 (Resolve RAN dependent open issues for selected solutions); start normative work.
  SA2#154AH Jan’23: 0.5 (Normative work)
  SA2#155 Feb’23: 1 (Normative work)
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_VMR | 2.75 | 2.25 | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 (0.25+0.75) | 0.5 | 1 | 5

## Slide 4: FS_VMR status at SA#96
Progress since SA#95-e:
  Architecture assumption updated to clarify NR satellite access does not apply to mobile base station relay
  1 new key issue and 15 solutions agreed to be documented in the TR.
  TR 23.700-05 v0.3.0 generated based on the agreed contributions
RAN impacts and dependencies:
  Handled 1 incoming LS from RAN plenary regarding the IAB support of NR satellite access.
Next steps:
  Continue the study
WI Code | Work Item Title | WP | Target Date | WID#
FS_VMR | Study on Vehicle Mounted Relays | 20% > 55% | Sept, 22 | SP-211636