## Slide 1: FS_AMP Status Report
Zhuoyi Chen
China Telecom (Rapporteur)

## Slide 2: FS_AMP status after SA2#151E (1/2)
General
  TR 23.700-89 v0.2.0 is available.
  Total TUs requested for Study Phase is 1.5 TUs, and 0.5 TU is remaining
  1 KI and 10 Solutions are documented.
NO TU is allocated for FS_AMP at SA2#151E. No update for TR23.700-89 v0.2.0 since SA2#150E.
Next Steps: Resolve ENs in solution(s), evaluate solutions and capture conclusion.
  RAN impacts and dependencies:
  No RAN impacts or dependencies are identified
WI Code | Work Item Title | WP | Target Date | WID#
FS_AMP | Study on 5G AM Policy | 80% > 80% | Sept, 22 | SP-211642

## Slide 3: FS_AMP status after SA2#151E (2/2)
Contentious Issue:
  None
Focus for the Next Meeting (SA2#152E):
  Remove EN. Evaluate solutions and reach conclusion.
  Normative WID submission.
Overall Plan:
  SA2#149-E, 0.5 TU assigned, TR Skeleton, TR Scope, Architectural Assumption, Key Issues, allow solutions.
  SA2#150-E, 0.5 TU assigned, no new Key Issue could be allowed and the last e-meeting for new solution(s).
  SA2#151-E, no TU assigned.
  SA2#152-E, 0.5 TU assigned, for solution clean-up, evaluation and conclusion. Normative WID creation. Submit TR23.700-89 to SA#97E.
Risks:
  Conclusion may not be reached at SA2#152-E due to unsolved Editor’s Note of some solutions.

## Slide 4: FS_AMP status at SA#96E
General
  TR23.700-89 skeleton , scope, Architecture Assumptions are agreed
  1 KI agreed
  10 Solutions agreed
  RAN impacts and dependencies
  No RAN impacts or dependencies are identified
Next steps
  SA2#152E (0.5 TU): for solution clean-up, evaluation and conclusion. Normative WID creation. TR23.700-89 ready to SA#97E for approval.
WI Code | Work Item Title | WP | Target Date | WID#
FS_AMP | Study on 5G AM Policy | 35% > 80% | Sept, 22 | SP-211642