## Slide 1: FS_XRM Status Report
Dan Wang, Hui Ni
China Mobile, Huawei

## Slide 2: FS_XRM status after SA2#151E (1/2)
General
  48 p-CRs agreed, including
  2 architecture requirement, term, Annex update
  20 solution update
  26 new solutions
  1 LS Out to SA4
  5 TU used and 4 TU left for the Study Phase.
Architectural requirement
  2 p-CRs terms and architecture requirement update
Key Issue1&2(Coordinated transmission for single UE& multiple UEs)
  1 p-CR updating the existing solution
  5 p-CRs adding new solutions
  Next step: Continue the work and start evaluation
Key Issue 3 (Information Exposure)
  2 p-CR updating the existing solution
  8 p-CRs adding new solutions
  Next step: Continue the work and start evaluation
Key Issues 4&5(PDU Set )
  12 p-CR updating the existing solution
  9 p-CRs adding new solutions
  Next step: Continue the work and start evaluation
WI Code | Work Item Title | WP | Target Date | WID#
FS_XRM | Study on XR (Extended Reality) and media services | 25%  40% | Dec, 2022 | SP-211646
Key Issue 6(Round-Trip latency requirements)
  1 p-CR updating the existing solution
  Next step: Continue the work and start evaluation
Key Issues 7(jitter minimization)
  2 p-CR updating the existing solution
  Next step: Continue the work and start evaluation
Key Issues 8 (power savings)
  2 p-CR updating the existing solution
  4 p-CRs adding new solutions
  Next step: Continue the work and start evaluation
Key Issues 9(Trade-off of QoE and Power Saving)
  1 p-CRs adding new solutions
  Next step: Continue the work and start evaluation

## Slide 3: FS_XRM status after SA2#151E (2/2)
  RAN impacts and dependencies:
  No
Other WG dependencies
  1 LS to SA4 for coordination
Contentious Issue:
  SID update for WT#1(related with KI1&2)
Focus for the Next Meeting (SA2#152):
  Handle solution update and new solutions, start solution evaluation
Overall Plan: (study phase)
  SA2#149 Feb’22: TR skeleton, arch assumptions, KIs
  SA2#150 Apr’22: solutions discussions, and KIs. Finalize the KIs (no new KI proposal afterwards)
  SA2#151 May’22: potential KI update, solution discussions; solution evaluation with low priority
  SA2#152 Aug’22: solution updates (last chance for new solution)and try to finalize start the evaluation and make conclusion ; send TR for information; first draft of WID
  SA2#153 Oct’22: finalize the conclusion for remaining TR KIs; WID Approval;
  SA2#154, SA2#154AH and SA2#155 meeting: normative work
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155
FS_XRM | 9 | 5 | 14 | 1 | 2 | 2 | 2 | 2 | 1 | 2 | 2

## Slide 4: FS_XRM Status after SA#95-e
WI Code | Work Item Title | WP | Target Date | WID#
FS_XRM | Study on XR (Extended Reality) and media services | 25%  40% | Dec, 2022 | SP-211646
  Progress since SA#95-e:
  86 p-CRs are approved
  The TR now including 62 solutions
  RAN impacts and dependencies:
  1 LS to RAN1&2 for power saving
Other WG dependencies
  2 LSs are sent to SA4 for coordination
Contentious Issue:
  SID update for WT#1(related with KI1&2)
Next steps in SA2#151E:
  The last time for capturing new solutions.
  Start solution evaluation and conclusion