## Slide 1: FS_5G_ProSe_Ph2 Status Report
CATT, OPPO

## Slide 2: FS_5G_ProSe_Ph2 status after SA2#151E (1/2)
General
  TR 23.700-33 v.0.3.0 was created based on approved contributions.
  19 new solutions and 9 solution update agreed for existing KIs.
  3 TUs used in total and 3 TUs left for the Study Phase.
  RAN impacts and dependencies:
  RAN impacts or dependencies identified for Key Issue #1, #2, #4, #5, #6 and #7.
Other WG dependencies
  Charging support is expected to be handled by SA5 and Security support is expected to be handled by SA3, and cooperation with SA5 and SA3 may be required.
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe_Ph2 | Study on Proximity-based Services in 5GS Phase 2 | 35% -> 55% | Sept, 22 | SP-211653

## Slide 3: FS_5G_ProSe_Ph2 status after SA2#151E (2/2)
Contentious Issue:
  None.
Focus for the Next Meeting (SA2#152E):
  No new Key Issue, no new solution.
  Handle solution update/consolidated solutions for all Key Issues.
  Solution evaluation and conclusion.
Overall Plan: (study phase)
  SA2#149-E, 1 TU assigned, TR Skeleton, TR Scope, Architectural Assumption, Key Issues, solutions if quota allowed.
  SA2#150-E, 1 TU assigned, Last e-meeting for any new Key Issue, solutions.
  SA2#151-E, 1 TU assigned, Last e-meeting for any new solution, start the initial evaluation.
  SA2#152-E, 1 TU assigned, Solution evaluation and conclusion, normative WID creation.
  SA2#153-E, 2 TU assigned, Finalize conclusions, update of normative WID if needed, TR for approval.
Risks:
  None.

## Slide 4: FS_5G_ProSe_Ph2 status at SA#96
Progress since SA#95-e:
  1 new key issue and 41 solutions agreed to be documented in the TR 23.700-33.
  TR 23.700-33 v0.3.0 generated based on the agreed contributions
RAN impacts and dependencies:
  RAN impacts or dependencies identified for Key Issue #1, #2, #4, #5, #6 and #7.
Next steps:
  Continue the study
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_ProSe_Ph2 | Study on Proximity-based Services in 5GS Phase 2 | 20% > 55% | Sept, 22 | SP-211653