## Slide 1: FS_eNPN_Ph2 Status Report
Peter Hedman
Ericsson (Rapporteur)

## Slide 2: FS_eNPN_Ph2 status after SA2#152E (1/3)
General
  28 P-CRs agreed
  1 LS out to SA3 sent on “Questions for SUCI protection requirements for non-3GPP (WLAN) access to SNPN” related to KI#2
  KI#1 evaluations and conclusions finalized
  KI#2 evaluations and conclusions been agreed, but 4 open issues been identified whereas at least 1 requires progress by SA3. SA2#153e meeting is expected to finalize the open issues that can be addressed by SA2.
  Evaluations started for KI#3-6, minor interim conclusions agreed
  8 new solutions added; the TR now includes 47 solutions
  Latest TR 23.700-08 is available here.
  Total TUs requested for Study Phase is 5.5 TUs, and 1 TU is remaining
Related to Key Issue 1: Enabling support for idle and connected mode mobility between SNPNs without new network selection
  1 P-CRs adding evaluation and conclusion agreed after Show-of-Hands (whether to include support for equivalent SNPNs with different SNPN IDs within the RA, it was agreed to exclude such support)
  Next Steps:
    Study finalized, i.e. normative work to be initiated according to the agreed conclusions
Related to Key Issue 2: Support of Non-3GPP access for SNPN
  1 P-CR with evaluations and 1 P-CR with conclusions agreed, including 4 ENs with open issues
  Next Steps:
    Finalize conclusions resolving the identified open issues and initiate normative work
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNPN_Ph2 | Enhanced support of Non-Public Networks | 50% > 75% | Sept, 22 | SP-211656

## Slide 3: FS_eNPN_Ph2 status after SA2#152E (2/3)
Related to Key Issue 3: Enabling NPN as hosting network for providing access to localized services
  1 P-CR updating solutions agreed
  1 P-CR adding evaluations and interim conclusions agreed
  Next Steps:
    Finalize the work i.e. evaluations and conclusions
Related to Key Issue 4: Enabling UE to discover, select and access NPN as hosting network and receive localized services
  9 P-CRs updating solutions agreed
  5 P-CRs adding a new solution agreed
  1 P-CR adding evaluations agreed
  Next Steps:
    Finalize the work i.e. evaluations and conclusions
Related to Key Issue 5: Enabling access to localized services via a specific hosting network
  1 P-CR updating solution agreed
  2 P-CRs adding a new solution agreed
  1 P-CR adding evaluations and interim conclusions agreed
  Next Steps:
    Finalize the work i.e. evaluations and conclusions
Related to Key Issue 6: Support for returning to home network
  2 P-CRs updating solution agreed
  1 P-CRs adding a new solution agreed
  1 P-CR adding evaluations and interim conclusions agreed
  Next Steps:
    Finalize the work i.e. evaluations and conclusions

## Slide 4: FS_eNPN_Ph2 status after SA2#152E (3/3)
  RAN impacts and dependencies:
  Potential RAN impacts or dependencies identified for Key Issue 1, 2 and 4.
WG dependencies
  SA3 dependencies related to key issue 2, 3, 4, 5
  SA5 dependencies related to key issue 3 and 5
Contentious Issue:
  none
Focus for the Next Meeting (SA2#153E):
  Evaluation and conclusions
  Update of normative WID based on conclusions, TBD whether to handle normative work related to KI#2 at SA2#153e
Overall Plan:
  SA2#149-E, 1 TU assigned, TR Skeleton, TR Scope, Architectural Assumption, Key Issues, allow solutions for KIs related to WT#1 and WT#2.
  SA2#150-E, 1 TU assigned, last e-meeting for any new Key Issue, solutions for all Key Issues/WTs
  SA2#151-E, 1,5 TU assigned, The last e-meeting for any new solution related to KI#1 and KI#2, start the initial evaluation, TR for information.
  SA2#152-E, 1 TU assigned, last e-meeting for any new solution related to KI#3-6, solution evaluation and conclusion, normative WID creation.
  SA2#153-E, 1 TU assigned, solution evaluation and conclusion, update of normative WID if needed, TR for approval (TBD if done at #152).
Risks:
  Some aspects dependent on SA3 progress

## Slide 5: FS_eNPN_Ph2 Status at SA#97e
Progress since SA#96-e:
  28 P-CRs agreed
  1 LS out to SA3 sent on “Questions for SUCI protection requirements for non-3GPP (WLAN) access to SNPN”
  KI#1 evaluations and conclusions finalized
  KI#2 evaluations and conclusions been agreed, but 4 open issues been identified whereas at least 1 requires progress by SA3. SA2#153e meeting is expected to finalize the open issues that can be addressed by SA2.
  Evaluations started for KI#3-6, minor interim conclusions agreed
  8 new solutions added; the TR now includes 47 solutions
  RAN impacts and dependencies:
  No new RAN impact identified (key issues 1, 2 and 4 have potential RAN impact)
Next steps:
  Finalize the study and initiate normative work
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNPN_Ph2 | Enhanced support of Non-Public Networks | 50% > 75% | Sept, 22 | SP-211656