## Slide 1: FS_EDGE_Ph2 status report
Patrice Hédé
Huawei Technologies

## Slide 2: EDGE Ph2 status after SA2#151E
  Progress since SA2#151-e:
  Total TUs requested for Study phase in 2022 is 7,25, 6 TUs used until SA2#152E and 1,25 TUs remaining.
  36 contributions approved:
    2 Key Issue updates (KI#1, KI#2)
    24 solution updates (KI#1:7+3, KI#3:1, KI#4:5, KI#5:5, KI#6:2, KI#7:1)
    3 new solutions (KI#1/HR:1, KI#4:1, KI#5:1)
  4 KIs (out of 7) have received conclusions:
    1 KI (KI#7) have received a complete conclusion
    3 KIs (KI#1(HR+LBO), KI#4, KI#4) have received a partial conclusion
  TR sent for information
  RAN impacts and dependencies:
  TBD
Next steps in SA2#153e:
  Complete evaluations and conclusions
  Send TR for approval
  Approve complete WID
WI Code | Work Item Title | WP | Target Date | WID#
FS_EDGE_Ph2 | Study on Edge Computing Phase 2 | 55% → 83% | Dec 2022 | SP-220352

## Slide 3: EDGE Ph2 status after SA2#152E — work plan
Study phase
  SA2#149e, Feb (1TU): Agreement on scenarios/use cases and assumptions for all KIs
  SA2#150e, Apr (1TU): Updates to KI definition. Solutions
  SA2#151e, May (2TU): Solutions
  SA2#152e, Aug (2TU): Solutions, evaluations, conclusions
    Approval of first version of Edge ph2 WID based on first conclusions, TR sent for information
  SA2#153e, Oct (1TU): evaluations, conclusions
    Completion of conclusions, Edge ph2 WID based on remaining conclusions
  SA2#154e, Nov (0,25 TU): final conclusions
    TR sent for approval
 |  |  |  | Feb. 22 | Apr. 22 | May 22 | Aug. 22 | Oct. 22 | Nov. 22 | Jan. 23 | Feb. 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_EDGE_Ph2 | 7,25 | 4,25 | 11,5 | 1 | 1 | 2 | 2 | 1 | 0,25/0,75 | 1,5 | 2 | 11,5

## Slide 4: EDGE Ph2 status at SA#96
  Progress since SA#96-e:
  Total TUs requested for Study phase in 2022 is 7,25,6 TU used until SA2#152E and 1,25 TUs remaining.
  55 solutions have been approved for all 7 KIs (+3 solutions since SA#96e).
  4 KIs have received partial or complete conclusions.
  RAN impacts and dependencies:
  TBD
Next steps at SA#98:
  Complete evaluations and conclusions for all 7 KIs
  TR to be sent for approval
  Complete Edge Ph2 WID for approval
WI Code | Work Item Title | WP | Target Date | WID#
FS_EDGE_Ph2 | Study on Edge Computing Phase 2 | 55% →83% | Dec 2022 | SP-220352