## SA2 Work Plan @ SA2#154AH-E
SA WG2 Meeting #154AHE |  |  | S2-2300381
Jan 16 – 20, 2023
|  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | Apr, 23 | May, 23
|  |  |  | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | #156 | #157
|  |  |  | Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan
Rel-15/Rel-16 maintenance
| Combined (Multiple WIDs) |  |  | 3 | 3 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Sum |  |  | 3 | 3 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Rel-17 maintenance
| Combined (17 WIDs) |  |  | 12 | 12 | 10 | 8 | 8 | 6 | 4 | 4 | 4 | 4
| Sum |  |  | 12 | 12 | 10 | 8 | 8 | 6 | 4 | 4 | 4 | 4
Rel-17 Alignment (with RAN/CT)
| Combined (3 WIDs) |  |  | 3 | 3 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0
Total (Maintenance) |  |  |  | 18 | 18 | 13 | 12 | 12 | 9 | 6 | 6 | 6 | 6
Buffer (TEI18, overflow, other)
| Buffer |  |  | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3
Total (Maintenance + Buffer) |  |  |  | 18 | 18 | 13 | 12 | 15 | 12 | 9 | 9 | 9 | 9
Available for Rel-18 SIDs/WIDs |  |  |  | 20 | 20 | 25 | 26 | 23 | 26 | 29 | 29 | 29 | 29
|  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | Apr, 23 | May, 23
Rel-18 SID/WID | Study TU (Planned) | Normative TU (Planned) | Total TU (Planned) | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | #156 | #157 | Study TU (Used) | Study % Compeltion | Work % completion | Normative TU (Used) | Total TU (Remaining) | Additonal TU Requested
FS_SATB | 3.5 | 1.5 | 5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 0.5 | 0 | 0.5 | 0 | 3.5 | 100% | 30% | 1 | 0.5 | 0.5
FS_5GSAT_Ph2 | 4 | 1 | 5 | 0.5 | 0.5 | 1 | 1 | 1 | 0 | 0.5 | 1 | 0.5 | 0 | 4 | 100% | 0% | 0 | 1 | 1
FS_PIN | 3.5 | 2 | 5.5 | 0.5 | 0.5 | 1 | 1 | 0.5 | 0 | 1 | 0 | 1 | 0 | 3.5 | 95% | 0% | 0 | 2 | 0
FS_UAS_Ph2 | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 0.5 | 1 | 0.75 | 0 | 1 | 1 | 1 | 0 | 3.25 | 98% | 0% | 0 | 2.25 | 1
FS_Ranging_SL | 3.5 | 2 | 5.5 | 0.5 | 0.5 | 1 | 0.5 | 0.5 | 0 | 1.5 | 1 | 1.5 | 0 | 3 | 85% | 0% | 0 | 2.5 | 1.5
FS_eLCS_Ph3 | 6.25 | 4 | 10.25 | 1 | 1 | 1 | 1.5 | 1.75 | 2 | 1.5 | 0.5 | 1 | 1 | 7.25 | 100% | 30% | 1 | 2 | 2
FS_5G_ProSe_Ph2 | 6 | 3.25 | 9.25 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 0.5 | 7 | 100% | 20% | 1 | 1.25 | 2.25
FS_GMEC | 4 | 1.75 | 5.75 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0.75 | 0 | 0.5 | 0.5 | 4 | 95% | 15% | 0.5 | 1.25 | 0.5
FS_AIMLsys | 7 | 5 | 12 | 1 | 1 | 1.5 | 2 | 1.5 | 2 | 2 | 1 | 2 | 1 | 8.5 | 100% | 5% | 0.5 | 3 | 3
FS_5MBS_Ph2 | 7.5 | 4.5 | 12 | 1 | 1 | 2 | 2 | 1 | 2 | 2 | 1 | 1 | 0 | 8.5 | 100% | 20% | 0.5 | 3 | 1
FS_eNS_Ph3 | 6 | 3.25 | 9.25 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1.25 | 1 | 7.75 | 100% | 1% | 0.25 | 1.25 | 3
FS_XRM | 9 | 5 | 14 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 11 | 100% | 0% | 0 | 3 | 4
FS_REDCAP_Ph2 | 2 | 1 | 3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5 | 0 | 0.25 | 0 | 2 | 100% | 60% | 0.5 | 0.5 | 0.25
FS_NG_RTC | 4 | 2 | 6 | 1 | 1 | 1 | 1 | 0.5 | 0 | 1 | 1 | 1 | 0 | 4.5 | 85% | 0% | 0 | 1.5 | 1.5
FS_ATSSS_ph3 | 6 | 2.5 | 8.5 | 0.5 | 1.5 | 1 | 2 | 1 | 0 | 1.25 | 0 | 1.25 | 0 | 6 | 100% | 0% | 0 | 2.5 | 0
FS_UPEAS | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 1 | 1 | 1 | 0 | 1 | 0.5 | 0 | 0 | 3.25 | 98% | 20% | 0.75 | 1.5 | 0
FS_EDGE_Ph2 | 7.25 | 4.25 | 11.5 | 1 | 1 | 2 | 2 | 1 | 2 | 1.5 | 1 | 1 | 0 | 8 | 100% | 15% | 1 | 2.5 | 1
FS_5TRS_URLLC | 5 | 4 | 9 | 1 | 1 | 1 | 1.5 | 1.5 | 2 | 1 | 0 | 0.5 | 0 | 7 | 98% | 50% | 1 | 1 | 0.5
FS_VMR | 2.75 | 2.25 | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 0.5 | 0 | 0.5 | 0 | 3.5 | 100% | 20% | 1 | 0.5 | 0.5
FS_5WWC_Ph2 | 1.5 | 1 | 2.5 | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0 | 0.25 | 0 | 0.75 | 0 | 1.5 | 90% | 20% | 0.5 | 0.5 | 0.5
MPS_WLAN | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | NA | 0% | 1 | 1 | 0
FS_AMP | 1.5 | 0.5 | 2 | 0.5 | 0.5 | 0 | 0.5 | 0.25 | 0 | 0.25 | 0 | 0 | 0 | 1.5 | 100% | 80% | 0.25 | 0.25 | 0
FS_eNA_Ph3 | 8 | 6 | 14 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 9 | 100% | 25% | 1 | 4 | 3
FS_eNPN_Ph2 | 5.5 | 4.25 | 9.75 | 1 | 1 | 1.5 | 1 | 1.5 | 2 | 1 | 1 | 0.75 | 0 | 7 | 98% | 50% | 1 | 1.75 | 1
FS_eUEPO | 4.25 | 1.5 | 5.75 | 0.5 | 1 | 1 | 1 | 0.75 | 0 | 0.75 | 1 | 1 | 0 | 4.25 | 95% | 0% | 0 | 1.5 | 1.25
FS_SFC | 2.5 | 1.5 | 4 | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 3 | 100% | 0% | 0 | 1 | 0
FS_DetNet | 1 | 1 | 2 | 0.25 | 0 | 0.5 | 0.25 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | 1 | 90% | 0% | 0 | 1 | 0.5
FS_SUECR | 1.5 | 0.25 | 1.75 | 0.5 | 0.5 | 0.5 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 1.5 | 100% | 100% | 0.25 | 0 | 0
TEI18_MLR |  | 0.5 | 0.5 | #153: 0.25; #154: 0.25 |  | NA | 100% | 0.5 | 0
TEI18_SDNAEPC |  | 0.5 | 0.5 | #153: 0.25; #154: 0.25 |  | NA | 100% | 0.5 | 0
TEI18_MBS4V2X |  | 1 | 1 | #154AH: 0.5; #155: 0.5 |  | NA | 0% | 0 | 1
TEI18_SLAMUP |  | 1 | 1 | #154AH: 0.5; #155: 0.5 |  | NA | 0% | 0 | 1
TEI18_ADEE |  | 0.5 | 0.5 | #154AH: 0.25; #155: 0.25 |  | NA | 0% | 0 | 0.5
TEI18_IPv6PD |  | 0.5 | 0.5 | #154AH: 0.25; #155: 0.25 |  | NA | 0% | 0 | 0.5
TEI18_DCAMP_Ph2 |  | 0.5 | 0.5 | #156: 0.25; #157: 0.25 |  | NA | 0% | 0 | 0.5
eNSAC |  | 0.5 | 0.5 | #156: 0.25; #157: 0.25 |  | NA | 0% | 0 | 0.5
Total | 119.5 | 76.75 | 196.25 | 19.25 | 21.5 | 27.5 | 29.75 | 26.75 | 23.5 | 28.75 | 18 | 24.25 | 6.5 | 134.25 |  |  | 14 | 48 | 29.75
NOTE1: Planning is based on max 38 TUs (including 3TU as buffer) per meeting
NOTE2: TU budget estimates assumes 8 meetings untill stage-2 freeze deadline
Note on K34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 (Normative) + 0.5 (Study)
Note on J39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 0.5 + 0.5
Note on I45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .25 + .75
Note on J46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .25 + .75
Note on I47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 0.5 + 1
Note on J48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .25 + .75
Note on I53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 (Study) + 0.5 (normative)

## SA2 Work Plan post SA2#154
SA WG2 Meeting #154
|  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23
|  |  |  | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155
|  |  |  | Plan | Plan | Plan | Plan | Plan | Plan | Plan | Plan
Rel-15/Rel-16 maintenance
| Combined (Multiple WIDs) |  |  | 3 | 3 | 0 | 2 | 2 | 2 | 2 | 2
| Sum |  |  | 3 | 3 | 0 | 2 | 2 | 2 | 2 | 2
Rel-17 maintenance
| Combined (17 WIDs) |  |  | 12 | 12 | 10 | 8 | 8 | 6 | 4 | 4
| Sum |  |  | 12 | 12 | 10 | 8 | 8 | 6 | 4 | 4
Rel-17 Alignment (with RAN/CT)
| Combined (3 WIDs) |  |  | 3 | 3 | 3 | 2 | 2 | 1 | 0 | 0
Total (Maintenance) |  |  |  | 18 | 18 | 13 | 12 | 12 | 9 | 6 | 6
Buffer (TEI18, overflow, other)
| Buffer |  |  | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3
Total (Maintenance + Buffer) |  |  |  | 18 | 18 | 13 | 12 | 15 | 12 | 9 | 9
Available for Rel-18 SIDs/WIDs |  |  |  | 20 | 20 | 25 | 26 | 23 | 26 | 29 | 29
|  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23
Rel-18 SID/WID | Study TU (Planned) | Normative TU (Planned) | Total TU (Planned) | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Study TU (Used) | Study % Compeltion | Work % completion | Normative TU (Used) | Total TU (Remaining)
FS_SATB | 3.5 | 1.5 | 5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 0.5 | 0 | 3.5 | 100% | 30% | 1 | 0.5
FS_5GSAT_Ph2 | 4 | 1 | 5 | 0.5 | 0.5 | 1 | 1 | 1 | 0 | 0.5 | 0.5 | 4 | 100% | 0% | 0 | 1
FS_PIN | 3.5 | 2 | 5.5 | 0.5 | 0.5 | 1 | 1 | 0.5 | 0 | 1 | 1 | 3.5 | 95% | 0% | 0 | 2
FS_UAS_Ph2 | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 0.5 | 1 | 0.75 | 0 | 1 | 1.25 | 3.25 | 98% | 0% | 0 | 2.25
FS_Ranging_SL | 3.5 | 2 | 5.5 | 0.5 | 0.5 | 1 | 0.5 | 0.5 | 0 | 1.5 | 1 | 3 | 85% | 0% | 0 | 2.5
FS_eLCS_Ph3 | 6.25 | 4 | 10.25 | 1 | 1 | 1 | 1.5 | 1.75 | 2 | 1.5 | 0.5 | 7.25 | 100% | 30% | 1 | 2
FS_5G_ProSe_Ph2 | 6 | 3.25 | 9.25 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 0.25 | 7 | 100% | 20% | 1 | 1.25
FS_GMEC | 4 | 1.75 | 5.75 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0.75 | 0.5 | 4 | 95% | 15% | 0.5 | 1.25
FS_AIMLsys | 7 | 5 | 12 | 1 | 1 | 1.5 | 2 | 1.5 | 2 | 2 | 1 | 8.5 | 100% | 5% | 0.5 | 3
FS_5MBS_Ph2 | 7.5 | 4.5 | 12 | 1 | 1 | 2 | 2 | 1 | 2 | 2 | 1 | 8.5 | 100% | 20% | 0.5 | 3
FS_eNS_Ph3 | 6 | 3.25 | 9.25 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 0.25 | 7.75 | 100% | 1% | 0.25 | 1.25
FS_XRM | 9 | 5 | 14 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 11 | 100% | 0% | 0 | 3
FS_REDCAP_Ph2 | 2 | 1 | 3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0.5 | 0 | 2 | 100% | 60% | 0.5 | 0.5
FS_NG_RTC | 4 | 2 | 6 | 1 | 1 | 1 | 1 | 0.5 | 0 | 1 | 0.5 | 4.5 | 85% | 0% | 0 | 1.5
FS_ATSSS_ph3 | 6 | 2.5 | 8.5 | 0.5 | 1.5 | 1 | 2 | 1 | 0 | 1.25 | 1.25 | 6 | 100% | 0% | 0 | 2.5
FS_UPEAS | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 1 | 1 | 1 | 0 | 1 | 0.5 | 3.5 | 98% | 20% | 0.5 | 1.5
FS_EDGE_Ph2 | 7.25 | 4.25 | 11.5 | 1 | 1 | 2 | 2 | 1 | 2 | 1.5 | 1 | 8 | 100% | 15% | 1 | 2.5
FS_5TRS_URLLC | 5 | 4 | 9 | 1 | 1 | 1 | 1.5 | 1.5 | 2 | 1 | 0 | 7 | 98% | 50% | 1 | 1
FS_VMR | 2.75 | 2.25 | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 0.5 | 0 | 3.5 | 100% | 20% | 1 | 0.5
FS_5WWC_Ph2 | 1.5 | 1 | 2.5 | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0 | 0.25 | 0.25 | 1.5 | 90% | 20% | 0.5 | 0.5
MPS_WLAN | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0.5 | 0.5 | 0 | NA | 0% | 1 | 1
FS_AMP | 1.5 | 0.5 | 2 | 0.5 | 0.5 | 0 | 0.5 | 0.25 | 0 | 0.25 | 0 | 1.5 | 100% | 80% | 0.25 | 0.25
FS_eNA_Ph3 | 8 | 6 | 14 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 9 | 100% | 25% | 1 | 4
FS_eNPN_Ph2 | 5.5 | 4.25 | 9.75 | 1 | 1 | 1.5 | 1 | 1.5 | 2 | 1 | 0.75 | 7 | 98% | 50% | 1 | 1.75
FS_eUEPO | 4.25 | 1.5 | 5.75 | 0.5 | 1 | 1 | 1 | 0.75 | 0 | 0.75 | 0.75 | 4.25 | 95% | 0% | 0 | 1.5
FS_SFC | 2.5 | 1.5 | 4 | 0.5 | 0.5 | 0.5 | 1 | 0.5 | 0 | 0.5 | 0.5 | 3 | 100% | 0% | 0 | 1
FS_DetNet | 1 | 1 | 2 | 0.25 | 0 | 0.5 | 0.25 | 0 | 0 | 0.5 | 0.5 | 1 | 90% | 0% | 0 | 1
FS_SUECR | 1.5 | 0.25 | 1.75 | 0.5 | 0.5 | 0.5 | 0 | 0.25 | 0 | 0 | 0 | 1.5 | 100% | 100% | 0.25 | 0
TEI18_MLR |  | 0.5 | 0.5 | #153: 0.25; #154: 0.25 |  | NA | 100% | 0.5 | 0
TEI18_SDNAEPC |  | 0.5 | 0.5 | #153: 0.25; #154: 0.25 |  | NA | 100% | 0.5 | 0
TEI18_MBS4V2X |  | 1 | 1 | [9 empty] | NA | 0% | 0 | 1
TEI18_SLAMUP |  | 1 | 1 | [9 empty] | NA | 0% | 0 | 1
TEI18_ADEE |  | 0.5 | 0.5 | [9 empty] | NA | 0% | 0 | 0.5
TEI18_IPv6PD |  | 0.5 | 0.5 | [9 empty] | NA | 0% | 0 | 0.5
TEI18_DCAMP_Ph2 |  | 0.5 | 0.5 | [9 empty] | NA | 0% | 0 | 0.5
eNSAC |  | 0.5 | 0.5 | [9 empty] | NA | 0% | 0 | 0.5
Total | 119.5 | 76.75 | 196.25 | 19.25 | 21.5 | 27.5 | 29.75 | 26.75 | 23.5 | 27.25 | 16.75 | 134.5 |  |  | 13.75 | 48
NOTE1: Planning is based on max 38 TUs (including 3TU as buffer) per meeting
NOTE2: TU budget estimates assumes 8 meetings untill stage-2 freeze deadline
Note on K34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 (Normative) + 0.5 (Study)
Note on J39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 0.5 + 0.5
Note on I45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .25 + .75
Note on J46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .25 + .75
Note on I47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 0.5 + 1
Note on J48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .25 + .75
Note on I53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 (Study) + 0.5 (normative)