## Slide 1: WI and SID Status Report on 5G AM Policy (AMP)
Zhuoyi Chen
China Telecom (Rapporteur)

## Slide 2: FS_AMP status after SA2#153E
General
  TR 23.700-89 v18.0.0 is available.
  Study phase is completed in SA2#152E.
  5 CRs are approved at SA2#154AHE.
  Normative phase is completed at SA2#154AHE.
Key Issue #1: RFSP Index consistency when UE moves from 5GC to EPC
  1 CR for 23.501 and 1 CR for 23.503 are approved to solve EN from SA2#153E.
  1 CR for 23.501 and 1 CR for 23.502 are approved for further clarification.
  1 CR for 23.502 for missing part from approved CR from SA2#153E.
  RAN impacts and dependencies:
  No RAN impacts or dependencies are identified
WI Code | Work Item Title | WP | Target Date | WID#
FS_AMP | Study on 5G AM Policy | 100% | Sept, 22 | SP-211642
AMP | 5G AM Policy | 80% -> 100% | ->Mar, 23 | SP-220807

## Slide 3: FS_AMP status after SA2#153E (2/2)
Contentious Issue:
  None
Overall Plan:
  SA2#149-E, 0.5 TU assigned, TR Skeleton, TR Scope, Architectural Assumption, Key Issues, allow solutions.
  SA2#150-E, 0.5 TU assigned, no new Key Issue could be allowed and the last e-meeting for new solution(s).
  SA2#151-E, no TU assigned.
  SA2#152-E, 0.5 TU assigned, for solution clean-up, evaluation and conclusion. Normative WID creation. Submit TR23.700-89 to SA#97E.
  SA2#153-E: 0.25 TU assigned, for normative
  SA2#154AH: 0.25 TU assigned, for normative
  Normative work is completed.
Risks:
  None.

## Slide 4: FS_AMP status at SA#98E
General
  TR 23.700-89 v18.0.0 is available.
  Study phase is completed.
  5 CRs are approved at SA2#154AHE.
  Normative phase is completed.
  RAN impacts and dependencies
  No RAN impacts or dependencies are identified
WI Code | Work Item Title | WP | Target Date | WID#
FS_AMP | Study on 5G AM Policy | 100% | Sept, 22 | SP-211642
AMP | 5G AM Policy | 80% -> 100% | Mar, 23 | SP-220807