## Slide 1: FS_eNPN_Ph2 + eNPN_Ph2 Status Report
Peter Hedman
Ericsson (Rapporteur)

## Slide 2: FS_eNPN_Ph2 and eNPN_Ph2 status after SA2#154AHE (1/3)
General
  3 P-CRs to TR 23.700-08 agreed
    The outstanding issue whether to standardize any additional Localized Service related information that may be sent to the UE to aid manual selection of hosting network has been resolved without further normative changes.
    Added optional location validity conditions to Credentials Holder controlled prioritized lists for automatic SNPN selection
  Latest TR 23.700-08 is available here; TR regarded as 100% complete and to be sent to TSG SA for approval from SA2#155
  10 CRs approved
  WID update postponed
  1 LS out sent to RAN2, RAN3 on “LS on RAN impact for NPN enhancement in Rel-18” with a summary of the RAN impacts due to eNPN_Ph2
  1 LS out sent to CT1 on “Regarding issues related to SNPN selection for Localized services”
  CR and LS out related to support for NSWO with CH postponed
  2 CRs related to CAG enhancements postponed
Related to Key Issue 1: Enabling support for idle and connected mode mobility between SNPNs without new network selection
  1 CR noted.
  Work completed.
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNPN_Ph2 | Enhanced support of Non-Public Networks | 98% > 100% | Dec, 22 | SP-211656
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNPN_Ph2 | Enhanced support of Non-Public Networks | 98% > 100% | Dec, 22 | SP-211656
eNPN_Ph2 | Enhanced support of Non-Public Networks | 50% > 70% | Mar, 23 -> Jun 23 | SP-220805 ->S2-23xyz

## Slide 3: FS_eNPN_Ph2 and eNPN_Ph2 status after SA2#154AHE (2/3)
Related to Key Issue 2: Support of Non-3GPP access for SNPN
  3 CRs approved (2 for TS 23.501 and 1 for TS 23.316)
  CRs related to the approved CRs but for other specifications marked as not handled
  One open issue for wireline support of onboarding noted in one of the approved CRs
Related to Key Issue 3: Enabling NPN as hosting network for providing access to localized services
  1 CR approved for TS 23.501
Related to Key Issue 4: Enabling UE to discover, select and access NPN as hosting network and receive localized services
  4 CRs approved (3 for TS 23.501 and 1 for TS 23.502)
  1 LS out on “Regarding issues related to SNPN selection for Localized services” sent to CT1 asking for feedback whether to extend existing lists or create new lists with validity conditions (issue left open in related CRs)
  2 CRs related to CAG enhancements postponed
Related to Key Issue 5: Enabling access to localized services via a specific hosting network
  1 CR approved for TS 23.501
  An open issue related to validity for SM procedures
Related to Key Issue 6: Support for returning to home network
  1 CR approved for TS 23.501

## Slide 4: FS_eNPN_Ph2 and eNPN_Ph2 status after SA2#154AHE (3/3)
  RAN impacts and dependencies:
  RAN impacts identified for Key Issue 1 and 2
WG dependencies
  SA3 dependencies related to key issue 2 and 4
Contentious Issue:
  Issue on providing UE with additional information UE for manual selection of hosting network resolved without any normative changes
Focus for the Next Meeting (3GPPSA2#155 in Feb 2023):
  Finalize the normative work (related to KI#2, KI#4 and KI#5)
Overall Plan:
  SA2#149-E, 1 TU assigned, TR Skeleton, TR Scope, Architectural Assumption, Key Issues, allow solutions for KIs related to WT#1 and WT#2.
  SA2#150-E, 1 TU assigned, last e-meeting for any new Key Issue, solutions for all Key Issues/WTs
  SA2#151-E, 1,5 TU assigned, The last e-meeting for any new solution related to KI#1 and KI#2.
  SA2#152-E, 1 TU assigned, last e-meeting for any new solution related to KI#3-6, solution evaluation and conclusion, normative WID creation.
  SA2#153-E, 1 TU assigned, solution evaluation and conclusion, update of normative WID if needed, TR for approval
  SA2#154, use TU planned for normative work to finalize the study, update normative WID, TR for approval->information.
  SA2#154AHE (Jan 2023), normative work
  SA2#155, normative work
  SA2#156, normative work
Risks:
  Some aspects dependent on SA3 progress

## Slide 5: FS_eNPN_Ph2 and eNPN_Ph2 Status at SA#98e
Progress since SA#97-e of FS_eNPN_Ph2:
  18 P-CRs agreed
  1 LS out sent to SA1, SA3, CT1 on “Progress and open issues for NPN enhancements in Rel-18” related to KI#2 and KI#4
  1 LS out sent to SA3-LI on “LI requirements applicable to non-3GPP access to SNPNs” related to KI#2
  2 solutions updated; the TR includes still 47 solutions
  KI#2 conclusions updated, open issue dependent on SA3 agreed to be resolved during normative work based on SA3 feedback
  KI#3-6 evaluations updated, and conclusions agreed, one open issues remains for KI#4
  TR sent for information the second time due to one remaining open issue, normative WID updated as per TR conclusions
  RAN impacts and dependencies:
  No new RAN impact identified (key issues 1, 2 have RAN impact)
  SA3 study FS_eNPN_Ph2_SEC, completion rate 60%
Next steps:
  Finalize the study (KI#4), if time given (estimated to 0.5 TU), and finalize normative work (estimated to require 1.5 TUs excluding KI#4 open issue)
Progress of eNPN_Ph2:
  2 CRs approved related to KI#1 (whereas 1 CR updated at SA2#154)
  5 CRs approved related to KI#2 (whereas 4 CRs updated at SA2#154)
  1 question/LS related to SNPN access mode for non-3GPP access (KI#2) sent to CT1 that may impact approved CRs related to KI#2
  1 question/LS related to LI requirements applicable to non-3GPP access to SNPNs sent to SA3-LI that may impact CR related to KI#2
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNPN_Ph2 | Enhanced support of Non-Public Networks | 75% > 98% | Dec, 22 | SP-211656
eNPN_Ph2 | Enhanced support of Non-Public Networks | 0% > 50% | Mar, 23 | SP-220805
TO BE UPDATED AFTER SA2#155