## Slide 1: FS_REDCAP_Ph2, NR_REDCAP_Ph2 Status Report
Qian Chen
Ericsson

## Slide 2: FS_REDCAP_Ph2, NR_REDCAP_Ph2 status after SA2#154AHE (1/2)
  General:
  Total 4 papers are agreed, including:
    3 normative CRs (S2-2301859/S2-2301477/S2-2301448)
    1 LS (S2-2301858) to RAN3/RAN2 for further question related to RAN reply LS
  Total TUs planed for normative work is 1 TU. And it is used up
  Additional 0.25TU (TBC) for April meeting and probably some additional TU in May meeting to handle responses from RAN WGs if responses are delayed from April meeting (RAN WGs will start normative work on Rel-17 RedCap from April meeting).
  RAN impacts and dependencies:
  Further response from RAN WGs is needed (Not able to receive RAN WGs response in time due to 0.5 TU is moved from SA2#155 to SA2#154AHE)
  Contentious Issue:
  None
WI Code | Work Item Title | WP | Target Date | WID#
FS_REDCAP_Ph2 | Study on RedCap phase 2 | 98% -> 100 % | September, 22 | SP-220074
NR_REDCAP_Ph2 | 5GS support of NR RedCap UE with long eDRX for RRC_INACTIVE State | 60%->95% | March, 23 | SP-220803

## Slide 3: FS_REDCAP_Ph2, NR_REDCAP_Ph2 status after SA2#154AHE (2/2)
Focus for the Next Meeting (SA2#156E):
  Continue to work on remaining issues (e.g. as indicated in the ENs), considering the responses from RAN WGs
  Details of the AMF support handling.
Overall Plan:
  100% progress on the study.
    SA2#149E Feb(0.5 TU): TR skeleton; Agreement on scope, architecture assumptions and requirements, key issues; solution proposals
    SA2#150E Apr(0.5 TU): Solution proposals/updates; initial evaluation
    SA2#151E May(0.5 TU): Evaluations; solution update; initial conclusion; TR for information
    SA2#152E Aug(0.5 TU): Evaluations; conclusions; WID approval; TR for approval
  95% progress on the normative work.
    SA2#153E Oct(0.5 TU): Start of the normative work
    SA2#155 Feb (0.5 TU): Solving remaining issues -> changed to SA2#154AHE Jan (0.5 TU)
    SA2#156 Apr (0.25 TU (TBC)): solving remaining issues, e.g. including ones related to RAN WGs responses
    SA2#157 May (TBC): solving remaining issues related to RAN WGs responses if it’s delayed from Apr meeting