## Slide 1: TEI18_SLAMUP Status Report
Uri Baniel Oracle (Rapporteur)

## Slide 2: TEI18_SLAMUP status after SA2 #154AH-e
Progress since SA2#154AHe:
  Total TUs requested for Normative Phase is 1 TUs, 0.5 TU remaining (we don’t intend to use the remaining 0.5 TU).
  4 CRs and 1 LS OUT were submitted to SA2#154AHEe meeting corresponding to draft-CRs, DP and approved WID from SA2#152-e.
  1 CR for TS 23.501, 2 CRs for TS 23.502, 1 CR for TS 23.503 and 1 LS OUT were approved.
Next steps:
  SA2#156-E meeting, April 2023
    Bring alignment CRs (to replace 3 ENs in 23.503 and 2 ENs in 23.501 with normative Text/tables) based on the SA5 response for our LS OUT.
    (Note: SA5 next meeting is expected to take place between Feb/27/2023 to Mar/3/2023)
WI Code | Work Item Title | WP | Target Date | WID#
TEI18_SLAMUP | Spending Limits for AM and UE Policies in the 5GC | 80% | April, 2023 | S2-2207832

## Slide 3: TEI18_SLAMUP Work Plan
Contentious Issue:
  N/A
Focus for the Next->Next Meeting (SA2#156-E):
  Total TU allocated for SLAMUP in SA2#156 meeting is 0 TU.
  Bring alignment CRs.
Overall Plan:
  SA2#151-E: initial DP and WID.
  SA2#152-E: DP and WID re-submitted along with 4 draft CRs.
  SA2#153 No SLAMUP work.
  SA2#154AH-E: Normative work - done.
  SA2#155 No SLAMUP work.
  SA2#156-E: Alignment CRs.
Risks: We depend on:
  1. Receiving an LS response from SA5 prior to SA2 #156-E.
  2. Having our Alignment CRs being handled in SA2 #156-E.
 |  |  | May, 22 | Aug, 22 | Jan, 23 | April, 23 | 
WID | Normative TU | Total TU | #151-E | #152-E | #154AH-E | #156-E | Total TU
SLAMUP | 0.5 | 0.5 | 0 | 0 | 0.5 | 0 | 0.5