## Slide 1: FS_EDGE_Ph2 status report EDGE_Ph2 status report
Patrice Hédé
Huawei Technologies

## Slide 2: FS EDGE Ph2 status after SA2#154
  Progress since SA2#153-e:
  Total TUs requested for Study phase in 2022 is 7,25, all TUs have now been used.
  3 contributions approved:
    1 editorial clean-up contribution
    1 conclusion (KI#6) and 1 conclusion update (KI#1)
  All KIs are now concluded:
    5 KIs are proceeding to normative phase
    1 KI will be handled as part of XRM WI (KI#2)
    1 KI will not proceed to normative phase (KI#6)
  RAN impacts and dependencies:
  None
Next steps:
  Study is now completed.
  TR is sent for approval to SA plenary.
WI Code | Work Item Title | WP | Target Date | WID#
FS_EDGE_Ph2 | Study on Edge Computing Phase 2 | 97% → 100% | Dec 2022 | SP-220352

## Slide 3: EDGE Ph2 status after SA2#154
  Progress since SA2#153-e:
  This is the first meeting for the Work Item.
  Total TUs for the work item: 4,25 TUs. 0,75 TUs used in SA2#154. Remaining TUs: 3,5 TUs.
  3 objectives have been discussed in this meeting, with 8 CRs approved:
    KI#1: 2 CRs
    KI#3: all CRs were postponed
    KI#4: 6 CRs
  RAN impacts and dependencies:
  None
Next steps:
  Continue the discussion and contributions on all objectives.
WI Code | Work Item Title | WP | Target Date | WID#
EDGE_Ph2 | Edge Computing Phase 2 | 0% → 15% | Mar 2023 | SP-220987 → S2-2209986

## Slide 4: FS EDGE Ph2 status at SA#98
  Progress since SA#97-e:
  Total TUs requested for Study phase in 2022 is 7,25, all TUs have now been used.
  All KIs are now concluded:
    5 KIs are proceeding to normative phase
    1 KI will be handled as part of XRM WI (KI#2)
    1 KI will not proceed to normative phase (KI#6)
  RAN impacts and dependencies:
  None
Next steps:
  Study is now completed.
  TR is sent for approval to SA plenary.
WI Code | Work Item Title | WP | Target Date | WID#
FS_EDGE_Ph2 | Study on Edge Computing Phase 2 | 83% → 100% | Dec 2022 | SP-220352

## Slide 5: EDGE Ph2 status at SA#98
  Progress since SA#97:
  This is the first quarter for the Work Item.
  The work item has been updated to include all objectives based on the conclusions of TR 23.700-48.
  Total TUs for the work item: 4,25 TUs. 0,75 TUs used in Q4-2022. Remaining TUs: 3,5 TUs.
  3 objectives have been discussed in this meeting, with 8 CRs approved:
    KI#1: 2 CRs
    KI#3: all CRs were postponed
    KI#4: 6 CRs
  RAN impacts and dependencies:
  None
Next steps:
  Complete the discussion and contributions on all objectives.
WI Code | Work Item Title | WP | Target Date | WID#
EDGE_Ph2 | Edge Computing Phase 2 | 0% → 15% | Mar 2023 | SP-220987 → S2-2209986

## Slide 6: EDGE Ph2 status after SA2#154 — work plan
Study phase
  SA2#149e, Feb (1TU): Agreement on scenarios/use cases and assumptions for all KIs
  SA2#150e, Apr (1TU): Updates to KI definition. Solutions
  SA2#151e, May (2TU): Solutions
  SA2#152e, Aug (2TU): Solutions, evaluations, conclusions
    Approval of first version of Edge ph2 WID based on first conclusions, TR sent for information
  SA2#153e, Oct (1TU): evaluations, conclusions
    Completion of conclusions, Edge ph2 WID based on remaining conclusions
  SA2#154, Nov (0,25 TU): final conclusions
    TR sent for approval, Edge ph2 WID based on final conclusions if needed
Normative phase
  SA2#154, Nov (0,75 TU): Initiate discussion on most KIs.
    First CRs discussed and approved
  SA2#155-ah, Jan (1,5 TU): Progress discussion on all KIs in the WID
    Further CRs approved, hopefully some KIs concluded (e.g. KI#3/5/7)
  SA2#155, Feb (2 TU): Completion of normative work
    Remaining CRs to be approved, main normative work completed
 |  |  |  | Feb. 22 | Apr. 22 | May 22 | Aug. 22 | Oct. 22 | Nov. 22 | Jan. 23 | Feb. 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_EDGE_Ph2 | 7,25 | 4,25 | 11,5 | 1 | 1 | 2 | 2 | 1 | 0,25/0,75 | 1,5 | 2 | 11,5