## Slide 1: FS_eUEPO Status Report
Intel (Rapporteur)

## Slide 2: FS_eUEPO status after SA#96
WI Code | Work Item Title | WP | Target Date | WID#
FS_eUEPO | Study on enhancement of 5G UE Policy | 80% -> 95% | Mar. 2023 | SP-220416
General
  The latest TR 23.700-85 v1.1.0 generated by incorporating approved contributions at SA2 #153E and sent to SA for further information.
  WID is updated based on the TR conclusion.
  28 papers were submitted including 4 LS OUT, 12 papers were approved, 0 papers were not handled at SA2#153E, no TU was allocated at SA2#154.
Contentious Issue:
  KI #1 conclusion on how to provide VPLMN ID to UE along URSP.
  KI #2 conclusion on solution based on UE reporting assistance information during PDU Session Establishment/Modification to 5GC.
  KI #3 conclusion on whether URSP mapping in EPS requires dynamic configuration mechanism and how to handle the EPS mobility for a UE that is dual registered (i.e. with a registration in 5GS via N3IWF and attached to EPC/E-UTRAN).
RAN impacts and dependencies:
  No.
Next steps:
  Resolve ENs for conclusion of KI #1, #2 and #3 at January SA2#155-AH meeting by borrowing 0.2 TU from normative phase.
  Complete normative work in Q1’23.

## Slide 3: FS_eUEPO status at SA2#153E
WI Code | Work Item Title | WP | Target Date | WID#
FS_eUEPO | Study on enhancement of 5G UE Policy | 80% -> 95% | Mar. 2022 | SP-220416
General
  The latest TR 23.700-85 v1.1.0 is generated by incorporating approved contributions at SA2 #153E. TR approval was postponed.
  Total TUs requested for Study Phase is 4.25 TUs, and 0 TUs are left.
  KI#4 are completely concluded, KI#1, #2 and #3 are concluded with some ENs.
  28 papers were submitted including 4 LS OUT, 12 papers were approved, 0 papers were not handled.
KI#1(URSP in VPLMN):
  1 existing solution is updated, 4 evaluation and conclusion papers are approved.
KI#2(5GC awareness of URSP enforcement):
  1 existing solution is updated, 1 conclusion paper was approved, 1 LS to SA3 is approved.
KI#3(Provision consistent URSP to UE across 5GS and EPS):
  1 evaluation and conclusion paper resolving the EN is approved.
KI#4(Support standardized and operator-specific traffic categories in URSP):
  1 evaluation and conclusion update paper is approved, 1 LS to GSMA and 1 LS to CT1 are approved.

## Slide 4: FS_eUEPO status at SA2#153E (2/2)
Contentious Issue:
  KI #1 conclusion on how to provide VPLMN ID to UE along URSP.
  KI #2 conclusion on solution based on UE reporting assistance information during PDU Session Establishment/Modification to 5GC.
  KI #3 conclusion on whether URSP mapping in EPS requires dynamic configuration mechanism and how to handle the EPS mobility for a UE that is dual registered (i.e. with a registration in 5GS via N3IWF and attached to EPC/E-UTRAN).

## Slide 5: FS_eUEPO status at SA2#154
WI Code | Work Item Title | WP | Target Date | WID#
FS_eUEPO | Study on enhancement of 5G UE Policy | 95% -> 95% | Mar. 2022 | SP-220416
General
  The latest TR 23.700-85 v1.1.0 is generated by incorporating approved contributions at SA2 #153E. TR approval is postponed to SA2#155-AH.
  No TU is allocated at this meeting.
  WID is updated based on the latest TR conclusion at SA2#153E.
  TR coversheet is approved for further information to SA Plenary.

## Slide 6: Rel-18 FS_eUEPO Overall Work Plan
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
  Overall Work Plan
  SA2#149e, 0.5 TU assigned, 15 documents in maximum:
    TR Skeleton, TR Scope, Architectural Assumption, Key Issues.
  SA2#150e, 1 TU assigned, 30 documents in maximum:
    Key issue update and new solutions. Last e-meeting for new Key Issue.
  SA2#151e, 1 TU assigned, 30 documents in maximum:
    Stabilize solution. Last e-meeting for new solution. Potential TR for information.
  SA2#152(e), 1 TU assigned, 30 documents in maximum:
    Stabilize solution and conclusion, TR for information and potential TR for approval, potential WID discussion and approval.
  SA2#153(e), 0.75 TU assigned, 23 documents in maximum:
    Potential update on solution and conclusions, WID update.
  SA2#154, 0 TU assigned:
    WID update, TR for further information.
  SA2#155AH(e), 0.2 TU borrowed from normative phase, 6 documents for study phase in maximum; 0.55 TU assigned for normative phase, 17 CRs for normative phase in maximum:
    Resolve the ENs in the TR conclusion, update conclusions, WID update, TR for approval.
  SA2#155, 0.75 TU assigned for normative phase, 23 CRs for normative phase in maximum:
    Complete the normative work.
FS_eUEPO | 4.25 | 1.5 | 5.75 | 0.5 | 1 | 1 | 1 | 0.75 | 0 | 0.75 | 0.75 | 5.75