## Slide 1: Vehicle Mounted Relays (VMR) Status Reprot
Qualcomm Incorporated
S2-2305415

## Slide 2: FS_VMR status after SA2#156E (1/2)
General
  Normative Phase work progress to 80%.
  1 TU used for the E-meeting (processed 35 contributions, including documents transferred from eNPN_Ph2).
  1 TU planned for May (SA2#157) meeting.
  RAN impacts and dependencies:
  Waiting further response from RAN3 regarding NRPPa enhancements.
Other WG dependencies
  Waiting SA5 resposne regarding access to VPLMN OAM server by a MBSR.
WID was updated in SA#99 (SP-230105) with the target dates
Normative work progress:
  8 CR approved.
  1 SoH regarding location restriction for CAG, and agreed to remove the feature from Rel-18 (reflected in S2-2305632).
WI Code | Work Item Title | WP | Target Date | WID#
FS_VMR | Study on Vehicle Mounted Relays | 100% | Nov, 22 | SP-211636
VMR | Architecture Enhancements for Vehicle Mounted Relays | 40% > 80% | Jun, 23 | SP-230105

## Slide 3: FS_VMR status after SA2#156E (2/2)
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | Apr, 23 | May, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | #156 | #157 | Total TU used
FS_VMR/ VMR | 3.75 | 2.75 | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2 (1.25+0.75) | 0.5 | 0 | 1.0 | 1.0 | 7.0
Contentious Issue:
  MBSR node authorization and deauthorization handling.
Focus of the May Meeting (SA2#157):
  Resolve MBSR node authorization/deauthorization (incl. NAS indication, UCU support)
  Resolve details on “Additional ULI” support in 5GC
  Resolve open issues regarding NRPPa enhancement for LCS support via MBSR
  Close all open ENs
Overall work Plan:
  SA2#149 Feb’22: 0.5 (TR skeleton, arch assumptions, KIs)
  SA2#150 Apr’22: 0.5 (New KIs; solutions)
  SA2#151 May’22: 0.5 (Last chance for KIs; last chance for new solutions; solution updates)
  SA2#152 Aug’22: 0.5 (Solution updates; evaluations; Interim conclusions, send TR to RAN for comments)
  SA2#153 Oct’22: 0.5 (Finalize conclusions; WID approval)
  SA2#154 Nov’22: 1.25 (Resolve RAN dependent open issues for selected solutions); start normative work 0.75.
  SA2#154AH-E Jan’23: 0.5 (Normative work)
  SA2#155 Feb’23: 0
  SA2#156E Apr’23: 1.0 (Normative work)
  SA2#157 May’23: 1.0 (Normative work) – additional 0.5 TU requested.

## Slide 4: FS_VMR status at SA#100
Progress since SA#99:
  Normative Phase work progress to 80%.
  8 CRs approved, 1 SoH with agreed WF w.r.t. CAG.
  1.0 TU remaining for the WID in SA2#157.
RAN impacts and dependencies:
  Pending response from RAN2/3.
Next steps:
  Normative work based on approved WID.
WI Code | Work Item Title | WP | Target Date | WID#
FS_VMR | Study on Vehicle Mounted Relays | 100% | Nov, 22 | SP-211636
VMR | Architecture Enhancements for Vehicle Mounted Relays | 40% > 80% | Jun, 23 | SP-230105