## Slide 1: FS_eUEPO/eUEPO Status Report
Intel (Rapporteur)

## Slide 2: eUEPO status at SA2#156E
WI Code | Work Item Title | WP | Target Date | WID#
eUEPO | enhancement of 5G UE Policy | 65% -> 90% | June 2023 | SP-221127
General
  At SA2#156AHE, 48 papers were submitted for normative work, 17 CRs were approved, 15 papers were not handled.
KI#1(URSP in VPLMN):
  8 CRs were approved.
KI#2(5GC awareness of URSP enforcement):
  4 CRs were approved.
KI#3(Provision consistent URSP to UE across 5GS and EPS):
  5 CRs were approved.
KI#4(Support standardized and operator-specific traffic categories in URSP):
  No CR was approved.
Contentious issue:
  None.

## Slide 3: Rel-18 eUEPO Overall Work Plan
 |  |  |  | Jan, 23 | Feb, 23 | Apr, 23 | May, 23 |  |  |  |  | 
SID/WID | Study TU | Normative TU | Total TU | #154AHE | #155 | #156E | #157 |  |  |  |  | Total TU
  Overall Work Plan
  SA2#155AH(e), 0.75 TU was assigned for both study and normative phases:
    Resolve the ENs in the TR conclusion, update conclusions, progress the normative work.
  SA2#155, 1 TU assigned for normative phase, 30 CRs for normative phase in maximum:
    Progress the normative work. WID update, TR for approval.
  SA2#156E, 1 TU assigned for normative phase, 30 CRs for normative phase in maximum:
    Progress the normative work.
  SA2#157, 1 TU assigned for normative phase:
    Complete the normative work.
eUEPO | 4.25 | 2.75 | 7 | 0.75 | 1 | 1 | 1 |  |  |  |  | 8