## Slide 1: NG_RTC Status Report
Yi Jiang (Rapporteur)
China Mobile

## Slide 2: FS_NG_RTC/NG_RTC work plan updates
  The TUs has been adjusted according to the delay of TR conclusion
    The total TU is currently increased from 6 to 8.5
    5 TU has been used to conclude the study, 2.5 TU has been used for normative phase
    1 TU at #157 is the last chance for completing normative work
  The work plan is updated according to the progress at #154AHE and #155:
  #154AH meeting: conclude TR; start normative work
  #155 to #156 meetings: continue normative work
  #157 meeting: complete normative work
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | Apr, 23 | May, 23
 |  |  |  | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | #156E | #157
SID/WID | Study Phase TU | Normative TU | Total TU |  |  |  |  |  |  |  |  |  | 
FS_NG_RTC/NG_RTC | 5 | 2.5 | 7.5 | 1 | 1 | 1 | 1 | 0.5 | 0 | 1 | 1 | 1 | 1

## Slide 3: NG_RTC status after SA2#156E
General
  39 contributions were submitted to #156E and 31 contributions (including a LS) were handled
  Achievements:
    Editor’s notes on service profile, interface for repository data retrieval, trigger of including DC SDP, stream ID and P2P media specification was resolved
    DC procedures were updated
    Registration and discovery of DCMF and enhanced MRF were agreed, with which KI#4 was completed
    Architecture and procedure for UE rendering AR communication were agreed
  Remaining issues
    How to extend IMS DC architecture to converge DCMF and ARMF needs further discussion
    DCMF service enhancements for supporting ARMF needs further discussion
    Roaming support is not handled in this meeting due to TU limitation
  RAN impacts and dependencies:
  None
Next steps:
  complete normative work on KI#1 and KI#2
  Synchronize with SA4 outcome
WI Code | Work Item Title | WP | Target Date | WID#
NG_RTC | System architecture for next generation real time communication services | 60%->85% | June, 2023 | 970014