## Slide 1: Vehicle Mounted Relays (VMR) Status Report
Qualcomm Incorporated
S2-2307438

## Slide 2: VMR status after SA2#157 (1/2)
General
  Normative Phase work progress to 100%.
  1 TU used for the Apr E-meeting (SA2#156E).
  1 TU used for May F2F meeting (SA2#157).
  RAN impacts and dependencies:
  Waiting further response from RAN3 regarding NRPPa enhancements and TAC managements.
  1 new LS to RAN3 regarding IAB-node deauthorization handling (S2-2308158)
Other WG dependencies
  None.
Normative work progress:
  12 CR approved.
  1 SoH regarding location restriction for CAG, and agreed to remove the feature from Rel-18 (reflected in S2-2305632).
WI Code | Work Item Title | WP | Target Date | WID#
FS_VMR | Study on Vehicle Mounted Relays | 100% | Nov, 22 | SP-211636
VMR | Architecture Enhancements for Vehicle Mounted Relays | 40% > 100% | Jun, 23 | SP-230105

## Slide 3: VMR status after SA2#157 (2/2)
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | Apr, 23 | May, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | #156 | #157 | Total TU used
FS_VMR/ VMR | 3.75 | 2.75 | 5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 2 (1.25+0.75) | 0.5 | 0 | 1.0 | 1.0 | 7.0
Contentious Issue:
  None.
Focus of the Aug Meeting (SA2#158):
  Resolve further details on the “Additional ULI” handling at 5GC.
  Handle incoming LS from RAN WGs.
Overall work Plan:
  SA2#149 Feb’22: 0.5 (TR skeleton, arch assumptions, KIs)
  SA2#150 Apr’22: 0.5 (New KIs; solutions)
  SA2#151 May’22: 0.5 (Last chance for KIs; last chance for new solutions; solution updates)
  SA2#152 Aug’22: 0.5 (Solution updates; evaluations; Interim conclusions, send TR to RAN for comments)
  SA2#153 Oct’22: 0.5 (Finalize conclusions; WID approval)
  SA2#154 Nov’22: 1.25 (Resolve RAN dependent open issues for selected solutions); start normative work 0.75.
  SA2#154AH-E Jan’23: 0.5 (Normative work)
  SA2#155 Feb’23: 0
  SA2#156E Apr’23: 1.0 (Normative work)
  SA2#157 May’23: 1.0 (Normative work) – additional 0.5 TU requested.

## Slide 4: VMR status at SA#100
Progress since SA#99:
  Normative Phase work progress to 100%.
  12 CRs approved, 1 SoH with agreed WF w.r.t. CAG location restriction.
RAN impacts and dependencies:
  1 new LS (S2-2308158) to RAN3 on IAB-node deauthorization handling
  Pending response from RAN2/3.
Next steps:
  Maintenance based on inputs from other WGs.
WI Code | Work Item Title | WP | Target Date | WID#
FS_VMR | Study on Vehicle Mounted Relays | 100% | Nov, 22 | SP-211636
VMR | Architecture Enhancements for Vehicle Mounted Relays | 40% > 100% | Jun, 23 | SP-230105