## Slide 1: SA2 Work Planning
Andy Bennett
SA2 Chair
SA WG2 Meeting #159 S2-2311663
October 09 – 13, 2023

## Slide 2: Contents
Release timeline
Meeting dates – summary
SA2#160 Meeting dates and agenda
SA2 ad hoc Meeting dates and agenda
SA2#161 Meeting dates and agenda
Overall planning for Rel-19

## Slide 3: Rel-19 timelines
TSG#101
Note: All starting dates are indicative
TSG#102
TSG#103
TSG#104
TSG#105
TSG#106
TSG#107
TSG#108
TSG#109
TSG#110
TSG#111
TSG#112
TSG#99
RAN4
content def.
RAN Content def.
2024
2025
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
2026
RAN Rel-19 workshop
RAN4_Perf
Stage 3 (CT & SA)
RAN1
Stage 2 (SA2, SA6,…)
RAN Completion (RAN2/3/4core)
ASN.1 & Open APIs
St.2 Content approval
SA Rel-19
Workshop
TSG#100
June
2023
100%
SA1 Stage 1 80%
SP-230390 - 3GPP TSG#99, 20 -24 March 2023, Rotterdam, The Netherlands

## Slide 4: SA2 meeting dates for 2023 & 2024
SA2#158 | Monday, August 21, 2023 | Friday, August 25, 2023 | Goteborg, SE
SA2#159 | Monday, October 9, 2023 | Friday, October 13, 2023 | Xiamen, CN
SA2#160 | Monday, November 13, 2023 | Friday, November 17, 2023 | Chicago, US
SA2-Ad Hoc | Monday, January 22, 2024 | Friday, January 26, 2024 | Electronic
SA2#161 | Monday, February 26, 2024 | Friday, March 1, 2024 | EU, EU
SA2#162 | Monday, April 15, 2024 | Friday, April 19, 2024 | CN (TBC)
SA2#163 | Monday, May 27, 2024 | Friday, May 31, 2024 | Korea, KR
SA2#164 | Monday, August 19, 2024 | Friday, August 23, 2024 | EU, EU
SA2#165 | Monday, October 14, 2024 | Friday, October 18, 2024 | India, IN
SA2#166 | Monday, November 18, 2024 | Friday, November 22, 2024 | US (TBC)

## Slide 5
SA2#160 Dates/Agenda
SA2#160 will be a F2F ordinary meeting
Preliminary Agenda (subjected to changes):
  AI 4.1: Incoming LSs on all agenda items
  AI 4.2: inclusive language for 2G/3G specs
  AI 5.X, 6.X, 7.X
  AI 8.X: Rel-17 Maintenance (CRs only if there any incoming LS)
  AI 9.X: Rel-18 Maintenance
  AI 19.X: Rel-19 approved study/work items
  AI 30.X: Rel-19 WID/SID proposals
  Email Approval may be scheduled immediately after the meeting, only if it becomes really necessary. Further details on email approval such as TDoc list, date/timings will be decided during the meeting.
Doc request deadline | Friday 3 November 2023 |  | 2359 UTC
Doc submission deadline | Friday 3 November 2023 |  | 2359 UTC
Registration | Monday 6 November 2023 |  | 0800 UTC
Start of meeting | Monday 13 November 2023 | 0900 Local time | 1500 UTC
Close of meeting | Friday 17 November 2023 | 1630 Local time (or earlier) | 2200 UTC
Upload approved documents | Friday 17 November 2023 | 1700 Local time | 2300 UTC

## Slide 6
SA2 ad hoc January Dates/Agenda
SA2 January meeting will be ad hoc Electronic
Preliminary Agenda (subjected to changes):
  AI 4.1: Incoming LSs on all agenda items
  AI 4.2: inclusive language for 2G/3G specs
  AI 5.X, 6.X, 7.X (LS only)
  AI 8.X: Rel-17 Maintenance (LS only)
  AI 9.X: Rel-18 Maintenance
  AI 19.X: Rel-19 approved study items
  AI 30.X: Rel-19 TEI-19 proposals
Doc request deadline | Friday 12 January 2024 |  | 2359 UTC
Doc submission deadline | Friday 12 January 2024 |  | 2359 UTC
Registration | Monday 15 January 2024 |  | 0000 UTC
Start of meeting | Monday 22 January 2024 |  | 0000 UTC
Close of meeting | Monday 29 January 2024 |  | 1600 UTC
Upload approved documents | Tuesday 30 January 2024 |  | 1600 UTC
Close the meeting on Monday 29th instead of Friday 26th to allow the comments deadline to be on Thursday 25th instead of Wednesday 24th.
Need to apply quotas for input documents on all agenda items. TU enforcement quotas 30 tdocs per TU for studies. What to schedule for Rel-18 maintenance and how to limit tdocs will be discussed in November)

## Slide 7
SA2#161 Dates/Agenda
SA2#161 will be a F2F ordinary meeting
Preliminary Agenda (subjected to changes):
  AI 4.1: Incoming LSs on all agenda items
  AI 4.2: inclusive language for 2G/3G specs
  AI 5.X, 6.X, 7.X
  AI 8.X: Rel-17 Maintenance
  AI 9.X: Rel-18 Maintenance
  AI 19.X: Rel-19 approved study/work items
  AI 30.X: Rel-19 TEI-19 proposals
  Email Approval may be scheduled immediately after the meeting, only if it becomes really necessary. Further details on email approval such as TDoc list, date/timings will be decided during the meeting.
Doc request deadline | Friday 16 February 2024 |  | 2359 UTC
Doc submission deadline | Friday 16 February 2024 |  | 2359 UTC
Registration | Monday 19 February 2024 |  | 0800 UTC
Start of meeting | Monday 26 February 2024 | 0900 Local time | 1500 UTC
Close of meeting | Friday 1 March 2024 | 1630 Local time (or earlier) | 2200 UTC
Upload approved documents | Friday 1 March 2024 | 1700 Local time | 2300 UTC

## Slide 8: Rel-19 planning for SA2
Final package for SA2 planned to be approved in December (SA#102)
The Rel-19 studies should complete no later than SA2#163 (May 2024)
  In general it is not expected that study work on any KI’s will continue beyond this date
  WIDs based on the outcomes of the studies to be agreed by SA2 in SA2#163 and submitted to SA#104 (June 2024)
  [Study-only items are not limited to this plan]
Normative work on these studies can start in SA2#164 (August 2024)
Normative work shall complete no later than SA2#166 (November 2024)
Discussion of TEI-19 items can start from January 2024
  Submission and discussion/endorsement of candidates in the January Ad Hoc
  Submission and discussion/agreement of candidates in SA2#161 (February 2024)
    Candidates will only be agreed in the second meeting
  Decision on which TEI-19 items will be agreed will be in SA2#161 (February 2024)
  Work can start on TEI-19 items in SA2#162 (April 2024)
Discussion points:
Allocate 10 TU’s to TEI-19 items?
Expectation is that TEI-19 items are typically 1 TU, and no larger than 2 TU’s