## Slide 1: WI and SID Status Report on Phase 2 for UAS, UAV and UAM (FS_UAS_Ph2 and UAS_Ph2)
Qualcomm Incorporated

## Slide 2: FS_UAS_Ph2 and UAS_Ph2 status after SA2#159 (1/2)
Normative work completed
General
  Few corrections were approved to correct the A2X features, align to stage 3, and clarify some of the mechanisms modified in previous mechanisms. New PQIs for A2X were introduced and an LS sent to RAN2
Next steps:
  Continue corrections as necessary, none expected
WI Code | Work Item Title | WP | Target Date | WID#
FS_UAS_Ph2 | Study on Phase 2 of UAS, UAV and UAM | 98% > 100% | Dec, 22 | SP-211636
UAS_Ph2 | Phase 2 of UAS, UAV and UAM | 85% > 100% | Jun, 23 | SP-221323

## Slide 3: FS_UAS_Ph2 and UAS_Ph2 status after SA2#159 (2/2)
  RAN and SA3 impacts and dependencies:
  None
Contentious Issue:
  None
Focus for the Next Meeting :
  Continue correction work.
Overall Plan:
  2024 Q2: progress correction work

## Slide 4: Appendix

## Slide 5: FS_UAS_Ph2 and UAS_Ph2 status after SA2#159 (1/2)
Normative work completed
General
  SA2 replied the SA3 LS on the relationship between UUAA-MM and UUAA-SM, indicating that SA2 specifications are correct and SA3 ones need to be aligned to SA2
  Based on CRs submitted, SA2 sent an LS to SA3 in S2-2309698 asking to verify if there are any reasons to adopt additional location mechanisms for reliable location
Next steps:
  Continue corrections as necessary, none expected
WI Code | Work Item Title | WP | Target Date | WID#
FS_UAS_Ph2 | Study on Phase 2 of UAS, UAV and UAM | 98% > 100% | Dec, 22 | SP-211636
UAS_Ph2 | Phase 2 of UAS, UAV and UAM | 85% > 100% | Jun, 23 | SP-221323

## Slide 6: FS_UAS_Ph2 and UAS_Ph2 status after SA2#159 (2/2)
  RAN and SA3 impacts and dependencies:
  None
Contentious Issue:
  None
Focus for the Next Meeting :
  Continue correction work.
Overall Plan:
  2024 Q2: progress correction work

## Slide 7: FS_UAS_Ph2 and UAS_Ph2 status after SA2#157 (1/2)
Normative work completed
General
  5 CRs to TS 23.256 were agreed
    Correction to Abbreviation for A2X and A2X definition
    N2 and Xn based HO for UAV
    Restructuring to clarify A2X Service
    Clarification of support of A2X capability of UAV UE
    Direct C2 authorization exceptions
  1 CR to TS 23.503 was agreed
    Provisioning of A2X policy to UE
  An LS on to RAN2 on BRID and DAA broadcast over LTE and NR PC5 was agreed
    Indication to RAN2 that their work supports existing SA2 specifications
    Indication that dedicated resources (PQI) for BRID and DAA are preferable and SA2 will align after SA2 decision
Next steps:
  N/A
WI Code | Work Item Title | WP | Target Date | WID#
FS_UAS_Ph2 | Study on Phase 2 of UAS, UAV and UAM | 98% > 100% | Dec, 22 | SP-211636
UAS_Ph2 | Phase 2 of UAS, UAV and UAM | 85% > 100% | Jun, 23 | SP-221323

## Slide 8: FS_UAS_Ph2 and UAS_Ph2 status after SA2#155 (1/2)
General
  An LS reply was sent to ETSI TFES on Release 17 supporting most requirements sets forward by ETSI TFES
  5 CRs to TS 23.256 were agreed
    Clarifications and additional details on architectural aspects for the use of PC5 for A2X (aircraft-to-anything)
    Additional details on PC5-based command and control
  2 CRs to TS 23.502 were agreed
    A2X subscription data in UDM and UDR
    PCF A2X capability indication during NF registration and discovery to NRF
  An LS on RAN dependency for UAS sent to RAN2 and RAN3
Next steps:
  continue normative work at next meeting.
WI Code | Work Item Title | WP | Target Date | WID#
FS_UAS_Ph2 | Study on Phase 2 of UAS, UAV and UAM | 98% > 100% | Dec, 22 | SP-211636
UAS_Ph2 | Phase 2 of UAS, UAV and UAM | 25% > 85% | Jun, 23 | SP-221323

## Slide 9: FS_UAS_Ph2 and UAS_Ph2 status after SA2#155 (2/2)
  RAN and SA3 impacts and dependencies:
  None determined yet for SA3
  Results of study to impact RAN decision to progress work on PC5.
Contentious Issue:
  None
Focus for the Next Meeting :
  Continue normative work.
  Capture the MBS-based solution for BRID by referring to V2X MBS solutions (from TEI 18 MBS4V2X), e.g. identifying the difference.
Overall Plan:
  2023 Q2: progress normative work

## Slide 10: FS_UAS_Ph2 and UAS_Ph2 status after SA2#154AHE (1/2)
General
  2 CRs agreed for TR 23.700-58 to address the outstanding issues:
    Use of PC5-U for payload data instead of PC5-S
    Resolution of RAN dependent aspects and editor’s notes
  An LS was sent to RAN2 in S2-2301854 on DAA based on PC5
  5 CRs to TS 23.256 were agreed
    Architectural aspects for the use of PC5 for A2X (aircraft-to-anything)
    A2X for BRID
    A2X for DAA
    PC5-based command and control
    Ground-based DAA for an area
Next steps:
  continue normative work at SA2#155.
WI Code | Work Item Title | WP | Target Date | WID#
FS_UAS_Ph2 | Study on Phase 2 of UAS, UAV and UAM | 98% > 100% | Dec, 22 | SP-211636
UAS_Ph2 | Phase 2 of UAS, UAV and UAM | 0% > 25% | Mar, 23 -> Jun 23 | SP-221323

## Slide 11: FS_UAS_Ph2 status after SA2#154AHE (2/2)
  RAN and SA3 impacts and dependencies:
  None determined yet for SA3
  Results of study to impact RAN decision to progress work on PC5.
Contentious Issue:
  How to capture the MBS-based solution for BRID, whether in TS 23.256 or as part of V2X MBS solutions
Focus for the Next Meeting (SA2#155 in Feb 2023):
  Continue normative work.
Overall Plan:
  2023 Q1: progress normative work

## Slide 12: FS_UAS_Ph2 status after SA2#154 (1/2)
General
  TR 23.700-58 v1.1.0 was created based on approved contributions.
  TR 23.700-58 v1.1.0 is being submitted for approval at SA#98e.
  WID approved at SA2#153e.
  No time slot at SA2#154 thus no further progress.
Next steps:
  Start normative work at SA2#154AH.
  Address existing Editor‘s Notes based on progress in RAN work and during normative phase.
WI Code | Work Item Title | WP | Target Date | WID#
FS_UAS_Ph2 | Study on Phase 2 of UAS, UAV and UAM | 98% | Sept, 22 | SP-211636

## Slide 13: FS_UAS_Ph2 status after SA2#154 (2/2)
  RAN and SA3 impacts and dependencies:
  None determined yet for SA3
  Results of study to impact RAN decision to progress work on PC5.
Contentious Issue:
  None left.
Focus for the Next Meeting (SA2#155e):
  Begin normative work.
Overall Plan:
  2023 Q1: progress normative work
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_UAS_Ph2 | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 0.5 | 1 | 0.75 | 0 | 1 | 1.25 | 5.5

## Slide 14: FS_UAS_Ph2 status after SA2#153E (1/2)
General
  TR 23.700-58 v.1.1.0 was created based on approved contributions.
  8 contributions agreed (no new solutions, no new key issues).
    Existing solutions were updated, ENs removed
    Conclusions for KI#1 were updated and finalized
    Conclusions for KI#2 and KI#3 were finalized
  0.75 TU left for the Study Phase.
  WID approved.
Next steps:
  TR sent to SA for Approval at SA2#154
  Start normative work at SA2#154AH
WI Code | Work Item Title | WP | Target Date | WID#
FS_UAS_Ph2 | Study on Phase 2 of UAS, UAV and UAM | 80% > 98% | Sept, 22 | SP-211636

## Slide 15: FS_UAS_Ph2 status after SA2#153E (2/2)
  RAN and SA3 impacts and dependencies:
  None determined yet for SA3
  Results of study to impact RAN decision to progress work on PC5.
Contentious Issue:
  None left.
Focus for the Next Meeting (SA2#154):
  TR sent to SA for Approval.
Overall Plan:
  2023 Q1: progress normative work
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_UAS_Ph2 | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 0.5 | 1 | 0.75 | 0 | 1 | 1.25 | 5.5

## Slide 16: FS_UAS_Ph2 status after SA2#152E (1/2)
General
  TR 23.700-58 v.0.4.0 was created based on approved contributions.
  8 contributions agreed (no new solutions, no new key issues).
    Existing solutions were updated, ENs removed
    Conclusions for KI#1 were captured
  1.5 TU used and 1.75 TU left for the Study Phase.
Next steps:
  Complete evaluations.
  Complete conclusions.
WI Code | Work Item Title | WP | Target Date | WID#
FS_UAS_Ph2 | Study on Phase 2 of UAS, UAV and UAM | 50% > 80% | Sept, 22 | SP-211636

## Slide 17: FS_UAS_Ph2 status after SA2#152E (2/2)
  RAN and SA3 impacts and dependencies:
  None determined yet for SA3
  Results of study to impact RAN decision to progress work on PC5.
Contentious Issue:
  Co-existence of PC5 and network based DAA solutions.
  Some technical details of network-based DAA solutions.
Focus for the Next Meeting (SA2#152e):
  Focus on evaluation and conclusions of KI#2 and KI#3.
Overall Plan: (study phase)
  SA2#151 May’22: 0.5 (new solutions; solution updates; start evaluation)
  SA2#152 Aug’22: 0.5 (solutions and solution updates; evaluations; interim conclusions; send TR to RAN for information)
  SA2#153 Oct’22: 0.5 (finalize TR conclusions; WID approval)
  SA2#154 Nov’22: 0.25 (start normative work)
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_UAS_Ph2 | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 0.5 | 1 | 0.75 | 0.5 | 1 | 0.75 | 5.5

## Slide 18: FS_UAS_Ph2 status after SA2#151E (1/2)
General
  TR 23.700-58 v.0.3.0 was created based on approved contributions.
  9 contributions agreed (2 new solutions, no new key issues).
  1.5 TU used and 1.75 TU left for the Study Phase.
3 Solutions agreed for the study:
  Sol. #1: C2 communication over PC5
  Sol. #2: Network assisted DAA
  Sol. #3: MBS-based UAV remote ID broadcast
  Sol. #4: Direct C2 communication over PC5
  Sol. #5: U2X for support of Broadcast Remote ID and Direct DAA via PC5
  Sol. #6: Handling C2 connection over PC5
  Sol. #7: Ground-based DAA for location such as Arena.
Next steps:
  Capture new solutions for all KIs, expand details on existing KI, start evaluations.
WI Code | Work Item Title | WP | Target Date | WID#
FS_UAS_Ph2 | Study on Phase 2 of UAS, UAV and UAM | 35% > 50% | Sept, 22 | SP-211636

## Slide 19: FS_UAS_Ph2 status after SA2#151E (2/2)
  RAN and SA3 impacts and dependencies:
  None determined yet for SA3
  Results of study to impact RAN decision to progress work on PC5.
Contentious Issue:
  None identified
Focus for the Next Meeting (SA2#152e):
  Focus on solutions (new and updated) and resolve the ENs in the Key Issues
Overall Plan: (study phase)
  SA2#151 May’22: 0.5 (new solutions; solution updates; start evaluation)
  SA2#152 Aug’22: 0.5 (solutions and solution updates; evaluations; interim conclusions; send TR to RAN for information)
  SA2#153 Oct’22: 0.5 (finalize TR conclusions; WID approval)
  SA2#154 Nov’22: 0.25 (start normative work)
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_UAS_Ph2 | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 0.5 | 1 | 0.75 | 0.5 | 1 | 0.75 | 5.5

## Slide 20: FS_UAS_Ph2 status after SA2#150E (1/2)
General
  TR 23.700-58 v.0.2.0 was created based on approved contributions.
  5 contributions agreed (5 new solutions, no new key issues).
  1 TU used and 2.25 TU left for the Study Phase.
3 Solutions agreed for the study:
  Sol. #1: C2 communication over PC5
  Sol. #2: Network assisted DAA
  Sol. #3: MBS-based UAV remote ID broadcast
  Sol. #4: Direct C2 communication over PC5
  Sol. #5: U2X for support of Broadcast Remote ID and Direct DAA via PC5
Next steps:
  Capture new solutions for all KIs, expand details on existing KI, start evaluations.
WI Code | Work Item Title | WP | Target Date | WID#
FS_UAS_Ph2 | Study on Phase 2 of UAS, UAV and UAM | 20% > 35% | Sept, 22 | SP-211636

## Slide 21: FS_UAS_Ph2 status after SA2#150E (2/2)
  RAN and SA3 impacts and dependencies:
  None determined yet for SA3
  Results of study to impact RAN decision to progress work on PC5.
Contentious Issue:
  None identified
Focus for the Next Meeting (SA2#151e):
  Focus on solutions (new and updated) and resolve the ENs in the Key Issues. LAST CHANCE FOR NEW SOLUTIONS
Overall Plan: (study phase)
  SA2#151 May’22: 0.5 (last chance for new solutions; solution updates; start evaluation)
  SA2#152 Aug’22: 0.5 (solutions updates; evaluations; interim conclusions; send TR to RAN for information)
  SA2#153 Oct’22: 0.5 (finalize TR conclusions; WID approval)
  SA2#154 Nov’22: 0.25 (start normative work)
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_UAS_Ph2 | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 0.5 | 1 | 0.75 | 0.5 | 1 | 0.75 | 5.5

## Slide 22: FS_UAS_Ph2 status after SA2#149E (1/2)
General
  TR 23.700-58 v.0.1.0 was created based on approved contributions.
  8 contributions agreed (including TR skeleton, scope, architecture assumptions and requirements, and key issues).
  0.5 TU used and 2.75 TU left for the Study Phase.
3 Key Issues agreed for the study:
  KI#1: Transport C2 communication over PC5 interface
  KI#2: Support of Broadcast Remote ID
  KI#3: Support of Detect and Avoid Mechanism in 3GPP system
Next steps:
  Capture new solutions for all KIs.
WI Code | Work Item Title | WP | Target Date | WID#
FS_UAS_Ph2 | Study on Phase 2 of UAS, UAV and UAM | 0% > 20% | Sept, 22 | SP-211636

## Slide 23: FS_UAS_Ph2 status after SA2#149E (2/2)
  RAN and SA3 impacts and dependencies:
  None determined yet for SA3
  Results of study to impact RAN decision to progress work on PC5.
Contentious Issue:
  None identified
Focus for the Next Meeting (SA2#150e):
  Focus on solutions (new and updated) and resolve the ENs in the Key Issues.
Overall Plan: (study phase)
  SA2#149 Feb’22: 0.5 (TR skeleton, arch assumptions, KIs)
  SA2#150 Apr’22: 0.5 (last chance for new KIs; solutions)
  SA2#151 May’22: 0.5 (last chance for new solutions; solution updates; start evaluation)
  SA2#152 Aug’22: 0.5 (solutions updates; evaluations; interim conclusions; send TR to RAN for information)
  SA2#153 Oct’22: 0.5 (finalize TR conclusions; WID approval)
  SA2#154 Nov’22: 0.25 (start normative work)
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
FS_UAS_Ph2 | 3.25 | 2.25 | 5.5 | 0.5 | 0.5 | 0.5 | 1 | 0.75 | 0.5 | 1 | 0.75 | 5.5