## Slide 1: FS_EnergySys Status Report
Jungshin Park
Samsung (Rapporteur)

## Slide 2: FS_EnergySys Status at SA#102
Progress since SA#101:
  TR 23.700-66 v0.2.0 is available
  Total 105 TDocs are submitted to SA2#159 and SA2#160
  7 pCRs have been agreed (15 pCRs merged, 1 pCR and 3DP noted, 1 LS postponed)
  TR skeleton, Definition, Scope, and Architecture Assumptions and Principles have been agreed
  Total 3 Key Issues to cover all three WTs in the SID have been agreed
  Solution discussion will start from the next SA2#160AH meeting
Impacts and dependencies on other WGs:
  None
  Contentious issues:
  None
Next steps:
  Start solution discussions for agreed Key Issues
  Continue discussion to refine Key Issues, Architectural Assumptions, Scope, etc.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010029 | Study on Energy Efficiency and Energy Saving | FS_EnergySys | 18/06/2024 | 0% | SP-231192 | 20% | Study in progress

## Slide 3: FS_EnergySys Status after SA2#160
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010029 | Study on Energy Efficiency and Energy Saving | FS_EnergySys | 18/06/2024 | 0% | SP-231192 | 20% | Study in progress
  General
  Discussion on new Key Issues has been continued from the last meeting
  Total 57 TDocs are submitted to SA#160, and 16 TDocs are handled
  Solution discussions are deferred to the next meeting
  Progress since SA2#159
  2 pCRs have been agreed for new Key Issues (related to Work Task #2 and #3)
  It is agreed to combine Work Task #3 related issues into a single Key Issue in the TR
  RAN impacts and dependencies
  None

## Slide 4: FS_EnergySys Status after SA2#160
  Other WG dependencies
  None
  Contentious issues
  None
  Plans for upcoming meetings (4.5 TUs remaining)
  SA2#160AH: Start solution discussion, last meeting for Key Issue updates
  SA2#161: Continue solution discussion, last meeting for new solution proposals
  SA2#162: last meeting for solution updates, start discussion on evaluation and conclusion
  SA2#163: Complete solution evaluation and study conclusion

## Slide 5: FS_EnergySys Work Plan
Total 13 TUs
  6.5 TUs for Study Phase
  6.5 TUs for Normative Work
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#159 | Oct 2023 | 1 | 1 | TR skeleton, scope, architectural assumptions, key issue discussion
SA2#160 | Nov 2023 | 1 | 1 | Continue discussion on Key Issues, start solution discussion
SA2 E-AH | Jan 2024 | 1 |  | Continue solution discussion, last meeting for Key Issue proposals
SA2#161 | Feb 2024 | 1.5 |  | Continue solution discussion, last meeting for new solution proposals
SA2#162 | Apr 2024 | 1 |  | last meeting for solution updates, start discussion on evaluation and conclusion
SA2#163 | May 2024 | 1 |  | Complete evaluations and conclusions
 | Total | 6.5 |  |