## Slide 1: FS_5G_Femto Status Report
NTT DOCOMO
(Rapporteur)

## Slide 2: FS_5G_Femto status after SA2#161
  Progress since SA2#161
  TR 23.700-45 v0.2.0 is available.
  23 Tdocs were submitted: 19 Tdocs are for new solution, 3 Tdocs are for KI update and 1 Tdoc is for scope update.
  20 Tdocs were handled including scope update, KI update and solution proposals for below two KIs:
    KI#1 Support of UE move between CAG cell of 5G Femto and CSG cell and
    KI#2 Enabling provisioning of subscribers allowed to access CAG cell and managing access control by the CAG owner or an authorized administrator.
    4 new solutions for KI#2 were approved.
    All solutions for KI#1 were either postponed or noted.
  RAN impacts and dependencies
  See contentious issue.
Contentious issues
  KI#1 needs clarification in regards to scope and some technical aspects such as RAN and UE impacts, without common understanding, this KI may be at risk not to complete by May, 2024.
Next steps
  At SA2#162, continue solution discussions and start KI#2 evaluations and interim conclusions (if possible).
    KI#1 and only new solutions for KI#2 will be prioritized (if not covered by the existing solutions).
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_Femto | Study on System aspects of 5G NR Femto | 15% -> 40% | June 2024 | 1020002

## Slide 3: FS_5G_Femto Status at SA#103
Progress since SA#102
  Study started with SA2#160AH-e.
  TR 23.700-45 v0.2.0 is available.
  At SA2#160AH-e: TR skeleton, Scope, Architecture Assumptions/Requirements, and 2 Key Issues to cover the WTs in the SID agreed.
  At SA2#161: New solutions agreed (4 solutions for KI#2).
  RAN impacts and dependencies
  See contentious issue.
Contentious issues
  KI#1 may be at risk not to complete by May, 2024 if common understanding cannot be reached on how RAN impact should be considered in SA2 proposed solutions.
Next steps
  Solution discussions, Evaluations, Conclusions, TR sent to SA for one-step Approval
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_Femto | Study on System aspects of 5G NR Femto | 15% -> 40% | June 2024 | 1020002

## Slide 4
Total 5 TUs
  2 TUs for Study Phase and 3 TUs for Normative Work
NOTE:
  WT#1 (normative only) is reserved for dealing with architectural aspects based on the RAN work that can be coordinated with RAN WGs (RAN3) and conclude in the normative phase.
FS_5G_Femto Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2 #160AH-e | Jan 2024 | 0.5 |  | TR skeleton, scope, architectural assumptions, key issue discussion, (solutions for information).
SA2#161 | Feb 2024 | 0.5 |  | Start solution discussion, last meeting for Key Issue proposals (if any).
SA2#162 | Apr 2024 | 0.5 |  | Continue solution discussion, last meeting for new solution proposals, start discussion on evaluation and interim conclusion (KI#2).
SA2#163 | May 2024 | 0.5 |  | Complete evaluations and conclusions.
 | Total | 2 |  | 

## Slide 5: BACKUP

## Slide 6: FS_5G_Femto Status after SA2#160AH-e
  Progress since SA2#160AH-e
  Study started with SA2#160AH-e.
  TR 23.700-45 v0.1.0 is available.
  23 TDocs were submitted (including TR skeleton and scope from the Rapporteur) and total 6 Tdocs (2 Tdocs proposing new KIs, 1 Tdoc on architecture assumptions and 3 Tdocs proposing solutions) could not be handled due to TU budget/quota.
    The contents of the not handled Tdocs were also considered when discussing the related new Key Issues and Architecture assumptions.
  TR skeleton, Scope, Architecture Assumptions/Requirements, 2 Key Issues to cover the WTs in the SID were approved.
  RAN impacts and dependencies
  None
Contentious issues
  None
Next steps
  Addressing EN in KI#1 and start solution discussions for agreed Key Issues in next meeting
WI Code | Work Item Title | WP | Target Date | WID#
FS_5G_Femto | Study on System aspects of 5G NR Femto | 0% -> 15% | June 2024 | 1020002