## Slide 1: Overall SA2 Rel-19 status
Andy Bennett
SA2 Chair
SA WG2 Meeting #165 Hyderabad
October 14 – October 18, 2024

## Slide 2: Status of Rel-19 work going into SA2#165
As we approach the Stage 2 freeze for Release 19 it is worth analyzing status and progress compared to our planning at the start of the release
This analysis can help us when considering the planning of Release 20

## Slide 3: Status of Rel-19 work going into SA2#165
Overall view
  Maintenance TU’s started higher than planned, but declined more quickly than expected
  Rel-19 study TU’s were fewer than planned in the first 6 months but increased rapidly after that
  TEI19 TU’s were as planned except for the additional time required at the start to discuss which to include in the release
  Clashes between topics mean that some TU’s have been “unconsumed”
Chart: TU's planned vs consumed
| #158 | #159 | #160 | E Ad hoc | #161 | #162 | #163 | #164
Maintenance Planned | 24 | 21 | 21 | 14 | 16 | 12 | 10 | 10
Maintenance Actual | 27 | 25 | 23.5 | 0 | 10.75 | 8 | 4.75 | 10
Rel-19 planned | 6 | 9 | 9 | 16 | 14 | 18 | 20 | 20
Rel-19 actual | 9 | 10 | 5.25 | 10.75 | 16 | 21.25 | 26.75 | 20.5
TEI19 planned | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2
TEI19 actual | 0 | 0 | 0 | 0 | 6 | 2 | 2.5 | 1.5

## Slide 4: Status of Rel-19 work going into SA2#165
Study phase
  Planned TU’s for the studies: 75
  Normal session TU’s consumed: 77.75
  2 Studies consumed fewer TU’s than planned
  8 Studies consumed more TU’s than planned
  In addition 28 drafting sessions were also allocated
  Future release planning should consider taking into account that in Rel-19 drafting sessions added approximately 30% additional TU’s
    This could be accounted for in the number of buffer TU’s to assume when planning the release

## Slide 5: Status of Rel-19 work going into SA2#165
Normative work
  After one meeting 8 out of 15 Work Items are on target
  12.5 TU’s out of 56 have been consumed (22%)
  However, 6.5 TU’s planned for normative work have been consumed by study work after June
  10 of 14 approved TEI19 items have been completed
  4 approved TEI19 items are on the agenda for Q4 2024
  4 TEI19 proposals were agreed to be submitted in Q4 2024