## Slide 1: 5GSAT_Ph3_ARCH & FS_5GSAT_Ph3_ARCH Status Report Integration of satellite components in the 5G architecture Phase 3
Hucheng Wang (CATT),
Ramon Ferrus (Sateliot)

## Slide 2
Progress since SA2#165
  8 CRs and 2 LS out are approved, 3 CRs are postpone
  KI#1 (Regenerative-based satellite access): 1 CR on support of regenerative based satellite access in 5GS is agreed, 1 CR for EPS is postponed. 1 LS Out is approved to reply LS In from RAN.
  KI#2 (S&F): 3 CRs are agreed to support both split MME option and whole EPC onboard option, 2 CRs for common functional and procedure description are postponed. 1 LS Out is approved to reply LS In from SA3.
  KI#3 (UE-satellite-UE): 4 CRs are agreed to support UE-satellite-UE communication activation with IMS-AGW onboard satellite.
  RAN impacts and dependencies
  Yes, KI#1 depends on RAN3 conclusion, and KI#2 has RAN impact (on SIB information)
Contentious issues
  KI#2: how to support S&F Monitoring List.
  KI#3: how to support procedures for change of the on-board IMS-AGW.
5GSAT_Ph3_ARCH status after SA#105
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1040027 | Integration of satellite components in the 5G architecture Phase 3 | 5GSAT_Ph3_ARCH | 12/12/2024 | 15 | SP-240986 | 45 | In progress
1010033 | Study on Integration of satellite components in the 5G architecture Phase 3 | FS_5GSAT_Ph3_ARCH | 21/06/2024 | 100 | SP-231199 | 100 | closed

## Slide 3
Next steps
  KI#1:
    Alignment to RAN conclusion on support of regenerative-based satellite access
  KI#2:
    Common functional description for support of store and forward
    Procedures to support store and forward
  KI#3:
    Support of UE-satellite-UE communication with IMS-AGW onboard satellite:
      Functional description to support satellite change (in both IMS and 5GS)
      Procedure to support satellite change in IMS
      Procedure to support UE-sat-UE communication in 5GS
    Support of UE-satellite-UE communication with UPF only onboard satellite (depending on SA3-LI feedback which should be available after Nov. 1st)
5GSAT_Ph3_ARCH status after SA#105

## Slide 4
Work plan
5GSAT_Ph3_ARCH status after SA#105
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#159 | Qct. 2023 | 1 | 1 | TR skeleton, scope, definition, assumption, scenario
SA2#160 | Nov. 2023 | 1 | 1 | Key issue, assumptions
SA2#160E-AH | Jan. 2024 | 1.5 | 1.5 | Last meeting for key issues update (no new KI), start solution discussions
SA2#161 | Feb. 2024 | 1 | 1 | Provide/update solutions, start solutions evaluation
SA2#162 | Apr. 2024 | 1.5 | 1.5 | Last meeting to update solutions, continue solutions evaluation and start conclusion.
SA2#163 | May. 2024 | 1 | 1 | Complete evaluation and conclusions
SA2#164 | Aug. 2024 | 1.5 | 1.5 | Functional descriptions for KI#2 and KI#3
SA2#165 | Qct. 2024 | 2 | 2 | Functional and procedure descriptions for KI#2 and KI#3 (only UE-sat-UE communication activation), functional description for KI#1 (only 5GS)
SA2#166 | Nov. 2024 | 2 | 2 | Alignment to RAN conclusion for KI#1, common functional description and procedure for KI#2, mobility support for KI#3, and support of UPF only onboard for KI#3
Total TU’s |  | 7 + 5.5 = 12.5 | 7 + 5.5 = 12.5 | 
Used TU’s |  |  | 7 + 3.5 = 10.5 | 

## Slide 5
Progress since SA2#165
  8 CRs and 2 LS out are approved, 3 CRs are postpone
  KI#1 (Regenerative-based satellite access): 1 CR on support of regenerative based satellite access in 5GS is agreed, 1 CR for EPS is postponed. 1 LS Out is approved to reply LS In from RAN.
  KI#2 (S&F): 3 CRs are agreed to support both split MME option and whole EPC onboard option, 2 CRs for common functional and procedure description are postponed. 1 LS Out is approved to reply LS In from SA3.
  KI#3 (UE-satellite-UE): 4 CRs are agreed to support UE-satellite-UE communication activation with IMS-AGW onboard satellite.
  RAN impacts and dependencies
  Yes, KI#1 depends on RAN3 conclusion, and KI#2 has RAN impact (on SIB information)
Contentious issues
  KI#2: how to support S&F Monitoring List.
  KI#3: how to support procedures for change of the on-board IMS-AGW.
5GSAT_Ph3_ARCH status after SA2#165
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1040027 | Integration of satellite components in the 5G architecture Phase 3 | 5GSAT_Ph3_ARCH | 12/12/2024 | 15 | SP-240986 | 45 | In progress
1010033 | Study on Integration of satellite components in the 5G architecture Phase 3 | FS_5GSAT_Ph3_ARCH | 21/06/2024 | 100 | SP-231199 | 100 | closed

## Slide 6
Next steps
  KI#1:
    Alignment to RAN conclusion on support of regenerative-based satellite access
  KI#2:
    Common functional description for support of store and forward
    Procedures to support store and forward
  KI#3:
    Support of UE-satellite-UE communication with IMS-AGW onboard satellite:
      Functional description to support satellite change (in both IMS and 5GS)
      Procedure to support satellite change in IMS
      Procedure to support UE-sat-UE communication in 5GS
    Support of UE-satellite-UE communication with UPF only onboard satellite (depending on SA3-LI feedback which should be available after Nov. 1st)
5GSAT_Ph3_ARCH status after SA2#165

## Slide 7
Work plan
5GSAT_Ph3_ARCH status after SA2#165
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#159 | Qct. 2023 | 1 | 1 | TR skeleton, scope, definition, assumption, scenario
SA2#160 | Nov. 2023 | 1 | 1 | Key issue, assumptions
SA2#160E-AH | Jan. 2024 | 1.5 | 1.5 | Last meeting for key issues update (no new KI), start solution discussions
SA2#161 | Feb. 2024 | 1 | 1 | Provide/update solutions, start solutions evaluation
SA2#162 | Apr. 2024 | 1.5 | 1.5 | Last meeting to update solutions, continue solutions evaluation and start conclusion.
SA2#163 | May. 2024 | 1 | 1 | Complete evaluation and conclusions
SA2#164 | Aug. 2024 | 1.5 | 1.5 | Functional descriptions for KI#2 and KI#3
SA2#165 | Qct. 2024 | 2 | 2 | Functional and procedure descriptions for KI#2 and KI#3 (only UE-sat-UE communication activation), functional description for KI#1 (only 5GS)
SA2#166 | Nov. 2024 | 2 | 2 | Alignment to RAN conclusion for KI#1, common functional description and procedure for KI#2, mobility support for KI#3, and support of UPF only onboard for KI#3
Total TU’s |  | 7 + 5.5 = 12.5 | 7 + 5.5 = 12.5 | 
Used TU’s |  |  | 7 + 3.5 = 10.5 | 

## Slide 8
Backup

## Slide 9
General
  Total TU estimates for the normative phase: 5.5
  1.5 TU has been used in SA2#164
  The rapporteurs for normative phase are to be updated
Progress since SA2#164
  Total 4 CRs were discussed, and 2 CRs are endorsed for implementing KI#2 (store and forward)
  Total 4 CRs were discussed, and 2 CRs are endorsed for implementing KI#3 (UE-satellite-UE communication)
  1 LS reply is to be sent to SA3LI asking them to support IMS-AGW relocation, and to check the feasibility of UPF only on-board solution
WI Code | Work Item Title | WP | Target Date | WID#
5GSAT_Ph3_ARCH | Integration of satellite components in the 5G architecture Phase 3 | 0 -> 15% | Dec, 2024 | SP-240986
FS_5GSAT_Ph3_ARCH | Study on Integration of satellite components in the 5G architecture Phase 3 | 100% | June, 2024 | SP-231199
5GSAT_Ph3_ARCH status after SA2#164

## Slide 10
  RAN impacts and dependencies
  Yes, KI#1 depends on RAN3 conclusion, and KI#2 has RAN impact (on SIB information)
Contentious issues
  none
Next steps
  KI#2:
    Procedures to support store and forward
  KI#3 (only considering IMS-AGW onboard satellite):
    Procedures of activating UE-satellite-UE communication
    Functional description of mobility support
  KI#1:
    Alignment to RAN conclusion on support of regenerative-based satellite access
5GSAT_Ph3_ARCH status after SA2#164

## Slide 11
General
  Total TU estimates for the normative phase: 5.5
  1.5 TU has been used in SA2#164
  The rapporteurs for normative phase are to be updated
Progress since SA#104
  Total 4 CRs were discussed, and 2 CRs are endorsed for implementing KI#2 (store and forward)
  Total 4 CRs were discussed, and 2 CRs are endorsed for implementing KI#3 (UE-satellite-UE communication)
  1 LS reply is to be sent to SA3LI asking them to support IMS-AGW relocation, and to check the feasibility of UPF only on-board solution
WI Code | Work Item Title | WP | Target Date | WID#
5GSAT_Ph3_ARCH | Integration of satellite components in the 5G architecture Phase 3 | 0 -> 15% | Dec, 2024 | SP-240986
FS_5GSAT_Ph3_ARCH | Study on Integration of satellite components in the 5G architecture Phase 3 | 100% | June, 2024 | SP-231199
5GSAT_Ph3_ARCH status after SA#104

## Slide 12
  RAN impacts and dependencies
  Yes, KI#1 depends on RAN3 conclusion, and KI#2 has RAN impact (on SIB information)
Contentious issues
  none
Next steps
  KI#2:
    Procedures to support store and forward
  KI#3 (only considering IMS-AGW onboard satellite):
    Procedures of activating UE-satellite-UE communication
    Functional description of mobility support
  KI#1:
    Alignment to RAN conclusion on support of regenerative-based satellite access
5GSAT_Ph3_ARCH status after SA#104