## Slide 1: 5G_Femto Status Report
NTT DOCOMO
(Rapporteur)

## Slide 2: 5G_Femto Status after SA2#165
  Progress since SA2#165
  A total of 5 CRs (4 CRs for TS 23.501 and 1 CR for TS 23.502 in relation to the WT#1) were agreed.
  LS from SA WG3 – “LS on Clarification regarding definition of 5G NR femto ownership”
    Reply LS on Clarification regarding definition of 5G NR femto ownership (S2-2411241) was agreed.
  LS from SA WG3 – “LS to request clarification on the potential baseline system architecture of 5G NR Femto” has been postponed.
  RAN impacts and dependencies
  None.
Outstanding issues
  A common understanding of access to local services via 5G Femto in relation to the impact of the specifications is required.
Next steps
  Finalize the normative work and completion of the WID.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | New % | Change or comment
1020002 | Study on System aspects of 5G NR Femto | FS_5G_Femto | 09/09/2024 | 100% | 100% | 
1040028 | System aspects of 5G NR Femto | 5G_Femto | 12/12/2024 | 30% | 75% | 

## Slide 3
Total 3 TUs for Normative Work
5G_Femto Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#164 | Aug 2024 | 1 | 0.75 | Start normative work
SA2#165 | Oct 2024 | 1 | 1 | Continue normative work
SA2#166 | Nov 2024 | 1 |  | Complete the normative work
 | Total | 3 | 3 |