## Slide 1: Rel-19 FS_AmbientIoT Status Report
Runze Zhou (Huawei), Fei Lu (OPPO)
(Rapporteurs)

## Slide 2: FS_AmbientIoT Status after SA2#165
  Progress since SA2#165
  7 pCR and 1 LS out were agreed.
  Interim conclusions are captured in TR 23.700-13 v1.1.0, including:
    Key issue 1:
      Architecture options of topology 1
      Architecture options of topology 2
      Common aspects for both topologies
    Key issue 2: Permanent AIoT Device ID component
    Key issue 3: AIoT services supported by the 5GC
  RAN impacts and dependencies
  Several editor’s notes in the TR interim conclusions need coordination with RAN and SA3
Outstanding issues
  Architecture options for T1 and T2 needs further discussion in next meeting.
  Whether and how temporary ID is supported for privacy protection, pending SA3 study and feedback on LSout S2-2411049
  Various open issues, e.g., reader selection, reader area identification, for topology 2 whether NAS option can be supported, et al
Next steps
  Finalize the TR conclusion in next SA2 meeting
  Discuss and try to approve the work item in next SA2 meeting
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020071 | Study on Architecture support of Ambient power-enabled Internet of Things | FS_AmbientIoT | Dec, 2024 | 80% | SP-240969 | 85% | 

## Slide 3
In total 11.5 TUs for Study Phase
Check in TSG#106 (Dec’24) for further Ambient IoT work taking into account RAN Ambient IoT progress
FS_AmbientIoT Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2 E-AH | Jan 2024 | 0.5 | 0.5 | TR skeleton, scope, architectural assumptions/requirements Start and complete key issue (only for information)Solutions
SA2#161 | Feb 2024 | 2 | 2 | Start solutions discussions key issue update to address the ENs can be considered NOTE: no new key issue proposal will be considered
SA2#162 | Apr 2024 | 2 | 2 | Continue solutions discussions
SA2#163 | May 2024 | 2 | 2 | Continue solutions discussions
SA2#164 | Aug 2024 | 2 |  | Continue and complete solution discussions (multi-sourced papers will be handled with priority, any new solution should be in principle different from the existing solutions in the TR and ready for evaluation). Start evaluation/conclusion: group/categorize the solutions, identify the non-controversial aspects and key controversial aspects, identify the dependency with other WHs and have earlier coordination. AIoT conference call and NWM discussion will be arranged between SA2#163 and SA2#164 for e.g. deployment scenarios including roaming, etc.
SA2#165 | Oct 2024 | 1.5 |  | Decide way forward for open issues Continue TR conclusion and evaluation, focus on conclusions (and where needed supporting evaluations). Priority will be for contributions that help us all work towards finalizing the conclusion.
SA2#166 | Nov 2024 | 1.5 |  | Finalize all key issue conclusions i.e. to address FFS in TR conclusion clause, and new conclusion proposal essential for the study
 | Total | 11.5 |  | 

## Slide 4: BACKUP

## Slide 5: FS_AmbientIoT Status after SA2#160AH-e
  Progress since SA2#160AH-e
  Study started with SA2#160AH-e.
  TR 23.700-13 v0.1.0 is available.
  40 TDocs were submitted and 22 Tdocs could not be handled due to TU budget/quota.
    The contents of the not handled Tdocs for new key issues were also considered in the discussion of the e-meeting.
  8 pCRs for TR skeleton, Scope, Terms, Architecture Assumptions/Requirements, 3 Key Issues to cover the WTs in the SID have been agreed.
  Key issue discussion has been finalized with two ENs(reference of the RAN TR to be updated, term name of “inventory” and “command” to be given). For future meetings, key issue update to address the ENs can be considered, but no new key issue proposal will be considered.
  RAN impacts and dependencies
  3 key issues have RAN dependency
  Whether traffic type “DO-A” will be in the R19 scope needs RAN decision
Contentious issues
  None
Next steps
  Start solution discussions for agreed Key Issues in next meeting
WI Code | Work Item Title | WP | Target Date | WID#
FS_AmbientIoT | Study on Architecture support of Ambient power-enabled Internet of Things | 0% -> 13% | Dec 2024 | 1020071

## Slide 6: FS_AmbientIoT Status after SA2#161
  Progress since SA#102
  TR skeleton, Scope, Terms, Architecture Assumptions and Requirements are agreed
  3 key issues are agreed and no new key issue will be considered
  12 solutions are agreed and documented in the TR
  TR 23.700-13 v0.2.0 is available
  RAN impacts and dependencies
  3 key issues have RAN dependency
  Whether traffic type “DO-A” will be in the R19 scope needs RAN decision
Contentious issues
  None
Next steps
  Continue solution discussions in SA2#162 meeting
WI Code | Work Item Title | WP | Target Date | WID#
FS_AmbientIoT | Study on Architecture support of Ambient power-enabled Internet of Things | 13% -> 25% | Dec 2024 | SP-231803 1020071

## Slide 7: FS_AmbientIoT Status at SA#103
  Progress since SA#102
  TR skeleton, Scope, Terms, Architecture Assumptions and Requirements are agreed
  3 key issues are agreed and no new key issue will be considered
  12 solutions are agreed and documented in the TR
  TR 23.700-13 v0.2.0 is available
  RAN impacts and dependencies
  3 key issues have RAN dependency
  Whether traffic type “DO-A” will be in the R19 scope needs RAN decision
Contentious issues
  None
Next steps
  Continue solution discussions
WI Code | Work Item Title | WP | Target Date | WID#
FS_AmbientIoT | Study on Architecture support of Ambient power-enabled Internet of Things | 13% -> 25% | Dec 2024 | SP-231803 1020071

## Slide 8: FS_AmbientIoT Status after SA2#162
  Overall progress in SA2#162
  In total 16 papers are agreed, including:
    12 new solutions
    3 solution update
    1 new abbreviation “RFID”
  TR 23.700-13 v0.3.0 is available, including 24 solutions
  Impacts and dependencies on other WGs
  Several solutions have EN/note, need coordination with RAN, SA3 and SA5
Next steps
WI Code | Work Item Title | WP | Target Date | WID#
FS_AmbientIoT | Study on Architecture support of Ambient power-enabled Internet of Things | 25% -> 45% | Dec 2024 | SP-231803 1020071

## Slide 9: FS_AmbientIoT Status at SA#104
  Progress since SA#102
  TR 23.700-13 v0.4.0 is available.
  22 new solutions agreed, for 3 key issues
  1 LS (S2-2407231) to SA1, SA3 and RAN1 (CC RAN2, RAN3)
  RAN impacts and dependencies
  1 LS (S2-2407231) to SA1, SA3 and RAN1 (CC RAN2, RAN3)
  Several solutions have EN/note, need coordination with RAN, SA3 and SA5
Contentious issues
  None
Next steps
  Continue and complete solution discussions (multi-sourced papers will be handled with priority, any new solution should be in principle different from the existing solutions in the TR and ready for evaluation).
  Start evaluation/conclusion: group/categorize the solutions, identify the non-controversial aspects and key controversial aspects, identify the dependency with other WHs and have earlier coordination.
  AIoT conference call and NWM discussion will be arranged between SA2#163 and SA2#164 for e.g. deployment scenarios including roaming, etc.
WI Code | Work Item Title | WP | Target Date | WID#
FS_AmbientIoT | Study on Architecture support of Ambient power-enabled Internet of Things | 25% -> 65% | Dec 2024 | SP-231803 1020071

## Slide 10: FS_AmbientIoT Status after SA2#163
  Overall progress in SA2#163
  TR 23.700-13 v0.4.0 is available, including 34 solutions
  15 papers has been agreed (62 submitted), including:
    1 LS out to SA1, SA3 and RAN1 (CC RAN2, RAN3)
    4 solution updates
    10 new solutions
  Impacts and dependencies on other WGs
  1 LS (S2-2407231) to SA1, SA3 and RAN1 (CC RAN2, RAN3)
  Several solutions have EN/note, need coordination with RAN, SA3 and SA5
Next steps
  Continue and complete solution discussions (multi-sourced papers will be handled with priority, any new solution should be in principle different from the existing solutions in the TR and ready for evaluation).
  Start evaluation/conclusion: group/categorize the solutions, identify the non-controversial aspects and key controversial aspects, identify the dependency with other WHs and have earlier coordination.
  AIoT conference call and NWM discussion will be arranged between SA2#163 and SA2#164 for e.g. deployment scenarios including roaming, etc.
WI Code | Work Item Title | WP | Target Date | WID#
FS_AmbientIoT | Study on Architecture support of Ambient power-enabled Internet of Things | 45% -> 65% | Dec 2024 | SP-231803 1020071

## Slide 11: FS_ AmbientIoT Status at SA#105
Progress since SA#104
  TR 23.700-13 v0.5.0 sent to TSG SA for information
  Revised SID was agreed in SA#104 (SP-240696)
  19 pCRs are approved in SA2#164, including: 8 new solutions, 8 solution updates, 1 new architecture assumption, and 2 interim conclusion.
  Other WG impacts and dependencies
  Incomplete feedback from SA1 due to lack of consensus in SA1 (no feedback on need for an unalterable/permanent equipment identification and related usage, no feedback on business model and need for subscription).
  Several editor’s notes in the TR solution, need coordination with RAN, SA3 and SA5
Outstanding issues
  Diverging views on the need for subscription, network layer security, temporary CN ID, roaming support and related to that, the implications for the overall architecture. Lack of clear SA1 feedback/requirements on these aspects poses a potential risk for SA2 conclusion.
Next steps
  Discuss way forward on open issues, taking into account LS reply from RAN1 and SA1, and 11 postponed papers from SA2#164 meeting.
  Continue with evaluation and conclusion
WI Code | Work Item Title | WP | Target Date | WID#
FS_AmbientIoT | Study on Architecture support of Ambient power-enabled Internet of Things | 65% -> 80% | December 2024 | SP-240969

## Slide 12: FS_ AmbientIoT Status after SA2#164
  Progress in SA2#164
  19 pCRs are approved in the meeting, including: 8 new solutions, 8 solution updates, 1 new architecture assumption, and 2 interim conclusions
  TR 23.700-13 v0.5.0 is available
  LS in from RAN2 (S2-2407447) was discussed but the reply LS was postponed, due to no consensus
  Other WG dependencies
  Incomplete feedback from SA1 due to lack of consensus in SA1 (no feedback on need for an unalterable/permanent equipment identification and related usage, no feedback on business model and need for subscription).
  Several editor’s notes in the TR solution, need coordination with RAN, SA3 and SA5
Outstanding issues
  Diverging views on the need for subscription, network layer security, temporary CN ID, roaming support and related to that, the implications for the overall architecture. Lack of clear SA1 feedback/requirements on these aspects poses a potential risk for SA2 conclusion.
Next steps
  Discuss way forward on open issues, taking into account LS reply from RAN1 and SA1, and 11 postponed papers from SA2#164 meeting
  Continue with evaluation and conclusion
WI Code | Work Item Title | WP | Target Date | WID#
FS_AmbientIoT | Study on Architecture support of Ambient power-enabled Internet of Things | 65% -> 80% | December 2024 | SP-240969