## Slide 1: AIML_CN Status Report
vivo (Rapporteur) MediaTek Inc. (Rapporteur)

## Slide 2: AIML_CN status after SA2#166 (1/2)
General
  154 papers(including discussion papers) were submitted, 18 CRs were agreed, 3 LS were agreed, 9 CRs were merged.
  KI#1: 7 CRs are agreed, 2 LS out were agreed
    23.273/23.288 CRs: LMF retrieving ML Model from MTLF, data collection by LMF, AI/ML model performance monitoring by NWDAF, LS to SA3 on User Privacy Aspects of LMF-based AI/ML Positioning, LS to SA5 on ML Model provisioning by OAM to LMF for UE positioning
  KI#2: 7 CRs are agreed
    23.288 CRs: updating general prepare/training/inference procedure, updating Registration and Discovery procedure for VFL, high level feature description
    One 23.502 CR for VFL support during the discovery of NWDAF, NEF, and AF instances
  KI#3: the CR for Support of QoS and policy assistance analytics is agreed.
  KI#4: 3 CR is agreed
    New analytics ID to support Signalling storm Mitigation and Prevention for 23.288, and corresponding update in 23.501, 23.502
  Impacts and dependence with other WGs :
  Impact on RAN: for KI#1, any data to be collected from UE/RAN by LMF for the model training/model inference/model performance monitoring for LMF-side model is assumed to be defined by RAN WGs and coordination with RAN is needed.
  Impact SA3: consent/privacy aspects, in coordination with SA3
Controversial issues
  NONE
Next Steps
  Continue normative work in 2025 Q1 (with exception sheet)
WI Code | Work Item Title | WP | Target Date | WID#
AIML_CN | Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | 50% > 85% | Dec, 24 | SP-240991
Notes: KI#1 : 9 agreed (2 LS out), 1 noted,
KI#2: 6 agreed, 1 approved, 5 merged, 2 open
KI#3: 1 agreed, 1 merged
KI#4: 3 agreed, 3 merged
LS (Reply LS on AIML data collection): agreed.
Total: 21 agreed, 9 merged,

## Slide 3: AIML_CN status after SA2#166 (2/2)
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2 #160AH-e | Jan 2024 | 0.5 | 0.5 | TR 23.700-84 TR Skeleton, Arch Assumptions, scope, Initial KIs use case(s)
SA2#161 | Feb 2024 | 1.5 | 1.5 | Final KI/use case updates + Initial Solutions, Attempt to close new Key Issue and new UC.
SA2#162* | Apr 2024 | 1 | 1 | Solution updates and new solution(s)
SA2#163 | May 2024 | 1 | 1 | Final solution updates and final Evaluations + Conclusions
SA2#164 | Aug 2024 | 1.5 | 1 | Normative work per KI conclusion
SA2#165 | Oct 2024 | 1.5 | 1.5 | Normative work per KI conclusion
SA2#166 | Nov 2024 | 1.5 | 1.5 | Normative work per KI conclusion
SA2#166--Ad Hoc-e | Jan 2025 | 1.5 |  | Normative work per KI conclusion (exception)
SA2#167 | Feb 2025 | 1.5 |  | Normative work per KI conclusion (exception)
Total 8 TUs
  4 TUs for Study Phase
  4 TUs for Normative Work
It is planned to request additional 3 TUs with exception sheet in 2025 Q1
Note 1: Rapporteurs will prepare question list and figure out the contribution plan/job split in Jan SA2 meeting
Note 2:Regarding UE side data collection, Reply LS sent to SA/RAN plenary indicates that a full evaluation of potential solutions would require further study in SA2, and coordination with SA5, SA3, and RAN2.

## Slide 4: AIML_CN status at SA#106
General
  308 papers(including discussion papers) were submitted, 22 CRs were agreed, 2 LS out were agreed, 2 LS reply were agreed.
  KI#1: 10 CRs are agreed, 2 LS out were agreed
    23.273/23.288 CRs: LMF retrieving ML Model from MTLF, data collection by LMF, AI/ML model performance monitoring by NWDAF, LS to SA3 on User Privacy Aspects of LMF-based AI/ML Positioning, LS to SA5 on ML Model provisioning by OAM to LMF for UE positioning
  KI#2: 8 CRs are agreed
    23.288 CRs: updating general prepare/training/inference procedure, updating Registration and Discovery procedure for VFL, high level feature description
    One 23.501, 23.502 CR for VFL support during the discovery of NWDAF, NEF, and AF instances
  KI#3: the CR for Support of QoS and policy assistance analytics is agreed
  KI#4: 3 CR is agreed
    New analytics ID to support Signalling storm Mitigation and Prevention for 23.288, and corresponding update in 23.501, 23.502
  Impacts and dependence with other WGs :
  Impact on RAN: For KI#1, any data to be collected from UE/RAN by LMF for the model training/model inference/model performance monitoring for LMF-side model is assumed to be defined by RAN WGs and coordination with RAN is needed.
  Impact SA3: consent/privacy aspects, in coordination with SA3
Controversial issues
  NONE
Next Steps
  Continue normative work in 2025 Q1 (with exception sheet)
WI Code | Work Item Title | WP | Target Date | WID#
AIML_CN | Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | 15% > 85% | Dec, 24 | SP-240991

## Slide 5: Annex
Status report for SA2#162/163/164/165

## Slide 6: AIML_CN status after SA2#165 (1/2)
General
  154 papers(including discussion papers) were submitted, 13 CRs were agreed, 8 CRs were merged, 8 CRs were postponed.
  KI#1: 7 CRs are agreed
    23.273/23.288 CRs: high level data collection, LMF retrieving ML Model from MTLF, AI/ML model performance monitoring by LMF and NWDAF.
  KI#2: 5 CRs are agreed
    23.288 CRs: updating general training/inference procedure for NWDAF as VFL server, updating Registration and Discovery procedure for VFL/high level feature description
    One 23.501 CR for VFL support during the discovery of NWDAF, NEF, and AF instances
  KI#3: the CR for Support of QoS and policy assistance analytics is postponed
  KI#4: one CR is agreed and progress is good
    one major CR for New analytics ID to support Signalling storm Mitigation and Prevention for 23.288 is to be approved (with few Editor’s Notes)
  RAN impacts and dependencies:
  For KI#1, any data to be collected from UE/RAN by LMF for the model training/model inference/model performance monitoring for LMF-side model is assumed to be defined by RAN WGs and coordination with RAN is needed.
Controversial issues
  Regarding KI#3 on Support of QoS and policy assistance analytics, the names of some parameter(s) e.g. the QoE f provided by PCF to NWDAF needs further discussion.
Next Steps
  Continue normative work
WI Code | Work Item Title | WP | Target Date | WID#
AIML_CN | Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | 15% > 50% | Dec, 24 | SP-240991

## Slide 7: AIML_CN status after SA2#164
General
  144 CRs were submitted, 18 CRs were handled, 2 CRs were NOTED, 4 CRs were merged, 5 CRs were postponed, 1 open and 6 CRs were agreed.
  KI#1: 3 CRs agreed.
    TS 23.288: MTLF supporting ML model provisioning with LMF.
    TS 23.273: general feature description of LMF supporting AI/ML based positioning, Data collection at LMF.
  KI#2: 3 CRs agreed.
    TS 23.288: General inference procedure, High level feature description for VFL, Registration and Discovery procedure for VFL.
    One CR for VFL training procedure reached offline agreement but was postponed due to the lack of time in Friday plenary.
  KI#3:No CR agreed. The majority companies prefer to have a new analytics ID but more discussion is needed.
  KI#4:The CR for New analytics ID to support Signalling storm Mitigation and Prevention reached offline agreement but was kept open due to the lack of time in Friday plenary and will be handled next meeting.
  RAN impacts and dependencies:
  For KI#1, any data to be collected from UE/RAN by LMF for the model training/model inference/model performance monitoring for LMF-side model is assumed to be defined by RAN WGs and coordination with RAN is needed.
Other WG dependencies
  Security aspects, will be addressed by SA3.
  OAM aspects, if any, will be addressed by SA5.
WI Code | Work Item Title | WP | Target Date | WID#
AIML_CN | Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | 0% > 15% | Dec, 24 | SP-240991

## Slide 8: FS_AIML_CN status after SA2#163
General
  95 PCRs were submitted, 10 PCRs were approved, 1 PCR was merged, 84 PCRs were not handled and draft TR 23.700-84 v1.0.0 will be submitted to SA plenary for information.
  The WID will be approved
  KI#1: Final conclusion is agreed.
  KI#2: Final conclusion is agreed, and terminology definition and 4 solution update are agreed.
  KI#3: Final conclusion is agreed, and use cases mapping is agreed.
  KI#4: Final conclusion is agreed.
  RAN impacts and dependencies:
  For KI#1, any data to be collected from UE/RAN by LMF for the model training/model inference/model performance monitoring for LMF-side model is assumed to be defined by RAN WGs and coordination with RAN is needed.
Other WG dependencies
  Security aspects, will be addressed by SA3.
  Charging aspects, will be addressed by SA5. OAM aspects, if any, will be addressed by SA5.
WI Code | Work Item Title | WP | Target Date | WID#
FS_AIML_CN | Study on Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | 65% >100% | Jun, 24 | SP-231800

## Slide 9: FS_AIML_CN status after SA2#162
General
  79 papers were received and 39 papers were not handled.
  36 PCRs and 1 LS OUT were approved in total:
    1 LS OUT to RAN WGs related to KI#1;
    8 PCRs papers for key issue #1 new solutions and solution update;
    14 PCRs for key issue #2 solutions and terminologies;
    9 PCRs for key issue #3 solutions;
    5 PCR for key issue #4 solutions.
  RAN impacts and dependencies:
  For KI#1, any data to be collected from UE/RAN by LMF for the model training/model inference/model performance monitoring for LMF-side model is assumed to be defined by RAN WGs.
Other WG dependencies
  None at this stage
Contentious issues
  None (note several ENs need to be addressed across the solutions.)
WI Code | Work Item Title | WP | Target Date | WID#
FS_AIML_CN | Study on Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | 25% > 65% | Jun, 24 | SP-231800