## Slide 1: VMR_Ph2 Status Report
Sony, Qualcomm Incorporated
S2-2411216

## Slide 2
Progress in SA2#166:
  11 CRs to TS 23.501 and TS 23.502 were agreed,
    Aspects agreed: UE access to MWAB; network slicing for UEs served by a MWAB, Backhaul PDU Session handling for MWAB, Support of emergency service via MWAB, Authorization of MWAB (MWAB-gNB and MWAB-UE), Support of Additional ULI,
    Updates to: MWAB architecture for 5GS to include Xn, Configuration of the MWAB-gNB, Impact of MWAB mobility, UE mobility, Annex to include when all entities are within same PLMN (non-roaming)
  TS 23.273: 1 CRs agreed.
    Address remaining EN, interaction between the GMLCs in different PLMNs.
Impacts and dependencies on other WGs:
  Pending response to LS (S2-2407345) sent to RAN3 and cc RAN2, with specific questions on access control and Additional ULI format.
  OAM support is expected to be handled by SA5, and security to be handled by SA3
Controversial issues:
  None
Next steps:
  Alignment considering responses from RAN WGs on LS (S2-2407345), e.g. "Additional ULI" handling, etc.
  Other Alignment based on work progressed in other working groups
  Maintenance work
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020067 | Study on Vehicle Mounted Relays Phase 2 | FS_VMR_Ph2 | 09/09/2024 | 95% | SP-240493 | 100% | Agreed in SA#105 to mark 100%
1040031 | Vehicle Mounted Relays Phase 2 | VMR_Ph2 | 12/12/2024 | 70% | SP-240989 | 100% | 
VMR_Ph2 status after SA2#166

## Slide 3
Progress since SA#105:
  15 CRs to TS 23.501, TS 23.502 and TS 23.273 were agreed.
  Aspects agreed: NAT for BH PDU sessions; Additional ULI support; Emergency service support; QoS Handling Authorization of MWAB; UE access to MWAB; network slicing for UEs served by a MWAB; Backhaul PDU Session handling for MWAB; Impact of MWAB mobility; UE mobility served by MWAB.
Impacts and dependencies on other WGs:
  Pending response to LS (S2-2407345) sent to RAN3 and cc RAN2, with specific questions on access control and Additional ULI format.
  OAM support is expected to be handled by SA5, and security to be handled by SA3
Next steps:
  Alignment considering responses from RAN WGs on LS (S2-2407345), e.g. "Additional ULI" handling, etc.
  Other Alignment based on work progressed in other working groups
  Maintenance work
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020067 | Study on Vehicle Mounted Relays Phase 2 | FS_VMR_Ph2 | 09/09/2024 | 95% | SP-240493 | 100% | Agreed in SA#105 to mark 100%
1040031 | Vehicle Mounted Relays Phase 2 | VMR_Ph2 | 12/12/2024 | 40% | SP-240989 | 100% | 
VMR_Ph2 status at SA#106

## Slide 4: Annex
Status report for SA2#165 and for SA#105

## Slide 5
Progress in SA2#165:
  7 CRs to TS 23.501 and TS 23.502 were agreed, 3 POSTPONED.
  Aspects agreed: NAT for BH PDU sessions; Additional ULI support; Emergency service support; QoS Handling Authorization of MWAB;
  Aspects postponed: Ethernet BH PDU session support; support of slice; support of moblity
  Aspects unhandled: UE Access control
Impacts and dependencies on other WGs:
  Pending response to LS (S2-2407345) sent to RAN3 and cc RAN2, with specific questions on access control and Additional ULI format.
  OAM support is expected to be handled by SA5, and security to be handled by SA3
Controversial issues:
  None
Next steps:
  Complete normative work based on the approved WID (S2-2407385) and conclusions in TR 23.700-06 (clause 8).
  Address postponed and unhandled aspects, and other open issues identified by the editor notes.
  Considering responses from RAN WGs on LS (S2-2407345), e.g. "Additional ULI" handling, etc.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020067 | Study on Vehicle Mounted Relays Phase 2 | FS_VMR_Ph2 | 09/09/2024 | 95% | SP-240493 | 100% | Agreed in SA#105 to mark 100%
1040031 | Vehicle Mounted Relays Phase 2 | VMR_Ph2 | 12/12/2024 | 40% | SP-240989 | 70% | 
VMR_Ph2 status after SA2#165

## Slide 6: VMR_Ph2 status at SA#105
Progress since SA#104:
  TS 23.501: 6 CRs agreed.
    General feature description, definitions, MWAB configuration, Mobility and Location services.
    Deployment options are documented in a new Annex
    Protocol stacks are documented in a new Annex
    Two CRs(S2-2409523 and S2-2409244) were objected by one company due to the reasons stated in meeting report.
  TS 23.273: 2 CRs agreed.
    Specification update to support for Location Services when MWAB is involved is completed
Impacts and dependencies on other WGs:
  RAN dependencies on the MWAB-gNB cell access control, and the Additional ULI format, as indicated in LS (S2-2407345).
  Additional mobility considerations, e.g. gNB ID change, based on potential RAN3 inputs.
  OAM support is expected to be handled by SA5, and security to be handled by SA3.
Next steps:
  Finalize the normative work based on the approved WID (SP-240989) and conclusions in TR 23.700-06 (clause 8), considering responses from RAN WGs.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1040031 | Vehicle Mounted Relays Phase 2 | VMR_Ph2 | 10/12/2024 | 0% | SP-240989 | 40% | 

## Slide 7
FS_VMR_Ph2 Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2 #160AH-e | Jan 2024 | 0.5 | 0.5 | TR skeleton, Scope, Assumptions, Key Issues
SA2#161 | Feb 2024 | 0.5 | 0.5 | New KIs, KI updates; New solutions
SA2#162 | Apr 2024 | 1 | 1 | Last chance for new solutions; solution updates, initial evaluations/Start coord with RAN
SA2#163 | May 2024 | 1 | 1 | Solution updates; evaluations; conclusions, send TR for approval; WID approval
SA2#164 | Aug 2024 | 0.5 | 1 | Normative work, coordination with RAN
SA2#165 | Oct 2024 | 1 | 1 | Normative work, coordination with RAN
SA2#166 | Nov 2024 | 1 | 1 | Complete Normative work, coordination with RAN
 | Total | 5.5 | 6 | 
Total 5.5 TUs
  3 TUs for Study Phase
  2.5 TUs for Normative Work