## Slide 1: Status report for 5GS Enhancement for Energy Efficiency and Energy Saving (EnergySys)
Jungshin Park (Samsung),
Konstantinos Samdanis (Lenovo)

## Slide 2: EnergySys Status at SA#105
  Progress since SA#105
  The normative work started and is progressing
  147 Tdocs were submitted for SA2#165 and #166 (56 CRs are handled, 13 CRs are agreed)
  KI#1: 8 CRs agreed, a new NF (EIF) for energy info collection and its services are defined
  KI#2: 4 CRs agreed for Energy Saving indicator in UE Subscription Data, and BDT policy negotiation
  KI#3: 1 CR agreed for UP path adjustment
  Impacts and dependencies on other WGs
  An LS to RAN WG2 and RAN WG3 is sent to request feedback on the Energy Saving Indicator that may be provided from AMF to NG-RAN to assist energy saving at RAN
  Contentious issues
  None
  Next steps:
  Continue CR discussion
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1050112 | 5GS Enhancement for Energy Efficiency and Energy Saving | EnergySys | 12/12/2024 | 0% | SP-241388 | 70% | Normative work in progress

## Slide 3: EnergySys Status after SA2#166
  Progress since SA2#165
  Total 79 Tdocs were submitted (20 Tdocs handled), and 6 CRs agreed, 2 CRs postponed, 8 CRs noted, 3 LSs noted
  KI#1: 5 CRs agreed, including EIF service definition and energy information collection procedure
  KI#2: 1 CRs agreed for Energy Saving indicator in the UE Subscription Data
  KI#3: CRs on NF selection and UP Path Adjustment are noted
  Impacts and dependencies on other WGs
  An LS to RAN WG2 and RAN WG3 is sent to request feedback on the Energy Saving Indicator that may be provided from AMF to NG-RAN to assist energy saving at RAN
  Contentious issues
  None
  Next steps:
  Continue CR discussion
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1050112 | 5GS Enhancement for Energy Efficiency and Energy Saving | EnergySys | 12/12/2024 | 20% | SP-241388 | 70% | Normative work continued

## Slide 4: FS_EnergySys/EnergySys Work Plan
Total 12.5 TUs used
  8.5 TUs (= 6.5 TU + additional 2 TUs) for Study Phase
  4 TUs for Normative Work
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#159 | Oct 2023 | 1 | 1 | TR skeleton, scope, architectural assumptions, key issue discussion
SA2#160 | Nov 2023 | 1 | 1 | Continue discussion on Key Issues, start solution discussion
SA2#160AH-e | Jan 2024 | 1 | 1 | Start solution discussion, last meeting for Key Issue proposals
SA2#161 | Feb 2024 | 1.5 | 1.5 | Continue solution discussion, last meeting for new solution proposals
SA2#162 | Apr 2024 | 1 | 1 | Focus on solution updates, only unhandled new solution proposals from #161, start discussion on evaluation and conclusion
SA2#163 | May 2024 | 1 | 1 | Critical solution updates only, Complete study conclusion, Prepare a WID proposal for normative work based on conclusion
SA2#164 | Aug 2024 | 2 | 2 | Complete study conclusions, Submit a WID proposal to SA#105
SA2#165 | Oct 2024 | 2 | 2 | Start normative work: discuss general description for essential parts of the feature, focus on changes for TS 23.501
SA2#166 | Nov 2024 | 2.5 | 2 | Continue normative work: update texts for functional descriptions in TS 23.501/503, work on procedures in TS 23.502
 | Total | 13 | 12.5 | 

## Slide 5: Backup

## Slide 6: EnergySys Status after SA2#165
  Progress since SA2#164
  The meeting started the normative work, and focused on the CRs for general descriptions of the feature in TS 23.501
  68 Tdocs were submitted (36 Tdocs handled), and 7 CRs agreed, 2 CRs postponed, 1 CR noted
  KI#1: 3 CRs agreed, including functional description of a new NF and arch. reference model
  KI#2: 3 CRs agreed for subscription info. & policy control aspects, and BDT policy negotiation
  KI#3: 1 CR agreed for UP path adjustment; 1 CR postponed for NF selection
  Impacts and dependencies on other WGs
  None
  Contentious issues
  Standard method for calculation of energy consumption information
  Procedure for collection of energy consumption information (new service vs. reuse of NNWDAF)
  Next steps:
  SA2#166: Continue the normative work
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1050112 | 5GS Enhancement for Energy Efficiency and Energy Saving | EnergySys | 12/12/2024 | 0% | SP-241388 | 20% | Normative work started

## Slide 7: FS_EnergySys Status at SA#105
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010029 | Study on Energy Efficiency and Energy Saving | FS_EnergySys | 18/06/2024 | 99% | SP-231192 | 100% | Study has been completed
  Progress since SA#104
  TR 23.700-66 v1.1.0 is submitted to TSG SA for approval
  1 pCR has been accepted for the update of study conclusion on KI#1
  Working Agreement on KI#1 has been established
  Impacts and dependencies on other WGs:
  Potential RAN support for UE Energy Consumption report requires feedback from RAN WGs for normative work alignment
  Contentious issues
  The content of the study conclusion for KI#1 was subject to the Working Assumption at SA2#164. If the WA is challenged this may be a contentious issue for TSG SA to resolve.
  Next Steps
  Start the normative work based on the study conclusions and the WID