## Slide 1
FS_UIA_ARC, UIA_ARC
Status Report
A.I. 19.8.1 and 19.8.2
Mike Starsinic (Rapporteur)
InterDigital
S2-2411125 - 3GPP SA2#166, November 18-22 2024, Orlando, FL, USA
© 3GPP 2024

## Slide 2: FS_UIA_ARC/UIA_ARC Status at SA #106
FS_UIA_ARC Progress since SA #105
  Based on the guidance that SA Plenary endorsed in SP-241401, 1 p-CR was approved which concludes that no normative work will take place in Rel-19 for Key Issues 1, 2, and 3.
  TR 23.700-32 was sent to SA for approval.
UIA_ARC Progress since SA #105
  48 documents were submitted to SA2 #165. 11 were handled, 8 were Approved, and 3 were postponed.
  53 documents were submitted to SA2 #166. 15 were handled, 4 were Approved, 1 was postponed, 10 were noted.
  In sumary 9 CRs were approved: 1 TS 23.316 CR, 3 TS 23.501 CRs, 3 TS 23.502 CRs, and 2 TS 23.503 CRs.
Impacts and dependencies on other WGs: none identified
  None identified
Contentious Issues
  DHCPv6 Solution – A solution using DHCPv6 to associate the Non-3GPP Device Identifier with a User Plane Address.
  Optional Restriction - The optional restriction within the 5GS on max number of simultaneously active Device Identifiers per UE/5G-RG.
  Differentiation Between PDU Sessions – How to indicate, in a NAS-SM message, that the PDU Session is associated with a device identifier when the PDU Session is used by just one device.
  Triggering the Request - no approved text that discusses the case whether and how the UE/5G-RG and/or AF triggers the UE/5G-RG to request for change of QoS Flows. The default assumption would be that this is implementation based.
  An exception sheet was discussed at SA2 #166 for the for Contentious issues listed above, but no consensus on the content of the exception sheet was reached in SA2. Whether an exception is approved does not impact the content of the approved CRs.
Next Steps
  The work is complete unless an exception sheet is approved by SA Plenary (i.e. based on a company contribution).
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1020063 | Study on User Identities and Authentication Architecture | FS_UIA_ARC | 30/06/2024 | 93% | SP-231804 | 100% | 
1040085 | Identifying non-3GPP Devices Connecting behind a UE or 5G-RG | UIA_ARC | 30/12/2024 | 15% | SP-240971 | 90% | If no exception is approved at plenary, the percent complete can be changed to 100%.

## Slide 3: FS_UIA_ARC/UIA_ARC Status after SA2 #166
UIA_ARC Progress since SA2 #165
  53 documents were submitted to SA2 #166. 15 were handled, 4 were Approved, 1 was postponed, 10 were noted.
Impacts and dependencies on other WGs: none identified
  None identified
Contentious Issues
  DHCPv6 Solution – A solution using DHCPv6 to associate the Non-3GPP Device Identifier with a User Plane Address.
  Optional Restriction - The optional restriction within the 5GS on max number of simultaneously active Device Identifiers per UE/5G-RG.
  Differentiation Between PDU Sessions – How to indicate, in a NAS-SM message, that the PDU Session is associated with a device identifier when the PDU Session is used by just one device.
  Triggering the Request - no approved text that discusses the case whether and how the UE/5G-RG and/or AF triggers the UE/5G-RG to request for change of QoS Flows. The default assumption would be that this is implementation based.
  An exception sheet was discussed at SA2 #166 for the for Contentious issues listed above, but no consensus on the content of the exception sheet was reached in SA2. Whether an exception is approved does not impact the content of the approved CRs.
Next Steps
  The work is complete unless an exception sheet is approved by SA Plenary (i.e. based on a company contribution).
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1020063 | Study on User Identities and Authentication Architecture | FS_UIA_ARC | 30/06/2024 | 100% | SP-231804 | 100% | No Activity at SA2 #166
1040085 | Identifying non-3GPP Devices Connecting behind a UE or 5G-RG | UIA_ARC | 30/12/2024 | 45% | SP-240971 | 90% | If no exception is approved at plenary, the percent complete can be changed to 100%.

## Slide 4: FS_UIA_ARC/UIA_ARC Status after SA2 #165
FS_UIA_ARC Progress since SA #105
  Based on the guidance that SA Plenary endorsed in SP-241401, 1 p-CR was approved which concludes that no normative work will take place in Rel-19 for Key Issues 1, 2, and 3.
  TR 23.700-32 was sent to SA for approval.
UIA_ARC Progress since SA #105
  48 documents were submitted to SA2 #165. 11 were handled, 8 were Approved, and 3 were postponed.
Impacts and dependencies on other WGs: none identified
  None identified
Contentious Issues
  Whether the URSP Rule should be updated to include the Non-3GPP Device Identifier as a Traffic Descriptor
Issues that Require More Discussion
  Whether the PDU Session Establishment Request can include a User Plane Address.
  The optional restriction within the 5GS on max number of simultaneously active Device Identifiers per UE/5G-RG.
  Some questions about the using DHCPv6 to associate the Non-3GPP Device Identifier with a User Plane Address.
Next Steps
  Continue to progress CRs.
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1020063 | Study on User Identities and Authentication Architecture | FS_UIA_ARC | 30/06/2024 | 93% | SP-231804 | 100% | 
1040085 | Identifying non-3GPP Devices Connecting behind a UE or 5G-RG | UIA_ARC | 30/12/2024 | 15% | SP-240971 | 45% | 

## Slide 5: FS_UIA_ARC Work Plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2 #160AH-e | Jan 2024 | 0.5 | 0.5 | TR, Skeleton, TR Scope, Key Issues, Arch Assumptions
SA2#161 | Feb 2024 | 1.5 | 1.5 | Key Issue Updates (e.g. KI#4 editor’s note), Solutions
SA2#162 | Apr 2024 | 1.75 | 1.75 | Solutions that apply to a KI with no/few existing solutions in the TR (i.e. FS_UIA_ARC Key Issue #4), New solutions significantly different to existing one and proposed in a previous meeting but not handled, Solution Updates will be lower priority than KI#4 solutions and new solutions that are significantly different to existing one and proposed in a previous meeting but not handled. Time needs also to be given to papers that propose conclusions/solution principles. NOTE: During the meeting, no solution updates were handled.
SA2#163 | May 2024 | 1.5 | 1.5 | Critical Solution Updates, Complete Study Conclusions NOTE: During the meeting, no solution updates were handled.
SA2#164 | Aug 2024 | X | 1 | Request to allocate 1 TU for FS_UIA_ARC (Key Issues #1, #2, and #3).
SA2#165 | Oct 2024 | X | 0 | 1 p-CR was agreed to conclude that there will be no normative work for key issues 1, 2, and 3.
 | Total | 5.25 | 6.25 | 

## Slide 6: UIA_ARC Work Plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#164 | Aug 2024 | 0.5 | 0.5 | Handle CRs
SA2#165 | Oct 2024 | 0.5 | 1 | Handle CRs
SA2#166 | Nov 2024 | 0.5 | 1 | Continue to progress CRs: Progress postponed CRs. Resolve Editor’s Notes in Approved CRs. The optional restriction within the 5GS on max number of simultaneously active Device Identifiers per UE/5G-RG.
SA2#166-AH-e | Jan 2025 | 0 |  | If an exception is approved by plenary for any of the following topics, then the suggested allocation is: Treat 0 papers for the DHCPv6 Solution Treat 3 papers for the optional restriction Treat 2 papers for Differentiation Between PDU Sessions Treat 2 papers for Triggering the Request
SA2#167 | Feb 2026 | 0 |  | If an exception is approved by plenary for any of the following topics, then the suggested allocation is: 0.2 TU for the DHCPv6 Solution 0.2 TU for the optional restriction 0 TU for Differentiation Between PDU Sessions 0.2 TU papers for Triggering the Request
 | Total | 1.5 | 2.5 |