## Slide 1: FS_UPEAS_Ph2/UPEAS_Ph2 Status Report
Jinguo Zhu(ZTE)
Susana Sabater(Vodafone)

## Slide 2: FS_UPEAS_Ph2/UPEAS_Ph2
Progress since SA#105:
  Continue normative work at SA2#165 and SA2#166
  10 CRs are approved at SA2#165, among of them 5 CR are further revised at SA2#166, and 2 new CR approved in SA2#166.
  All key issues were completed
Impacts and dependencies on other WGs:
  None
Controversial issues:
  None
Next steps:
  maintenance
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020003 | Study on UPF enhancement for Exposure And SBA Phase 2 | FS_UPEAS_Ph2 | 06/06/2024 | 100% | SP-231795 | 100% | 
1040035 | UPF enhancement for Exposure And SBA Phase 2 | UPEAS_Ph2 | 12/12/2024 | 65% | SP-240995 | 100% | 

## Slide 3
FS_UPEAS_Ph2 Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2 #160AH-e | Jan 2024 | 0.25 | 0.25 | TR, Skeleton, TR Scope, Key Issues, Arch Assumptions
SA2#161 | Feb 2024 | 0.5 | 0.5 | Solutions
SA2#162 | Apr 2024 | 1 | 1 | Solution Updates, new solutions, Evaluations
SA2#163 | May 2024 | 0.5 | 1 | Evaluations, Conclusions
SA2#164 | Aug 2024 | 1 | 1 | Start Normative work
SA2#165 | Oct 2024 | 0.75 | 1 | Continue normative work
SA2#166 | Nov 2024 | 0.5 | 1 | Continue normative work
 | Total | 4.5 |  | 
Total 4.5 TUs
  2.25 TUs for Study Phase
  2.25 TUs for Normative Work